## Sheet1
Ticket ID | Status | Discrepancy | Submitter | Unit | Device ID | Date/Time Reported | Date/Time Acknowledged | Notification Mode | Subject | Repeat CAT 1 | Corrective Action | Asignee | Date Resolved | Root Cause | Remarks
#JTC00000397 | Hold | CAT 2 | Steve Dumont | QuantaDyn | 0 | 2018-06-13 14:11:32 | 2018-06-13 14:11:32 | None | Seam separation Ft Hood 9 ASOS | No | None | Steve Dumont |  | Root Cause - Visual Screen Damaged | Screen Damaged
#JTC00000985 | Open | CAT 2 | Robert Gaines | None | 0 | 2019-03-14 15:22:54 | 2019-03-14 15:22:54 | None | Projector 7 - Failure | No | None | Robert Gaines |  | Root Cause - Visual Projector Failure (SONY) | Projector Failure (SONY)
#JTC00000986 | Open | CAT 2 | Robert Gaines | None | 0 | 2019-03-14 15:26:45 | 2019-03-14 15:26:45 | None | Projector 8 - Failure | No | None | Robert Gaines |  | Root Cause - Visual Projector Failure (SONY) | Projector Failure (SONY)
#JTC00001000 | Open | CAT 2 | Robert Gaines | DMOC | 0 | 2019-03-20 15:50:59 | 2019-03-20 15:50:59 | None | FW: Issues with the DOME | No | None | Robert Gaines |  | Undefined | None
#JTC00001022 | Open | CAT 2 | Robert Gaines | 20th ASOS | 0 | 2019-04-01 20:47:01 | 2019-04-01 20:47:01 | Phone call inbound | Replacement RP-PC Monitor does not fit the mount | No | None | Robert Gaines |  | Root Cause - Hardware Monitor | Monitor
#JTC00001037 | New | CAT 2 | Robert Gaines | 20th ASOS | 0 | 2019-04-03 20:46:25 | 2019-04-03 20:46:25 | Phone call inbound | Ranger 47-2 is falling apart | No | None | Robert Gaines |  | Root Cause - Hardware Ranger 47 | Ranger 47
#JTC00001038 | New | CAT 2 | Robert Gaines | 20th ASOS | 0 | 2019-04-03 20:53:47 | 2019-04-03 20:53:47 | Phone call inbound | Primary game pad stopped working | No | Primary game pad failure | Robert Gaines |  | Root Cause - Hardware Gamepad | Gamepad
#JTC00000347 | Hold | CAT 2 | Devin Hoeckel | 14 ASOS | 3 | 2018-05-10 13:56:37 | 2018-05-10 13:56:37 | Web form | ASTI Radios bleeding over. | No | Issue sent to ASTi for review | Devin Hoeckel |  | Root Cause - Software ASTi Error | ASTi Error
#JTC00000581 | Hold | CAT 3 | Devin Hoeckel | 14 ASOS | 3 | 2018-10-10 19:37:11 | 2018-10-10 19:37:11 | None | IG Projctors color-blending/Focus needs to be adjusted. | No | None | Devin Hoeckel |  | Root Cause - Visual Calibration | Calibration
#JTC00000955 | Pending | CAT 2 | Skip Hamilton | 14 ASOS | 3 | 2019-02-28 20:57:08 | 2019-02-28 20:57:08 | Web form | M4 needs to be repaired/replaced, was causing EME-Server boot issues | No | Faulty M4 | Skip Hamilton |  | Root Cause - Hardware M-4 | M-4
#JTC00000910 | Hold | CAT 2 | Steve Dumont | 7 ASOS | 4 | 2019-02-13 13:24:45 | 2019-02-13 13:24:45 | Web form | Can't Calibrate Projectors through scalable; IG3 Error stating "Wrong Resolution Detected" | No | Attempted multiple fixes from two help desk agents and IDSI to resolve calibration issues. We were unable and need additional support to fix the problem | Steve Dumont |  | Root Cause - Software Scalable Error | Scalable Error
#JTC00001009 | Open | CAT 3 | Robert Gaines | 7 ASOS | 4 | 2019-03-28 18:21:25 | 2019-03-28 18:21:25 | None | Touch capability non-functional on top MVP monitor | No | MVP Top Monitor Touchscreen Capability non-functional | Robert Gaines |  | Root Cause - Hardware Monitor Cable | Monitor Cable
#JTC00001026 | New | CAT 2 | Robert Gaines | 7 ASOS | 4 | 2019-04-02 18:30:20 | 2019-04-02 18:30:20 | None | Scenarios don't load fast enough and Student 2 has lost touch screen capability | No | None | Robert Gaines |  | Undefined | None
#JTC00001034 | Pending | CAT 2 | Robert Gaines | 7 ASOS | 4 | 2019-04-03 19:52:44 | 2019-04-03 19:52:44 | None | Radio applications are locked up and failing to tansmit | No | None | Robert Gaines |  | Undefined | None
#JTC00000564 | Pending | CAT 2 | Robert Gaines | 20 ASOS | 5 | 2018-10-04 12:19:12 | 2018-10-04 12:19:12 | None | PEQ-15 from M4 #2 broken tab & PEQ-15 from M4 #1 broken mount | No | None | Robert Gaines |  | Root Cause - Hardware M-4 | M-4
#JTC00000872 | Hold | CAT 2 | Skip Hamilton | 20 ASOS | 5 | 2019-02-01 20:05:35 | 2019-02-01 20:05:35 | Web form | Ranger47 1 and 2 Mounts need to be replaced/repaired | No | Ranger 47 Screws were stripped from usage | Skip Hamilton |  | Root Cause - Other Other - See Comments | Other - See Comments
#JTC00000981 | Hold | CAT 2 | Robert Gaines | 20 ASOS | 5 | 2019-03-14 12:08:12 | 2019-03-14 12:08:12 | None | MVP VRSG shutting down | No | None | Robert Gaines |  | Root Cause - Software VRSG Error | VRSG Error
#JTC00000982 | Pending | CAT 2 | Skip Hamilton | 20 ASOS | 5 | 2019-03-14 12:11:20 | 2019-03-14 12:11:20 | Web form | Scenario Editor not opening. | No | VRSG Scenario Editor issues | Skip Hamilton |  | Root Cause - Software VRSG Error | VRSG Error
#JTC00000983 | Pending | CAT 2 | Robert Gaines | 20 ASOS | 5 | 2019-03-14 12:20:55 | 2019-03-14 12:20:55 | None | Physical Security | No | None | Robert Gaines |  | Root Cause - Other Other - See Comments | Other - See Comments
#JTC00000984 | Pending | CAT 2 | Robert Gaines | 20 ASOS | 5 | 2019-03-14 12:51:28 | 2019-03-14 12:51:28 | None | Rover Feed at Student 2 Station | No | None | Robert Gaines |  | Root Cause - Software Q-Fires ROVER Error | Q-Fires ROVER Error
#JTC00000310 | Pending | CAT 2 | Skip Hamilton | 10 ASOS | 6 | 2018-04-17 14:42:11 | 2018-04-17 14:42:11 | Web form | MVP visual height error during DMO events | No | Floating Entities during DMO on MVP Views | Skip Hamilton |  | Root Cause - Software VRSG Error | VRSG Error
#JTC00000134 | Hold | CAT 2 | Devin Hoeckel | 19 ASOS | 7 | 2018-01-08 16:57:45 | 2018-01-08 16:57:45 | None | Entities not viewable in parts of the SW US | No | None | Devin Hoeckel |  | Root Cause - Software Visual Database Discrepancy | Visual Database Discrepancy
#JTC00000224 | Pending | CAT 2 | Kyle Zamudio | 19 ASOS | 7 | 2018-03-08 21:24:00 | 2018-03-08 21:24:00 | None | ROLE Player radio transmits garbled at initial start up. | No | None | Kyle Zamudio |  | Root Cause - Software ASTi Error | ASTi Error
#JTC00000855 | Open | CAT 2 | Skip Hamilton | 19 ASOS | 7 | 2019-01-31 14:19:00 | 2019-01-31 14:19:00 | None | DOME image color and blending is very poor | No | None | Skip Hamilton |  | Root Cause - Visual Calibration | Calibration
#JTC00000897 | Pending | CAT 3 | Robert Gaines | 19 ASOS | 7 | 2019-02-08 14:53:23 | 2019-02-08 14:53:23 | None | TrackIR | No | None | Robert Gaines |  | Root Cause - Hardware TrackIR | TrackIR
#JTC00000958 | Pending | CAT 3 | Robert Gaines | 19 ASOS | 7 | 2019-03-01 14:26:53 | 2019-03-01 14:26:53 | None | IZLID cap no longer functional | No | None | Robert Gaines |  | Root Cause - Hardware IZLID | IZLID
#JTC00000991 | Pending | CAT 2 | Robert Gaines | 19 ASOS | 7 | 2019-03-14 20:32:25 | 2019-03-14 20:32:25 | None | ROVER feed | No | None | Robert Gaines |  | Undefined | None
#JTC00001008 | Open | CAT 2 | Devin Hoeckel | 19 ASOS | 7 | 2019-03-28 14:27:03 | 2019-03-28 14:27:03 | None | Incoming call from +12704619994 | No | None | Devin Hoeckel |  | Undefined | None
#JTC00000789 | Pending | CAT 3 | Devin Hoeckel | 3 ASOS, Det 1 | 8 | 2019-01-17 17:08:27 | 2019-01-17 17:08:27 | None | Dome Image Blurry | No | None | Devin Hoeckel |  | Root Cause - Visual Calibration | Calibration
#JTC00000823 | Pending | CAT 2 | Robert Gaines | 3 ASOS, Det 1 | 8 | 2019-01-25 16:05:04 | 2019-01-25 16:05:04 | None | Projector 8 not booting up and has "XOXOXO" on it. Incorrect Resolution | No | None | Robert Gaines |  | Root Cause - Visual Projector Failure (SONY) | Projector Failure (SONY)
#JTC00001001 | Pending | CAT 2 | Robert Gaines | 3 ASOS, Det 1 | 8 | 2019-03-26 19:36:00 | 2019-03-26 19:36:00 | None | IG - 8 GPU critical failure | No | GPU Failure on IG 8. Swapped with EME-Server for temp fix. Need new GPU for EME-Server | Robert Gaines |  | Root Cause - Other Other - See Comments | Other - See Comments
#JTC00001003 | Open | CAT 2 | Robert Gaines | 3 ASOS, Det 1 | 8 | 2019-03-26 19:44:32 | 2019-03-26 19:44:32 | None | DIScord Settings no Longer Function with Upgrade 2 | No | DIScord no longer works with Upgrade 2 | Robert Gaines |  | Root Cause - Software MACE Error | MACE Error
#JTC00000765 | Pending | CAT 2 | Robert Gaines | 25 ASOS | 9 | 2019-01-10 22:25:35 | 2019-01-10 22:25:35 | None | Degraded video quality from MVP VRSG | No | None | Robert Gaines |  | Root Cause - Software Q-Fires ROVER Error | Q-Fires ROVER Error
#JTC00000770 | Pending | CAT 2 | Robert Gaines | 25 ASOS | 9 | 2019-01-11 23:38:23 | 2019-01-11 23:38:23 | None | absent transporter erector launcher (TEL) in VRSG | No | None | Robert Gaines |  | Root Cause - Software Visual Database Discrepancy | Visual Database Discrepancy
#JTC00000524 | Hold | CAT 2 | Skip Hamilton | 15 ASOS | 10 | 2018-09-04 12:49:03 | 2018-09-04 12:49:03 | None | Tear in screen | No | None | Skip Hamilton |  | Root Cause - Visual Screen Damaged | Screen Damaged
#JTC00001011 | Pending | CAT 2 | Robert Gaines | 15 ASOS | 10 | 2019-03-29 11:55:15 | 2019-03-29 11:55:15 | None | EME Server will not shut down #JTC0000010 | No | None | Robert Gaines |  | Undefined | None
#JTC00000702 | Open | CAT 2 | Skip Hamilton | WPC | 11 | 2018-12-11 11:58:14 | 2018-12-11 11:58:14 | None | MVP Crashing | No | None | Skip Hamilton |  | Root Cause - Software VRSG Error | VRSG Error
#JTC00000972 | Pending | CAT 2 | Robert Gaines | WPC | 11 | 2019-03-06 13:40:32 | 2019-03-06 13:40:32 | None | RP Station INOP on NATO Secret Drives | No | None | Robert Gaines |  | Root Cause - Software MACE Error | MACE Error
#JTC00000654 | Hold | CAT 2 | Skip Hamilton | 2 ASOS | 12 | 2018-11-20 13:54:53 | 2018-11-20 13:54:53 | None | Temporary canvas replacement screen requires replacement with high-contrast screen. | No | None | Skip Hamilton |  | Root Cause - Visual Screen Damaged | Screen Damaged
#JTC00000862 | Hold | CAT 2 | Kyle Zamudio | 2 ASOS | 12 | 2019-01-31 15:45:53 | 2019-01-31 15:45:53 | None | Viewpoint attachment in dome jumps from one entitiy to another | No | None | Kyle Zamudio |  | Root Cause - Software VRSG Error | VRSG Error
#JTC00000949 | Pending | CAT 3 | Steve Dumont | 2 ASOS | 12 | 2019-02-27 16:14:57 | 2019-02-27 16:14:57 | None | Issues with Sound/ASTi Post UG2/HF | No | None | Steve Dumont |  | Root Cause - Software ASTi Error | ASTi Error
#JTC00001012 | Pending | CAT 2 | Robert Gaines | 2 ASOS | 12 | 2019-03-29 15:30:21 | 2019-03-29 15:30:21 | Mail | IOS turns on by itself | No | None | Robert Gaines |  | Root Cause - Hardware IOS PC | IOS PC
#JTC00000540 | Open | CAT 2 | Skip Hamilton | 12 CTS | 13 | 2018-09-12 21:57:01 | 2018-09-12 21:57:01 | None | Re: IG 8 surround broken / bad display port | No | None | Skip Hamilton |  | Root Cause - Visual DisplayPort Cable Failure | DisplayPort Cable Failure
#JTC00000937 | Pending | CAT 2 | Skip Hamilton | 20 ASOS, Det 1 | 14 | 2019-02-26 18:42:08 | 2019-02-26 18:42:08 | Mail | Ranger 47 2 Inoperable | No | Ranger 47 Display Issues | Skip Hamilton |  | Root Cause - Other Other - See Comments | Other - See Comments
#JTC00000168 | Hold | CAT 2 | Skip Hamilton | 6 CTS | 17 | 2018-02-08 20:30:12 | 2018-02-08 20:30:12 | None | Projector #4 image (bottom right of screen blacks out for a couple seconds or flickers and goes to a yellow/green tint over the image every 5-10 minutes | No | None | Skip Hamilton |  | Root Cause - Visual DisplayPort Cable Failure | DisplayPort Cable Failure
#JTC00000171 | Hold | CAT 2 | Skip Hamilton | 6 CTS | 17 | 2018-02-08 21:32:28 | 2018-02-08 21:32:28 | None | Projector #10 image blacks out routinely for 1-3 seconds and then comes back | No | None | Skip Hamilton |  | Root Cause - Visual DisplayPort Cable Failure | DisplayPort Cable Failure
#JTC00000625 | Pending | CAT 2 | Skip Hamilton | 6 CTS | 17 | 2018-11-07 17:10:51 | 2018-11-07 17:10:51 | None | VRSG on MVP shutting down by itself during mission | No | None | Skip Hamilton |  | Root Cause - Software VRSG Error | VRSG Error
#JTC00000626 | Pending | CAT 2 | Skip Hamilton | 6 CTS | 17 | 2018-11-07 17:11:36 | 2018-11-07 17:11:36 | None | VRSG on MVP shutting down by itself during mission | No | None | Skip Hamilton |  | Root Cause - Software VRSG Error | VRSG Error
#JTC00000740 | Hold | CAT 2 | Robert Gaines | 6 CTS | 17 | 2018-12-21 20:59:26 | 2018-12-21 20:59:26 | None | IG 1 VRSG starts up in window Mode on all 3 devices | No | None | Robert Gaines |  | Root Cause - Software VRSG Error | VRSG Error
#JTC00000775 | Hold | CAT 2 | Robert Gaines | 6 CTS | 17 | 2019-01-14 22:27:04 | 2019-01-14 22:27:04 | None | Projector #9 strobing yellow tint on entire image | No | None | Robert Gaines |  | Root Cause - Visual Projector Failure (BARCO) | Projector Failure (BARCO)
#JTC00000793 | Pending | CAT 2 | Robert Gaines | 6 CTS | 17 | 2019-01-18 19:05:31 | 2019-01-18 19:05:31 | None | RPS Targeting Pod Display Issue & MVP TGP Accuracy | No | Targeting Pod error | Robert Gaines |  | Root Cause - Software DIScover Error | DIScover Error
#JTC00000814 | Pending | CAT 2 | Skip Hamilton | 6 CTS | 17 | 2019-01-24 18:26:35 | 2019-01-24 18:26:35 | None | Projector # 7 goes to stand by mode every 10 minutes, image turns black | No | None | Skip Hamilton |  | Root Cause - Visual Projector Failure (BARCO) | Projector Failure (BARCO)
#JTC00000815 | Open | CAT 2 | Robert Gaines | 6 CTS | 17 | 2019-01-24 18:28:07 | 2019-01-24 18:28:07 | None | Pilot Station MACE shuts down by itself during mission | No | None | Robert Gaines |  | Root Cause - Software MACE Error | MACE Error
#JTC00000816 | Hold | CAT 2 | Robert Gaines | 6 CTS | 17 | 2019-01-24 18:29:24 | 2019-01-24 18:29:24 | None | Pilot Station VRSG closes by itself during missions | No | None | Robert Gaines |  | Root Cause - Software VRSG Error | VRSG Error
#JTC00000912 | Pending | CAT 2 | Skip Hamilton | 6 CTS | 17 | 2019-02-13 22:05:17 | 2019-02-13 22:05:17 | Web form | Student 1, M41 firing by itself rapid fire | No | None | Skip Hamilton |  | Root Cause - Hardware M-4 | M-4
#JTC00000971 | Pending | CAT 3 | Robert Gaines | 6 CTS | 17 | 2019-03-05 19:36:30 | 2019-03-05 19:36:30 | None | Systems 15, 16, 17 have old AAJTS display cables | No | None | Robert Gaines |  | Root Cause - Visual DisplayPort Cable Failure | DisplayPort Cable Failure
#JTC00000261 | Pending | CAT 3 | Robert Gaines | 5 ASOS | 18 | 2018-03-27 17:26:43 | 2018-03-27 17:26:43 | None | MACE sound scripting does not work properly with ASTi radios | No | None | Robert Gaines |  | Root Cause - Software MACE Error | MACE Error
#JTC00000605 | Hold | CAT 2 | Robert Gaines | 5 ASOS | 18 | 2018-10-26 21:37:36 | 2018-10-26 21:37:36 | None | M4 #1 continuously fires in MACE | No | None | Robert Gaines |  | Root Cause - Hardware M-4 | M-4
#JTC00000650 | Pending | CAT 2 | Robert Gaines | 5 ASOS | 18 | 2018-11-19 16:33:42 | 2018-11-19 16:33:42 | None | VRSG Remote fails to consistently update the terrain search path | No | None | Robert Gaines |  | Root Cause - Software DOC Error | DOC Error
#JTC00000671 | Pending | CAT 2 | Robert Gaines | 5 ASOS | 18 | 2018-11-27 23:25:58 | 2018-11-27 23:25:58 | None | Q-Fires Rover Crashing | No | None | Robert Gaines |  | Root Cause - Software Q-Fires ROVER Error | Q-Fires ROVER Error
#JTC00000687 | Hold | CAT 2 | Robert Gaines | 5 ASOS | 18 | 2018-12-05 15:43:54 | 2018-12-05 15:43:54 | None | MVP VRSG Crash | No | None | Robert Gaines |  | Root Cause - Software VRSG Error | VRSG Error
#JTC00000717 | Hold | CAT 2 | Robert Gaines | 5 ASOS | 18 | 2018-12-14 15:51:59 | 2018-12-14 15:51:59 | None | Grids unreadable on student and RPS ROVER displays | No | Targeting Pod Plugin | Robert Gaines |  | Root Cause - Software DIScover Error | DIScover Error
#JTC00000873 | Hold | CAT 3 | Devin Hoeckel | 5 ASOS | 18 | 2019-02-01 23:51:12 | 2019-02-01 23:51:12 | None | MACE maintenance expired | No | None | Devin Hoeckel |  | Root Cause - Software MACE Error | MACE Error
#JTC00000965 | Pending | CAT 2 | Robert Gaines | 5 ASOS | 18 | 2019-03-01 22:02:29 | 2019-03-01 22:02:29 | None | Sound levels | No | None | Robert Gaines |  | Root Cause - Software ASTi Error | ASTi Error
#JTC00000980 | Pending | CAT 3 | Robert Gaines | 5 ASOS | 18 | 2019-03-13 14:11:23 | 2019-03-13 14:11:23 | None | MACE Detonation Tool Sound - Faulty Sound Mapping | No | None | Robert Gaines |  | Root Cause - Software ASTi Error | ASTi Error
#JTC00001006 | Open | CAT 3 | Robert Gaines | 5 ASOS | 18 | 2019-03-27 19:25:15 | 2019-03-27 19:25:15 | None | Multiple crashes during a DMO event | No | None | Robert Gaines |  | Undefined | None
#JTC00000568 | Hold | CAT 2 | Robert Gaines | 23 STS | 19 | 2018-10-05 17:21:05 | 2018-10-05 17:21:05 | None | IG & Proj 4 having resolution issues and IOS is randoly booting up overnight after system shutdown | No | None | Robert Gaines |  | Root Cause - Visual Surround Error | Surround Error
#JTC00000975 | Hold | CAT 2 | Steve Dumont | STTS | 20 | 2019-03-07 16:38:28 | 2019-03-07 16:38:28 | Web form | Runaway M-4 Carbine #1; device fires autonomously--need a replacement and repairs on faulty device | No | Trigger pressure sensor is presumed to be faulty | Steve Dumont |  | Root Cause - Hardware M-4 | M-4
#JTC00001013 | Hold | CAT 2 | Steve Dumont | STTS | 20 | 2019-03-29 19:44:51 | 2019-03-29 19:44:51 | Web form | Runaway M-4 Carbine #2; device fires autonomously--repairs needed | No | Brian's 2nd M4 is now faulty and needs repairs. Will submit FR report | Steve Dumont |  | Root Cause - Hardware M-4 | M-4
#JTC00000926 | Pending | CAT 2 | Robert Gaines | 13 ASOS | 21 | 2019-02-22 21:02:25 | 2019-02-22 21:02:25 | None | Student Station won't pick up MVP ROVER feed | No | None | Robert Gaines |  | Root Cause - Software Q-Fires ROVER Error | Q-Fires ROVER Error
#JTC00000963 | Pending | CAT 3 | Devin Hoeckel | 13 ASOS | 21 | 2019-03-01 17:33:59 | 2019-03-01 17:33:59 | None | LED Tasklight has stopped working | No | None | Devin Hoeckel |  | Root Cause - Hardware Desk Light | Desk Light
#JTC00000993 | Pending | CAT 3 | Robert Gaines | 13 ASOS | 21 | 2019-03-18 15:37:56 | 2019-03-18 15:37:56 | None | DAT Switch exhibits abnormal behavior - failure possible | No | None | Robert Gaines |  | Undefined | None
#JTC00000883 | Hold | CAT 2 | Skip Hamilton | 9 ASOS | 22 | 2019-02-06 17:21:50 | 2019-02-06 17:21:50 | None | Projector 8 randomly switches to NVG mode, then back to correct mode of Scenario | No | None | Skip Hamilton |  | Root Cause - Visual Projector Failure (SONY) | Projector Failure (SONY)
#JTC00000920 | Hold | CAT 2 | Steve Dumont | 9 ASOS | 22 | 2019-02-21 01:23:20 | 2019-02-21 01:23:20 | Web form | IG8/PRJ8 Projector Cable Faulty; troubleshot cables and identified single cable non functional--restored comms using single cable 4096x2160@29hz | No | Cables are out of stock | Steve Dumont |  | Root Cause - Hardware Monitor Cable | Monitor Cable
#JTC00000943 | Hold | CAT 3 | Steve Dumont | 9 ASOS | 22 | 2019-02-26 21:12:18 | 2019-02-26 21:12:18 | None | Shutter function not working from DOC to turn off light emissions from projectors | No | None | Steve Dumont |  | Root Cause - Visual Projector Failure (SONY) | Projector Failure (SONY)
#JTC00000849 | Hold | CAT 2 | Steve Dumont | 607 ASOG | 26 | 2019-01-30 11:38:38 | 2019-01-30 11:38:38 | Web form | IG 8 has a faulty dp cable | No | Waiting for SIM OPR to confirm new cable was recieved | Steve Dumont |  | Root Cause - Hardware Monitor Cable | Monitor Cable
#JTC00000979 | Pending | CAT 2 | Robert Gaines | 607 ASOG | 26 | 2019-03-13 05:01:07 | 2019-03-13 05:01:07 | None | black dot in the visual of ranger 1 | No | None | Robert Gaines |  | Root Cause - Hardware Ranger 47 | Ranger 47