## Sheet1
Ticket ID | Status | Discrepancy | Submitter | Unit | Device ID | Date/Time Reported | Date/Time Acknowledged | Notification Mode | Subject | Repeat CAT 1 | Corrective Action | Asignee | Date Rsolved | Root Cause | Remarks
#JTC00000134 | Hold | CAT 2 | Devin Hoeckel | 19 ASOS | ['No'] | 2018-01-08 16:57:45 | 2018-01-08 16:57:45 | None | Entities not viewable in parts of the SW US | 7 | None | Devin Hoeckel | 2018-01-08 | Root Cause - Software Visual Database Discrepancy
#JTC00000168 | Hold | CAT 2 | Skip Hamilton | 6 CTS | ['No'] | 2018-02-08 20:30:12 | 2018-02-08 20:30:12 | None | Projector #4 image (bottom right of screen blacks out for a couple seconds or flickers and goes to a yellow/green tint over the image every 5-10 minutes | 16 | None | Skip Hamilton | 2018-02-08 | Root Cause - Visual DisplayPort Cable Failure
#JTC00000171 | Hold | CAT 2 | Skip Hamilton | 6 CTS | ['No'] | 2018-02-08 21:32:28 | 2018-02-08 21:32:28 | None | Projector #10 image blacks out routinely for 1-3 seconds and then comes back | 16 | None | Skip Hamilton | 2018-02-08 | Root Cause - Visual DisplayPort Cable Failure
#JTC00000206 | Solved | CAT 2 | Chris Johnson | 20 ASOS | None | 2018-03-01 19:48:23 | 2018-03-01 19:48:23 | None | BAD Feb Update disk | [] | None | Chris Johnson | 2018-03-01 | Undefined
#JTC00000207 | Solved | CAT 2 | Devin Hoeckel | 14 ASOS | [] | 2018-03-02 16:17:42 | 2018-03-02 16:17:42 | Web form | ASTi freq bleed over | 3 | ASTi Radios Bleeding over during DMO events. Only site to report such activity and is captured in a different ticket | Devin Hoeckel | 2018-03-02 | Root Cause - Software ASTi Error
#JTC00000208 | Solved | CAT 2 | Devin Hoeckel | WPC | None | 2018-03-02 16:29:21 | 2018-03-02 16:29:21 | None | IZLID Com Failure | [] | None | Devin Hoeckel | 2018-03-02 | Undefined
#JTC00000209 | Solved | CAT 2 | Chris Johnson | WPC | None | 2018-03-02 16:36:57 | 2018-03-02 16:36:57 | None | Ground based laser spot does not show in targeting pod view. | [] | None | Chris Johnson | 2018-03-02 | Undefined
#JTC00000210 | Solved | CAT 3 | Chris Johnson | 5 ASOS | None | 2018-03-02 23:00:21 | 2018-03-02 23:00:21 | None | Helpdesk migration | [] | None | Chris Johnson | 2018-03-02 | Undefined
#JTC00000211 | Solved | CAT 3 | Devin Hoeckel | 5 ASOS | None | 2018-03-02 23:07:13 | 2018-03-02 23:07:13 | None | Korea Terrain Database | [] | None | Devin Hoeckel | 2018-03-02 | Undefined
#JTC00000212 | Solved | CAT 2 | Devin Hoeckel | 5 ASOS | None | 2018-03-03 01:07:30 | 2018-03-03 01:07:30 | None | Ranger 47 lock up | [] | None | Devin Hoeckel | 2018-03-03 | Undefined
#JTC00000213 | Solved | CAT 3 | Chris Johnson | 20 ASOS, Det 1 | None | 2018-03-05 21:17:43 | 2018-03-05 21:17:43 | None | Updates | [] | None | Chris Johnson | 2018-03-05 | Undefined
#JTC00000214 | Solved | CAT 2 | Devin Hoeckel | 20 ASOS, Det 1 | None | 2018-03-05 21:19:25 | 2018-03-05 21:19:25 | None | IZLID | [] | None | Devin Hoeckel | 2018-03-05 | Undefined
#JTC00000215 | Solved | CAT 2 | Chris Johnson | 5 ASOS | None | 2018-03-06 20:14:29 | 2018-03-06 20:14:29 | None | Projectors blinking in and out | [] | None | Chris Johnson | 2018-03-06 | Undefined
#JTC00000216 | Solved | CAT 1 | Chris Johnson | 10 ASOS | None | 2018-03-06 21:14:01 | 2018-03-06 21:14:01 | None | Sony Projector login | [] | None | Chris Johnson | 2018-03-06 | Undefined
#JTC00000217 | Solved | CAT 1 | Chris Johnson | 10 ASOS | None | 2018-03-07 15:24:13 | 2018-03-07 15:24:13 | None | Projector blending | [] | None | Chris Johnson | 2018-03-07 | Undefined
#JTC00000218 | Solved | CAT 1 | Chris Johnson | 10 ASOS | None | 2018-03-07 15:25:17 | 2018-03-07 15:25:17 | None | Prjoector recalibration | [] | None | Chris Johnson | 2018-03-07 | Undefined
#JTC00000219 | Solved | CAT 2 | Chris Johnson | 5 ASOS | None | 2018-03-07 15:59:53 | 2018-03-07 15:59:53 | None | DMO operations | [] | None | Chris Johnson | 2018-03-07 | Undefined
#JTC00000220 | Solved | CAT 2 | Devin Hoeckel | 5 ASOS | None | 2018-03-07 17:16:45 | 2018-03-07 17:16:45 | None | VRSG problems after editing terrain | [] | None | Devin Hoeckel | 2018-03-07 | Undefined
#JTC00000221 | Solved | CAT 2 | Chris Johnson | 5 ASOS | None | 2018-03-07 17:20:58 | 2018-03-07 17:20:58 | None | Projectors blinking in and out | [] | None | Chris Johnson | 2018-03-07 | Undefined
#JTC00000222 | Solved | CAT 1 | Chris Johnson | 20 ASOS, Det 1 | None | 2018-03-08 17:27:00 | 2018-03-08 17:27:00 | None | Projector Issue | [] | None | Chris Johnson | 2018-03-08 | Undefined
#JTC00000223 | Solved | CAT 3 | Chris Johnson | 13 ASOS | None | 2018-03-08 19:09:49 | 2018-03-08 19:09:49 | None | Create Password | [] | None | Chris Johnson | 2018-03-08 | Undefined
#JTC00000224 | Pending | CAT 2 | Kyle Zamudio | 19 ASOS | ['No'] | 2018-03-08 21:24:00 | 2018-03-08 21:24:00 | None | ROLE Player radio transmits garbled at initial start up. | 7 | None | Kyle Zamudio | 2018-03-08 | Root Cause - Software ASTi Error
#JTC00000225 | Solved | CAT 3 | Chris Johnson | 20 ASOS, Det 1 | None | 2018-03-09 19:35:50 | 2018-03-09 19:35:50 | None | NESSUS results | [] | None | Chris Johnson | 2018-03-09 | Undefined
#JTC00000226 | Solved | CAT 2 | Chris Johnson | 6 CTS | None | 2018-03-09 19:58:07 | 2018-03-09 19:58:07 | None | Black spot in Ranger | [] | None | Chris Johnson | 2018-03-09 | Undefined
#JTC00000227 | Solved | CAT 1 | Devin Hoeckel | 2 ASOS | None | 2018-03-09 20:05:31 | 2018-03-09 20:05:31 | None | Dome display is not synched on over 50% of dome | [] | None | Devin Hoeckel | 2018-03-09 | Undefined
#JTC00000228 | Solved | CAT 3 | Chris Johnson | WPC | None | 2018-03-13 15:40:24 | 2018-03-13 15:40:24 | None | Need number other than 877 help desk number | [] | None | Chris Johnson | 2018-03-13 | Undefined
#JTC00000229 | Solved | CAT 2 | Chris Johnson | WPC | None | 2018-03-13 15:52:20 | 2018-03-13 15:52:20 | None | Help | [] | None | Chris Johnson | 2018-03-13 | Undefined
#JTC00000230 | Solved | CAT 2 | Chris Johnson | 5 ASOS | None | 2018-03-13 19:51:12 | 2018-03-13 19:51:12 | None | Ranger 47 not tracking | [] | None | Chris Johnson | 2018-03-13 | Undefined
#JTC00000231 | Solved | CAT 2 | Devin Hoeckel | 2 ASOS | None | 2018-03-14 15:27:19 | 2018-03-14 15:27:19 | None | Incoming call from +4971170731200 | [] | None | Devin Hoeckel | 2018-03-14 | Undefined
#JTC00000232 | Solved | CAT 2 | Chris Johnson | 19 ASOS | None | 2018-03-14 20:33:10 | 2018-03-14 20:33:10 | None | ROLE PLAYER POD | [] | None | Chris Johnson | 2018-03-14 | Undefined
#JTC00000233 | Solved | CAT 2 | Devin Hoeckel | WPC | None | 2018-03-15 13:09:39 | 2018-03-15 13:09:39 | None | IOS WakeON issue | [] | None | Devin Hoeckel | 2018-03-15 | Undefined
#JTC00000234 | Solved | CAT 2 | Chris Johnson | 5 ASOS | None | 2018-03-15 21:37:44 | 2018-03-15 21:37:44 | None | Ranger locked up and more | [] | None | Chris Johnson | 2018-03-15 | Undefined
#JTC00000235 | Solved | CAT 2 | Chris Johnson | 5 ASOS | None | 2018-03-15 21:41:15 | 2018-03-15 21:41:15 | None | Cloud coverage displays improperly in ROVER view | [] | None | Chris Johnson | 2018-03-15 | Undefined
#JTC00000236 | Solved | CAT 3 | Chris Johnson | 5 ASOS | None | 2018-03-15 21:52:37 | 2018-03-15 21:52:37 | None | Scripting radio traffic | [] | None | Chris Johnson | 2018-03-15 | Undefined
#JTC00000237 | Solved | CAT 2 | Chris Johnson | 25 ASOS | None | 2018-03-20 21:48:19 | 2018-03-20 21:48:19 | None | Feb 18 Scans and Update files | [] | None | Chris Johnson | 2018-03-20 | Undefined
#JTC00000238 | Solved | CAT 2 | Chris Johnson | 5 ASOS | None | 2018-03-21 14:41:31 | 2018-03-21 14:41:31 | None | VRSG on MVP | [] | None | Chris Johnson | 2018-03-21 | Undefined
#JTC00000239 | Solved | CAT 3 | Chris Johnson | 5 ASOS | None | 2018-03-21 15:29:16 | 2018-03-21 15:29:16 | None | UPS battery | [] | None | Chris Johnson | 2018-03-21 | Undefined
#JTC00000240 | Solved | CAT 2 | Devin Hoeckel | 6 CTS | None | 2018-03-21 15:37:51 | 2018-03-21 15:37:51 | None | Comm Panels /foot pedals at MVP and IOS shorting out monitors, no transmit, or constant transmit | [] | None | Devin Hoeckel | 2018-03-21 | Undefined
#JTC00000241 | Solved | CAT 2 | Chris Johnson | 6 CTS | None | 2018-03-21 15:41:43 | 2018-03-21 15:41:43 | None | In-dome volume insane. | [] | None | Chris Johnson | 2018-03-21 | Undefined
#JTC00000242 | Solved | CAT 2 | Chris Johnson | 13 ASOS | None | 2018-03-21 18:57:21 | 2018-03-21 18:57:21 | None | Sys #21 IG-2 not projecting image | [] | None | Chris Johnson | 2018-03-21 | Undefined
#JTC00000243 | Solved | CAT 2 | Chris Johnson | 13 ASOS | None | 2018-03-21 19:06:55 | 2018-03-21 19:06:55 | None | IG-2 will not open and produce an image | [] | None | Chris Johnson | 2018-03-21 | Undefined
#JTC00000244 | Solved | CAT 1 | Devin Hoeckel | 25 ASOS | None | 2018-03-21 20:18:29 | 2018-03-21 20:18:29 | None | VRSG does not display correctly in dome | [] | None | Devin Hoeckel | 2018-03-21 | Undefined
#JTC00000245 | Solved | CAT 2 | Devin Hoeckel | 19 ASOS | None | 2018-03-21 20:31:23 | 2018-03-21 20:31:23 | None | EME equipment is showing up under the ground | [] | None | Devin Hoeckel | 2018-03-21 | Undefined
#JTC00000246 | Solved | CAT 2 | Devin Hoeckel | 19 ASOS | None | 2018-03-21 20:38:00 | 2018-03-21 20:38:00 | None | A/C are splitting into duobles | [] | None | Devin Hoeckel | 2018-03-21 | Undefined
#JTC00000247 | Solved | CAT 2 | Devin Hoeckel | 13 ASOS | None | 2018-03-21 21:54:25 | 2018-03-21 21:54:25 | None | Incoming call from +17195240044 | [] | None | Devin Hoeckel | 2018-03-21 | Undefined
#JTC00000248 | Solved | CAT 3 | Chris Johnson | 5 ASOS | None | 2018-03-22 14:33:24 | 2018-03-22 14:33:24 | None | monthly cyber security package | [] | None | Chris Johnson | 2018-03-22 | Undefined
#JTC00000249 | Solved | CAT 2 | Chris Johnson | 19 ASOS | None | 2018-03-22 14:36:37 | 2018-03-22 14:36:37 | None | Incoming call from +12704619994 | [] | None | Chris Johnson | 2018-03-22 | Undefined
#JTC00000250 | Solved | CAT 2 | Chris Johnson | 5 ASOS | None | 2018-03-22 15:55:55 | 2018-03-22 15:55:55 | None | Voisus Comm panel display a NO ROLE SET | [] | None | Chris Johnson | 2018-03-22 | Undefined
#JTC00000251 | Solved | CAT 2 | Chris Johnson | 5 ASOS | None | 2018-03-22 16:05:19 | 2018-03-22 16:05:19 | None | Incoming call from +12539670181 | [] | None | Chris Johnson | 2018-03-22 | Undefined
#JTC00000252 | Solved | CAT 2 | Chris Johnson | 5 ASOS | None | 2018-03-22 16:31:20 | 2018-03-22 16:31:20 | None | Incoming call from +12539670181 | [] | None | Chris Johnson | 2018-03-22 | Undefined
#JTC00000253 | Solved | CAT 2 | Devin Hoeckel | 13 ASOS | None | 2018-03-22 17:24:24 | 2018-03-22 17:24:24 | None | Incoming call from +17195240044 | [] | None | Devin Hoeckel | 2018-03-22 | Undefined
#JTC00000254 | Solved | CAT 2 | Chris Johnson | 7 ASOS | None | 2018-03-22 17:33:41 | 2018-03-22 17:33:41 | None | VRSG license expire | [] | None | Chris Johnson | 2018-03-22 | Undefined
#JTC00000255 | Solved | CAT 2 | Chris Johnson | 15 ASOS | None | 2018-03-23 21:40:51 | 2018-03-23 21:40:51 | None | Unable to connect to Security Center through Web Interface | [] | None | Chris Johnson | 2018-03-23 | Undefined
#JTC00000256 | Solved | CAT 2 | Chris Johnson | 5 ASOS | None | 2018-03-23 23:31:50 | 2018-03-23 23:31:50 | None | Ranger locked up | [] | None | Chris Johnson | 2018-03-23 | Undefined
#JTC00000257 | Solved | CAT 2 | Devin Hoeckel | 15 ASOS | None | 2018-03-26 12:08:18 | 2018-03-26 12:08:18 | None | ISO is Off Line | [] | None | Devin Hoeckel | 2018-03-26 | Undefined
#JTC00000258 | Solved | CAT 2 | Devin Hoeckel | 19 ASOS | None | 2018-03-26 13:06:14 | 2018-03-26 13:06:14 | None | Scalable coming up with error message, won't run. | [] | None | Devin Hoeckel | 2018-03-26 | Undefined
#JTC00000259 | Solved | CAT 1 | Chris Johnson | 25 ASOS | None | 2018-03-26 22:41:49 | 2018-03-26 22:41:49 | None | March Updates Wheeler AAF HI | [] | None | Chris Johnson | 2018-03-26 | Undefined
#JTC00000260 | Solved | CAT 2 | Chris Johnson | 15 ASOS | None | 2018-03-27 12:24:03 | 2018-03-27 12:24:03 | None | ACAS Scans | [] | None | Chris Johnson | 2018-03-27 | Undefined
#JTC00000261 | Pending | CAT 3 | Robert Gaines | 5 ASOS | ['No'] | 2018-03-27 17:26:43 | 2018-03-27 17:26:43 | None | MACE sound scripting does not work properly with ASTi radios | 18 | None | Robert Gaines | 2018-03-27 | Root Cause - Software MACE Error
#JTC00000262 | Solved | CAT 2 | Chris Johnson | 13 ASOS | None | 2018-03-27 19:19:15 | 2018-03-27 19:19:15 | None | Projector 1 won't turn on | [] | None | Chris Johnson | 2018-03-27 | Undefined
#JTC00000263 | Solved | CAT 2 | Chris Johnson | 25 ASOS | None | 2018-03-28 22:14:08 | 2018-03-28 22:14:08 | None | Projector 1 not working | [] | None | Chris Johnson | 2018-03-28 | Undefined
#JTC00000264 | Solved | CAT 3 | Devin Hoeckel | 5 ASOS | None | 2018-03-29 16:43:37 | 2018-03-29 16:43:37 | None | Anchor issue | [] | None | Devin Hoeckel | 2018-03-29 | Undefined
#JTC00000310 | Pending | CAT 2 | Skip Hamilton | 10 ASOS | ['No'] | 2018-04-17 14:42:11 | 2018-04-17 14:42:11 | Web form | MVP visual height error during DMO events | 6 | Floating Entities during DMO on MVP Views | Skip Hamilton | 2019-04-01 | Root Cause - Software VRSG Error
#JTC00000347 | Hold | CAT 2 | Devin Hoeckel | 14 ASOS | ['No'] | 2018-05-10 13:56:37 | 2018-05-10 13:56:37 | Web form | ASTI Radios bleeding over. | 3 | Issue sent to ASTi for review | Devin Hoeckel | 2018-05-10 | Root Cause - Software ASTi Error
#JTC00000397 | Hold | CAT 2 | Steve Dumont | QuantaDyn | ['No'] | 2018-06-13 14:11:32 | 2018-06-13 14:11:32 | None | Seam separation Ft Hood 9 ASOS | 22 | None | Steve Dumont | 2018-06-13 | Root Cause - Visual Screen Damaged
#JTC00000524 | Hold | CAT 2 | Skip Hamilton | 15 ASOS | ['No'] | 2018-09-04 12:49:03 | 2018-09-04 12:49:03 | None | Tear in screen | 10 | None | Skip Hamilton | 2018-09-04 | Root Cause - Visual Screen Damaged
#JTC00000540 | Open | CAT 2 | Skip Hamilton | 12 CTS | ['No'] | 2018-09-12 21:57:01 | 2018-09-12 21:57:01 | None | Re: IG 8 surround broken / bad display port | 13 | None | Skip Hamilton | 2018-09-12 | Root Cause - Visual DisplayPort Cable Failure
#JTC00000564 | Pending | CAT 2 | Robert Gaines | 20 ASOS | ['No'] | 2018-10-04 12:19:12 | 2018-10-04 12:19:12 | None | PEQ-15 from M4 #2 broken tab & PEQ-15 from M4 #1 broken mount | 5 | None | Robert Gaines | 2018-10-04 | Root Cause - Hardware M-4
#JTC00000568 | Hold | CAT 2 | Robert Gaines | 23 STS | ['No'] | 2018-10-05 17:21:05 | 2018-10-05 17:21:05 | None | IG & Proj 4 having resolution issues and IOS is randoly booting up overnight after system shutdown | 19 | None | Robert Gaines | 2018-10-05 | Root Cause - Visual Surround Error
#JTC00000581 | Hold | CAT 3 | Devin Hoeckel | 14 ASOS | ['No'] | 2018-10-10 19:37:11 | 2018-10-10 19:37:11 | None | IG Projctors color-blending/Focus needs to be adjusted. | 3 | None | Devin Hoeckel | 2018-10-10 | Root Cause - Visual Calibration
#JTC00000605 | Hold | CAT 2 | Robert Gaines | 5 ASOS | ['No'] | 2018-10-26 21:37:36 | 2018-10-26 21:37:36 | None | M4 #1 continuously fires in MACE | 18 | None | Robert Gaines | 2018-10-26 | Root Cause - Hardware M-4
#JTC00000625 | Pending | CAT 2 | Skip Hamilton | 6 CTS | ['No'] | 2018-11-07 17:10:51 | 2018-11-07 17:10:51 | None | VRSG on MVP shutting down by itself during mission | 15 | None | Skip Hamilton | 2018-11-07 | Root Cause - Software VRSG Error
#JTC00000626 | Pending | CAT 2 | Skip Hamilton | 6 CTS | ['No'] | 2018-11-07 17:11:36 | 2018-11-07 17:11:36 | None | VRSG on MVP shutting down by itself during mission | 16 | None | Skip Hamilton | 2018-11-07 | Root Cause - Software VRSG Error
#JTC00000650 | Pending | CAT 2 | Robert Gaines | 5 ASOS | ['No'] | 2018-11-19 16:33:42 | 2018-11-19 16:33:42 | None | VRSG Remote fails to consistently update the terrain search path | 18 | None | Robert Gaines | 2018-11-19 | Root Cause - Software DOC Error
#JTC00000654 | Hold | CAT 2 | Skip Hamilton | 2 ASOS | ['No'] | 2018-11-20 13:54:53 | 2018-11-20 13:54:53 | None | Temporary canvas replacement screen requires replacement with high-contrast screen. | 12 | None | Skip Hamilton | 2018-11-20 | Root Cause - Visual Screen Damaged
#JTC00000671 | Pending | CAT 2 | Robert Gaines | 5 ASOS | ['No'] | 2018-11-27 23:25:58 | 2018-11-27 23:25:58 | None | Q-Fires Rover Crashing | 18 | None | Robert Gaines | 2018-11-27 | Root Cause - Software Q-Fires ROVER Error
#JTC00000687 | Hold | CAT 2 | Robert Gaines | 5 ASOS | ['No'] | 2018-12-05 15:43:54 | 2018-12-05 15:43:54 | None | MVP VRSG Crash | 18 | None | Robert Gaines | 2018-12-05 | Root Cause - Software VRSG Error
#JTC00000702 | Open | CAT 2 | Skip Hamilton | WPC | ['No'] | 2018-12-11 11:58:14 | 2018-12-11 11:58:14 | None | MVP Crashing | 11 | None | Skip Hamilton | 2018-12-11 | Root Cause - Software VRSG Error
#JTC00000717 | Hold | CAT 2 | Robert Gaines | 5 ASOS | ['No'] | 2018-12-14 15:51:59 | 2018-12-14 15:51:59 | None | Grids unreadable on student and RPS ROVER displays | 18 | Targeting Pod Plugin | Robert Gaines | 2018-12-14 | Root Cause - Software DIScover Error
#JTC00000740 | Hold | CAT 2 | Robert Gaines | 6 CTS | ['No'] | 2018-12-21 20:59:26 | 2018-12-21 20:59:26 | None | IG 1 VRSG starts up in window Mode on all 3 devices | 15 | None | Robert Gaines | 2018-12-21 | Root Cause - Software VRSG Error
#JTC00000765 | Pending | CAT 2 | Robert Gaines | 25 ASOS | ['No'] | 2019-01-10 22:25:35 | 2019-01-10 22:25:35 | None | Degraded video quality from MVP VRSG | 9 | None | Robert Gaines | 2019-01-10 | Root Cause - Software Q-Fires ROVER Error
#JTC00000770 | Pending | CAT 2 | Robert Gaines | 25 ASOS | ['No'] | 2019-01-11 23:38:23 | 2019-01-11 23:38:23 | None | absent transporter erector launcher (TEL) in VRSG | 9 | None | Robert Gaines | 2019-01-11 | Root Cause - Software Visual Database Discrepancy
#JTC00000775 | Hold | CAT 2 | Robert Gaines | 6 CTS | ['No'] | 2019-01-14 22:27:04 | 2019-01-14 22:27:04 | None | Projector #9 strobing yellow tint on entire image | 17 | None | Robert Gaines | 2019-01-14 | Root Cause - Visual Projector Failure (BARCO)
#JTC00000789 | Pending | CAT 3 | Devin Hoeckel | 3 ASOS, Det 1 | ['No'] | 2019-01-17 17:08:27 | 2019-01-17 17:08:27 | None | Dome Image Blurry | 8 | None | Devin Hoeckel | 2019-03-26 | Root Cause - Visual Calibration
#JTC00000793 | Pending | CAT 2 | Robert Gaines | 6 CTS | ['No'] | 2019-01-18 19:05:31 | 2019-01-18 19:05:31 | None | RPS Targeting Pod Display Issue & MVP TGP Accuracy | 16 | Targeting Pod error | Robert Gaines | 2019-01-18 | Root Cause - Software DIScover Error
#JTC00000814 | Pending | CAT 2 | Skip Hamilton | 6 CTS | ['No'] | 2019-01-24 18:26:35 | 2019-01-24 18:26:35 | None | Projector # 7 goes to stand by mode every 10 minutes, image turns black | 16 | None | Skip Hamilton | 2019-01-24 | Root Cause - Visual Projector Failure (BARCO)
#JTC00000815 | Open | CAT 2 | Robert Gaines | 6 CTS | ['No'] | 2019-01-24 18:28:07 | 2019-01-24 18:28:07 | None | Pilot Station MACE shuts down by itself during mission | 16 | None | Robert Gaines | 2019-01-24 | Root Cause - Software MACE Error
#JTC00000816 | Hold | CAT 2 | Robert Gaines | 6 CTS | ['No'] | 2019-01-24 18:29:24 | 2019-01-24 18:29:24 | None | Pilot Station VRSG closes by itself during missions | 16 | None | Robert Gaines | 2019-01-24 | Root Cause - Software VRSG Error
#JTC00000823 | Pending | CAT 2 | Robert Gaines | 3 ASOS, Det 1 | ['No'] | 2019-01-25 16:05:04 | 2019-01-25 16:05:04 | None | Projector 8 not booting up and has "XOXOXO" on it. Incorrect Resolution | 8 | None | Robert Gaines | 2019-03-26 | Root Cause - Visual Projector Failure (SONY)
#JTC00000849 | Hold | CAT 2 | Steve Dumont | 607 ASOG | ['No'] | 2019-01-30 11:38:38 | 2019-01-30 11:38:38 | Web form | IG 8 has a faulty dp cable | 26 | Waiting for SIM OPR to confirm new cable was recieved | Steve Dumont | 2019-01-30 | Root Cause - Hardware Monitor Cable
#JTC00000855 | Open | CAT 2 | Skip Hamilton | 19 ASOS | ['No'] | 2019-01-31 14:19:00 | 2019-01-31 14:19:00 | None | DOME image color and blending is very poor | 7 | None | Skip Hamilton | 2019-01-31 | Root Cause - Visual Calibration
#JTC00000862 | Hold | CAT 2 | Kyle Zamudio | 2 ASOS | ['No'] | 2019-01-31 15:45:53 | 2019-01-31 15:45:53 | None | Viewpoint attachment in dome jumps from one entitiy to another | 12 | None | Kyle Zamudio | 2019-01-31 | Root Cause - Software VRSG Error
#JTC00000872 | Hold | CAT 2 | Skip Hamilton | 20 ASOS | ['No'] | 2019-02-01 20:05:35 | 2019-02-01 20:05:35 | Web form | Ranger47 1 and 2 Mounts need to be replaced/repaired | 5 | Ranger 47 Screws were stripped from usage | Skip Hamilton | 2019-02-01 | Root Cause - Other Other - See Comments
#JTC00000873 | Hold | CAT 3 | Devin Hoeckel | 5 ASOS | ['No'] | 2019-02-01 23:51:12 | 2019-02-01 23:51:12 | None | MACE maintenance expired | 18 | None | Devin Hoeckel | 2019-02-01 | Root Cause - Software MACE Error
#JTC00000883 | Hold | CAT 2 | Skip Hamilton | 9 ASOS | ['No'] | 2019-02-06 17:21:50 | 2019-02-06 17:21:50 | None | Projector 8 randomly switches to NVG mode, then back to correct mode of Scenario | 24 | None | Skip Hamilton | 2019-02-06 | Root Cause - Visual Projector Failure (SONY)
#JTC00000897 | Pending | CAT 3 | Robert Gaines | 19 ASOS | ['No'] | 2019-02-08 14:53:23 | 2019-02-08 14:53:23 | None | TrackIR | 7 | None | Robert Gaines | 2019-04-01 | Root Cause - Hardware TrackIR
#JTC00000910 | Hold | CAT 2 | Steve Dumont | 7 ASOS | ['No'] | 2019-02-13 13:24:45 | 2019-02-13 13:24:45 | Web form | Can't Calibrate Projectors through scalable; IG3 Error stating "Wrong Resolution Detected" | 4 | Attempted multiple fixes from two help desk agents and IDSI to resolve calibration issues. We were unable and need additional support to fix the problem | Steve Dumont | 2019-04-01 | Root Cause - Software Scalable Error
#JTC00000912 | Pending | CAT 2 | Skip Hamilton | 6 CTS | ['No'] | 2019-02-13 22:05:17 | 2019-02-13 22:05:17 | Web form | Student 1, M41 firing by itself rapid fire | 15 | None | Skip Hamilton | 2019-04-01 | Root Cause - Hardware M-4
#JTC00000920 | Hold | CAT 2 | Steve Dumont | 9 ASOS | ['No'] | 2019-02-21 01:23:20 | 2019-02-21 01:23:20 | Web form | IG8/PRJ8 Projector Cable Faulty; troubleshot cables and identified single cable non functional--restored comms using single cable 4096x2160@29hz | 24 | Cables are out of stock | Steve Dumont | 2019-02-21 | Root Cause - Hardware Monitor Cable
#JTC00000926 | Pending | CAT 2 | Robert Gaines | 13 ASOS | ['No'] | 2019-02-22 21:02:25 | 2019-02-22 21:02:25 | None | Student Station won't pick up MVP ROVER feed | 21 | None | Robert Gaines | 2019-02-22 | Root Cause - Software Q-Fires ROVER Error
#JTC00000937 | Pending | CAT 2 | Skip Hamilton | 20 ASOS, Det 1 | ['No'] | 2019-02-26 18:42:08 | 2019-02-26 18:42:08 | Mail | Ranger 47 2 Inoperable | 14 | Ranger 47 Display Issues | Skip Hamilton | 2019-04-02 | Root Cause - Other Other - See Comments
#JTC00000943 | Hold | CAT 3 | Steve Dumont | 9 ASOS | ['No'] | 2019-02-26 21:12:18 | 2019-02-26 21:12:18 | None | Shutter function not working from DOC to turn off light emissions from projectors | 24 | None | Steve Dumont | 2019-02-26 | Root Cause - Visual Projector Failure (SONY)
#JTC00000949 | Pending | CAT 3 | Steve Dumont | 2 ASOS | ['No'] | 2019-02-27 16:14:57 | 2019-02-27 16:14:57 | None | Issues with Sound/ASTi Post UG2/HF | 12 | None | Steve Dumont | 2019-04-03 | Root Cause - Software ASTi Error
#JTC00000955 | Pending | CAT 2 | Skip Hamilton | 14 ASOS | ['No'] | 2019-02-28 20:57:08 | 2019-02-28 20:57:08 | Web form | M4 needs to be repaired/replaced, was causing EME-Server boot issues | 3 | Faulty M4 | Skip Hamilton | 2019-04-02 | Root Cause - Hardware M-4
#JTC00000956 | Solved | CAT 3 | Skip Hamilton | 15 ASOS | [] | 2019-03-01 13:38:14 | 2019-03-01 13:38:14 | None | Feb 2019 Patch (UNCLASSIFIED) | 10 | perators level 2 credentials weren't working, possibly needed to reset his password. | Skip Hamilton | 2019-03-01 | Root Cause - Other Operator Error
#JTC00000957 | Solved | CAT 3 | Devin Hoeckel | 20 ASOS, Det 1 | [] | 2019-03-01 14:18:38 | 2019-03-01 14:18:38 | None | Camera for Calibration - Error not powered | 14 | Insufficient power or incorrect settings for camera during calibration | Devin Hoeckel | 2019-03-01 | Root Cause - Visual Calibration
#JTC00000958 | Pending | CAT 3 | Robert Gaines | 19 ASOS | ['No'] | 2019-03-01 14:26:53 | 2019-03-01 14:26:53 | None | IZLID cap no longer functional | 7 | None | Robert Gaines | 2019-04-01 | Root Cause - Hardware IZLID
#JTC00000959 | Solved | CAT 2 | Robert Gaines | 23 STS | None | 2019-03-01 14:50:47 | 2019-03-01 14:50:47 | None | Voicemail from: Caller +1 (337) 531-6209 | [] | None | Robert Gaines | 2019-03-01 | Undefined
#JTC00000960 | Solved | CAT 3 | Devin Hoeckel | 23 STS | [] | 2019-03-01 15:19:36 | 2019-03-01 15:19:36 | None | Wanted to add Terrain | 23 | None | Devin Hoeckel | 2019-03-01 | Root Cause - Other Other - See Comments
#JTC00000961 | Solved | CAT 3 | Skip Hamilton | 23 STS | [] | 2019-03-01 16:10:32 | 2019-03-01 16:10:32 | None | IA Update Inquiry | 10 | None | Skip Hamilton | 2019-03-01 | Root Cause - Other Other - See Comments
#JTC00000962 | Solved | CAT 3 | Skip Hamilton | DMOC | [] | 2019-03-01 16:36:55 | 2019-03-01 16:36:55 | None | Unk Caller and No Voicemail - Spoke with Shane, no current issues | 23 | None | Skip Hamilton | 2019-03-01 | Root Cause - Other Other - See Comments
#JTC00000963 | Pending | CAT 3 | Devin Hoeckel | 13 ASOS | ['No'] | 2019-03-01 17:33:59 | 2019-03-01 17:33:59 | None | LED Tasklight has stopped working | 21 | None | Devin Hoeckel | 2019-03-01 | Root Cause - Hardware Desk Light
#JTC00000964 | Solved | CAT 3 | Chris Johnson | QunataDyn | [] | 2019-03-01 18:06:50 | 2019-03-01 18:06:50 | Mail | Re: [JTC-TRS TSSC] test email | 2 | None | Chris Johnson | 2019-03-01 | Root Cause - Other Unknown
#JTC00000965 | Pending | CAT 2 | Robert Gaines | 5 ASOS | ['No'] | 2019-03-01 22:02:29 | 2019-03-01 22:02:29 | None | Sound levels | 18 | None | Robert Gaines | 2019-03-01 | Root Cause - Software ASTi Error
#JTC00000966 | Solved | CAT 2 | Robert Gaines | 724 STG | [] | 2019-03-04 17:49:14 | 2019-03-04 17:49:14 | None | Radio & Sound Issues | 27 | None | Robert Gaines | 2019-03-04 | Root Cause - Software ASTi Error
#JTC00000967 | Solved | CAT 2 | Robert Gaines | 15 ASOS | [] | 2019-03-04 18:27:42 | 2019-03-04 18:27:42 | Mail | Audio Cable for Student 1 | 10 | Frayed Cable | Robert Gaines | 2019-03-04 | Root Cause - Hardware ASTi Audio Cable
#JTC00000968 | Solved | CAT 3 | Robert Gaines | 14 ASOS | [] | 2019-03-05 12:30:39 | 2019-03-05 12:30:39 | Phone call inbound | IA Equipment Arrival Notification | 3 | None | Robert Gaines | 2019-03-05 | Root Cause - Other Unknown
#JTC00000969 | Solved | CAT 2 | Robert Gaines | 724 STG | [] | 2019-03-05 16:25:10 | 2019-03-05 16:25:10 | Mail | Image inconsistencies on MVP | 27 | Duplicate Discover Instance | Robert Gaines | 2019-03-05 | Root Cause - Software DIScover Error
#JTC00000970 | Solved | CAT 2 | Robert Gaines | 23 STS | [] | 2019-03-05 17:35:20 | 2019-03-05 17:35:20 | Voicemail | Dome Resolution Dropped | 19 | Surround settings dropped | Robert Gaines | 2019-03-05 | Root Cause - Visual Surround Error
#JTC00000971 | Pending | CAT 3 | Robert Gaines | 6 CTS | ['No'] | 2019-03-05 19:36:30 | 2019-03-05 19:36:30 | None | Systems 15, 16, 17 have old AAJTS display cables | 15 | None | Robert Gaines | 2019-03-05 | Root Cause - Visual DisplayPort Cable Failure
#JTC00000972 | Pending | CAT 2 | Robert Gaines | WPC | ['No'] | 2019-03-06 13:40:32 | 2019-03-06 13:40:32 | None | RP Station INOP on NATO Secret Drives | 11 | None | Robert Gaines | 2019-03-06 | Root Cause - Software MACE Error
#JTC00000973 | Solved | CAT 2 | Steve Dumont | STTS | [] | 2019-03-06 16:16:47 | 2019-03-06 16:16:47 | Web form | Student Station 1 will not produce an image through tablet; bad mini-DP cable and extender | 20 | None | Steve Dumont | 2019-03-06 | Root Cause - Hardware USB Cable
#JTC00000974 | Solved | CAT 2 | Robert Gaines | 23 STS | [] | 2019-03-07 14:58:58 | 2019-03-07 14:58:58 | Voicemail | Discover Crashed - MVP Unresponsive | 19 | Discover Crashed | Robert Gaines | 2019-03-07 | Root Cause - Software DIScover Error
#JTC00000975 | Hold | CAT 2 | Steve Dumont | STTS | ['No'] | 2019-03-07 16:38:28 | 2019-03-07 16:38:28 | Web form | Runaway M-4 Carbine #1; device fires autonomously--need a replacement and repairs on faulty device | 20 | Trigger pressure sensor is presumed to be faulty | Steve Dumont | 2019-03-07 | Root Cause - Hardware M-4
#JTC00000976 | Closed | CAT 3 | Robert Gaines | 15 ASOS | None | 2019-03-08 12:44:45 | 2019-03-08 12:44:45 | None | EME Server will not shut down | [] | None | Robert Gaines | 2019-03-08 | Undefined
#JTC00000977 | Solved | CAT 3 | Devin Hoeckel | 23 STS | [] | 2019-03-08 16:53:50 | 2019-03-08 16:53:50 | None | Operator having trouble with system fully shutting down. | 25 | None | Devin Hoeckel | 2019-03-08 | Root Cause - Software ASTi Error
#JTC00000978 | Solved | CAT 2 | Robert Gaines | 13 ASOS | [] | 2019-03-12 14:26:00 | 2019-03-12 14:26:00 | Phone call inbound | NAS Synchronization Issues | 21 | Time Synchronization | Robert Gaines | 2019-03-12 | Root Cause - Hardware Network Attached Storage (NAS)
#JTC00000979 | Pending | CAT 2 | Robert Gaines | 607 ASOG | ['No'] | 2019-03-13 05:01:07 | 2019-03-13 05:01:07 | None | black dot in the visual of ranger 1 | 26 | None | Robert Gaines | 2019-03-13 | Root Cause - Hardware Ranger 47
#JTC00000980 | Pending | CAT 3 | Robert Gaines | 5 ASOS | ['No'] | 2019-03-13 14:11:23 | 2019-03-13 14:11:23 | None | MACE Detonation Tool Sound - Faulty Sound Mapping | 18 | None | Robert Gaines | 2019-03-13 | Root Cause - Software ASTi Error
#JTC00000981 | Hold | CAT 2 | Robert Gaines | 20 ASOS | ['No'] | 2019-03-14 12:08:12 | 2019-03-14 12:08:12 | None | MVP VRSG shutting down | 5 | None | Robert Gaines | 2019-03-14 | Root Cause - Software VRSG Error
#JTC00000982 | Pending | CAT 2 | Skip Hamilton | 20 ASOS | ['No'] | 2019-03-14 12:11:20 | 2019-03-14 12:11:20 | Web form | Scenario Editor not opening. | 5 | VRSG Scenario Editor issues | Skip Hamilton | 2019-04-01 | Root Cause - Software VRSG Error
#JTC00000983 | Pending | CAT 2 | Robert Gaines | 20 ASOS | ['No'] | 2019-03-14 12:20:55 | 2019-03-14 12:20:55 | None | Physical Security | 5 | None | Robert Gaines | 2019-04-01 | Root Cause - Other Other - See Comments
#JTC00000984 | Pending | CAT 2 | Robert Gaines | 20 ASOS | ['No'] | 2019-03-14 12:51:28 | 2019-03-14 12:51:28 | None | Rover Feed at Student 2 Station | 5 | None | Robert Gaines | 2019-03-14 | Root Cause - Software Q-Fires ROVER Error
#JTC00000985 | Open | CAT 2 | Robert Gaines | None | ['No'] | 2019-03-14 15:22:54 | 2019-03-14 15:22:54 | None | Projector 7 - Failure | 13 | None | Robert Gaines | 2019-03-14 | Root Cause - Visual Projector Failure (SONY)
#JTC00000986 | Open | CAT 2 | Robert Gaines | None | ['No'] | 2019-03-14 15:26:45 | 2019-03-14 15:26:45 | None | Projector 8 - Failure | 13 | None | Robert Gaines | 2019-03-14 | Root Cause - Visual Projector Failure (SONY)
#JTC00000987 | Solved | CAT 3 | Robert Gaines | 23 STS | [] | 2019-03-14 16:52:15 | 2019-03-14 16:52:15 | Phone call inbound | RP-PC Display Issues | 20 | Screen resolution changed to sub-optimal setting | Robert Gaines | 2019-03-14 | Root Cause - Other Operator Error
#JTC00000989 | Solved | CAT 2 | Chris Johnson | 14 ASOS | [] | 2019-03-14 17:40:44 | 2019-03-14 17:40:44 | None | Torn Screen in the Dome | 3 | Tear in Dome Screen | Chris Johnson | 2019-03-14 | Root Cause - Hardware Peripheral (Mouse/Keyboard/Desklamp)
#JTC00000990 | Solved | CAT 3 | Robert Gaines | 3 ASOS, Det 1 | [] | 2019-03-14 19:18:19 | 2019-03-14 19:18:19 | Phone call inbound | VRSG Terrain Inquiry and Configuration Guidance | 8 | Configuration Deficiency - Terrain Search Path | Robert Gaines | 2019-03-14 | Root Cause - Software VRSG Error
#JTC00000991 | Pending | CAT 2 | Robert Gaines | 19 ASOS | 07 | 2019-03-14 20:32:25 | 2019-03-14 20:32:25 | None | ROVER feed | ['No'] | None | Robert Gaines | 2019-04-01 | Undefined
#JTC00000992 | Solved | CAT 2 | Robert Gaines | 20 ASOS | [] | 2019-03-15 16:29:08 | 2019-03-15 16:29:08 | Mail | Role Player Monitor | 5 | RP-PC Monitor Cracked | Robert Gaines | 2019-03-29 | Root Cause - Hardware Monitor
#JTC00000993 | Pending | CAT 3 | Robert Gaines | 13 ASOS | 21 | 2019-03-18 15:37:56 | 2019-03-18 15:37:56 | None | DAT Switch exhibits abnormal behavior - failure possible | ['No'] | None | Robert Gaines | 2019-03-18 | Undefined
#JTC00000994 | Solved | CAT 2 | Devin Hoeckel | 17 STS | [] | 2019-03-19 14:29:25 | 2019-03-19 14:29:25 | None | No sound in the Dome / Student 3 comes up with radio not on the screen | 1 | None | Devin Hoeckel | 2019-03-19 | Root Cause - Software ASTi Error
#JTC00000995 | Solved | CAT 2 | Skip Hamilton | STTS | [] | 2019-03-19 16:00:58 | 2019-03-19 16:00:58 | None | Error when switching terrain | 19 | None | Skip Hamilton | 2019-03-19 | Root Cause - Software DOC Error
#JTC00000996 | Solved | CAT 2 | Robert Gaines | 19 ASOS | [] | 2019-03-19 17:58:57 | 2019-03-19 17:58:57 | None | Student 1 / 148 won't transmit | 7 | None | Robert Gaines | 2019-03-19 | Root Cause - Software ASTi Error
#JTC00000997 | Solved | CAT 2 | Robert Gaines | 19 ASOS | ['No'] | 2019-03-19 20:27:41 | 2019-03-19 20:27:41 | Phone call inbound | Student radio issues | 7 | Incorrect settings introduced by operator | Robert Gaines | 2019-03-19 | Root Cause - Other Operator Error
#JTC00000998 | Solved | CAT 3 | Robert Gaines | 5 ASOS | [] | 2019-03-19 23:42:52 | 2019-03-19 23:42:52 | Phone call inbound | DOC Dome Hud | 18 | None | Robert Gaines | 2019-03-19 | Root Cause - Software DIScover Error
#JTC00000999 | Solved | CAT 3 | Robert Gaines | 5 ASOS | [] | 2019-03-19 23:43:23 | 2019-03-19 23:43:23 | None | Projector shut down | 18 | Mismatched Configuration Values | Robert Gaines | 2019-03-19 | Root Cause - Software DIScover Error
#JTC00001000 | Open | CAT 2 | Robert Gaines | DMOC | 23 | 2019-03-20 15:50:59 | 2019-03-20 15:50:59 | None | FW: Issues with the DOME | ['No'] | None | Robert Gaines | 2019-03-20 | Undefined