## Sheet1
Ticket ID | Status | Discrepancy | Submitter | Unit | Device ID | Date/Time Reported | Date/Time Acknowledged | Notification Mode | Subject | Repeat CAT 1 | Corrective Action | Asignee | Date Resolved | Root Cause | Remarks
#JTC00000842 | Solved | CAT 2 | Steve Dumont | QunataDyn | 0 | 2019-01-29 19:57:58 | 2019-01-29 19:57:58 | 22 | IG3 continues to Intermittently Fall out of the Network; won't shutdown/startup from DOC; shows "Offline"--Image from PRJ 5 & 6 comes and goes | No | IG PC | Steve Dumont | 2019-04-30 | Failure Category Hardware | Hardware
#JTC00000843 | Solved | CAT 2 | Steve Dumont | QunataDyn | 0 | 2019-01-29 20:07:45 | 2019-01-29 20:07:45 | 22 | Terrain will not Path/Write-to-File to VRSG from VRSG Remote--Have to manually modify in VRSGTerrainSearchPath, Restart System to upload Terrain | No | DOC Error | Steve Dumont | 2019-04-30 | Failure Category Software | Software
#JTC00000844 | Solved | CAT 2 | Skip Hamilton | QunataDyn | 0 | 2019-01-29 20:14:11 | 2019-01-29 20:14:11 | 24 | ASTi will not Startup on Initial Startup of SIM; have to start remotely from server | No | DOC Error | Skip Hamilton | 2019-04-30 | Failure Category Software | Software
#JTC00000845 | Solved | CAT 2 | Steve Dumont | QunataDyn | 0 | 2019-01-29 20:20:37 | 2019-01-29 20:20:37 | 24 | IG4 & 8 will not Produce an Image in Dome unless set to "Desktop Cover" under Preferances in VRSG Dashboard from both IGs | No | Surround Error | Steve Dumont | 2019-04-30 | Failure Category Visual | Visual
#JTC00000898 | Solved | CAT 3 | Robert Gaines | 724 STG | 0 | 2019-02-08 14:59:32 | 2019-02-08 14:59:32 | 27 | Upgrade 2 - Inquiry | No | Other - See Comments | Robert Gaines | 2019-04-30 | Failure Category Other | Other
#JTC00000966 | Solved | CAT 2 | Robert Gaines | 724 STG | 0 | 2019-03-04 17:49:14 | 2019-03-04 17:49:14 | 27 | Radio & Sound Issues | No | ASTi Error | Robert Gaines | 2019-04-26 | Failure Category Software | Software
#JTC00000969 | Solved | CAT 2 | Robert Gaines | 724 STG | 0 | 2019-03-05 16:25:10 | 2019-03-05 16:25:10 | 27 | Image inconsistencies on MVP | No | DIScover Error | Robert Gaines | 2019-04-26 | Failure Category Software | Software
#JTC00000950 | Solved | CAT 3 | Robert Gaines | 17 STS | 1 | 2019-02-27 20:13:28 | 2019-02-27 20:13:28 | 1 | VRSG License Expiration | No | VRSG Error | Robert Gaines | 2019-04-26 | Failure Category Software | Software
#JTC00000994 | Solved | CAT 2 | Devin Hoeckel | 17 STS | 1 | 2019-03-19 14:29:25 | 2019-03-19 14:29:25 | 1 | No sound in the Dome / Student 3 comes up with radio not on the screen | No | ASTi Error | Devin Hoeckel | 2019-04-26 | Failure Category Software | Software
#JTC00000347 | Hold | CAT 2 | Devin Hoeckel | 14 ASOS | 3 | 2018-05-10 13:56:37 | 2018-05-10 13:56:37 | 3 | ASTI Radios bleeding over. | No | ASTi Error | Devin Hoeckel |  | Failure Category Software | Software
#JTC00000581 | Hold | CAT 3 | Devin Hoeckel | 14 ASOS | 3 | 2018-10-10 19:37:11 | 2018-10-10 19:37:11 | 3 | IG Projctors color-blending/Focus needs to be adjusted. | No | Calibration | Devin Hoeckel |  | Failure Category Visual | Visual
#JTC00000868 | Solved | CAT 3 | Chris Johnson | 14 ASOS | 3 | 2019-01-31 19:39:55 | 2019-01-31 19:39:55 | 3 | DMON VOIP phones. | No | Other - See Comments | Chris Johnson | 2019-04-30 | Failure Category Other | Other
#JTC00000904 | Solved | CAT 2 | Devin Hoeckel | 14 ASOS | 3 | 2019-02-11 14:14:42 | 2019-02-11 14:14:42 | 3 | Cannot receive on Radios during DMO events. | No | Other - See Comments | Devin Hoeckel | 2019-04-30 | Failure Category Other | Other
#JTC00000905 | Solved | CAT 2 | Devin Hoeckel | 14 ASOS | 3 | 2019-02-11 14:31:16 | 2019-02-11 14:31:16 | 3 | Ranger 47 issues using different Model Maps. | No | VRSG Error | Devin Hoeckel | 2019-04-30 | Failure Category Software | Software
#JTC00000954 | Solved | CAT 1 | Skip Hamilton | 14 ASOS | 3 | 2019-02-28 15:45:07 | 2019-02-28 15:45:07 | 3 | EME Server Fails to boot. | No | M-4 | Skip Hamilton | 2019-04-26 | Failure Category Hardware | Hardware
#JTC00000955 | Solved | CAT 2 | Skip Hamilton | 14 ASOS | 3 | 2019-02-28 20:57:08 | 2019-02-28 20:57:08 | 3 | M4 needs to be repaired/replaced, was causing EME-Server boot issues | No | M-4 | Skip Hamilton | 2019-04-08 | Failure Category Hardware | Hardware
#JTC00000968 | Solved | CAT 3 | Robert Gaines | 14 ASOS | 3 | 2019-03-05 12:30:39 | 2019-03-05 12:30:39 | 3 | IA Equipment Arrival Notification | No | Unknown | Robert Gaines | 2019-04-26 | Failure Category Other | Other
#JTC00000989 | Solved | CAT 2 | Chris Johnson | 14 ASOS | 3 | 2019-03-14 17:40:44 | 2019-03-14 17:40:44 | 3 | Torn Screen in the Dome | No | Peripheral (Mouse/Keyboard/Desklamp) | Chris Johnson | 2019-04-26 | Failure Category Hardware | Hardware
#JTC00000839 | Solved | CAT 3 | Skip Hamilton | 7 ASOS | 4 | 2019-01-29 17:38:55 | 2019-01-29 17:38:55 | 4 | Issues/Questions with MVP and RPS post Upgarde 2 | No | Closed by Merge | Skip Hamilton | 2019-04-30 | Failure Category Other | Other
#JTC00000851 | Solved | CAT 3 | Steve Dumont | 7 ASOS | 4 | 2019-01-30 19:33:33 | 2019-01-30 19:33:33 | 4 | Assisted Client w/EME Configuration post UG2 | No | Software Upgrade Issues | Steve Dumont | 2019-04-30 | Failure Category Other | Other
#JTC00000867 | Solved | CAT 2 | Devin Hoeckel | 7 ASOS | 4 | 2019-01-31 18:20:21 | 2019-01-31 18:20:21 | 4 | Ranger 1 not tracking and functions (lrf, laser, ) not working. | No | Ranger 47 | Devin Hoeckel | 2019-04-30 | Failure Category Hardware | Hardware
#JTC00000899 | Solved | CAT 1 | Robert Gaines | 7 ASOS | 4 | 2019-02-08 16:00:47 | 2019-02-08 16:00:47 | 4 | DIScover not populating with correct settings post 1.2.9 installation | No | Q-Fires Startup Error | Robert Gaines | 2019-04-30 | Failure Category Software | Software
#JTC00000901 | Solved | CAT 2 | Devin Hoeckel | 7 ASOS | 4 | 2019-02-08 18:48:58 | 2019-02-08 18:48:58 | 4 | Ranger 1 scroll wheel does not incrementally scroll. | No | Ranger 47 | Devin Hoeckel | 2019-04-30 | Failure Category Hardware | Hardware
#JTC00000902 | Solved | CAT 2 | Devin Hoeckel | 7 ASOS | 4 | 2019-02-08 18:53:25 | 2019-02-08 18:53:25 | 4 | Anchor 1 is intermittently connecting. | No | Indotraq Anchor | Devin Hoeckel | 2019-04-30 | Failure Category Hardware | Hardware
#JTC00000909 | Solved | CAT 2 | Steve Dumont | 7 ASOS | 4 | 2019-02-12 22:25:10 | 2019-02-12 22:25:10 | None | Voicemail from: Andre Aragon | No | Closed by Merge | Steve Dumont | 2019-04-30 | Failure Category Other | Other
#JTC00000910 | Solved | CAT 2 | Steve Dumont | 7 ASOS | 4 | 2019-02-13 13:24:45 | 2019-02-13 13:24:45 | 4 | Can't Calibrate Projectors through scalable; IG3 Error stating "Wrong Resolution Detected" | No | Scalable Error | Steve Dumont | 2019-04-08 | Failure Category Software | Software
#JTC00000915 | Solved | CAT 2 | Robert Gaines | 7 ASOS | 4 | 2019-02-20 17:35:35 | 2019-02-20 17:35:35 | None | Phone Call from: Andre Aragon | No | Closed by Merge | Robert Gaines | 2019-04-29 | Failure Category Other | Other
#JTC00000916 | Solved | CAT 2 | Robert Gaines | 7 ASOS | 4 | 2019-02-20 18:39:58 | 2019-02-20 18:39:58 | 4 | VRSG Visual not responding at startup | No | Operator Error | Robert Gaines | 2019-04-30 | Failure Category Other | Other
#JTC00000928 | Solved | CAT 2 | Robert Gaines | 7 ASOS | 4 | 2019-02-25 17:51:39 | 2019-02-25 17:51:39 | 4 | DMO connection troubleshooting | No | Other - See Comments | Robert Gaines | 2019-04-27 | Failure Category Other | Other
#JTC00000930 | Solved | CAT 2 | Skip Hamilton | 7 ASOS | 4 | 2019-02-25 19:06:02 | 2019-02-25 19:06:02 | 4 | DMO Testing Issues | No | Closed by Merge | Skip Hamilton | 2019-04-27 | Failure Category Other | Other
#JTC00000934 | Solved | CAT 2 | Robert Gaines | 7 ASOS | 4 | 2019-02-26 16:09:28 | 2019-02-26 16:09:28 | 3 | Merge ticket 1232 | No | Closed by Merge | Robert Gaines | 2019-04-27 | Failure Category Other | Other
#JTC00000935 | Solved | CAT 2 | Robert Gaines | 7 ASOS | 4 | 2019-02-26 16:41:40 | 2019-02-26 16:41:40 | None | Merge ticket 1232 | No | Closed by Merge | Robert Gaines | 2019-04-27 | Failure Category Other | Other
#JTC00000942 | Solved | CAT 3 | Steve Dumont | 7 ASOS | 4 | 2019-02-26 18:55:27 | 2019-02-26 18:55:27 | 4 | Phone Call from: Andre Aragon | No | Other - See Comments | Steve Dumont | 2019-04-26 | Failure Category Other | Other
#JTC00001009 | Pending | CAT 2 | Robert Gaines | 7 ASOS | 4 | 2019-03-28 18:21:25 | 2019-03-28 18:21:25 | 4 | Touch capability non-functional on top MVP monitor | No | Monitor Cable | Robert Gaines |  | Failure Category Hardware | Hardware
#JTC00000564 | Pending | CAT 2 | Robert Gaines | 20 ASOS | 5 | 2018-10-04 12:19:12 | 2018-10-04 12:19:12 | 5 | PEQ-15 from M4 #2 broken tab & PEQ-15 from M4 #1 broken mount | No | M-4 | Robert Gaines |  | Failure Category Hardware | Hardware
#JTC00000872 | Hold | CAT 2 | Skip Hamilton | 20 ASOS | 5 | 2019-02-01 20:05:35 | 2019-02-01 20:05:35 | 5 | Ranger47 1 and 2 Mounts need to be replaced/repaired | No | Other - See Comments | Skip Hamilton |  | Failure Category Other | Other
#JTC00000927 | Solved | CAT 3 | Robert Gaines | 20 ASOS | 5 | 2019-02-25 14:18:57 | 2019-02-25 14:18:57 | 14 | VRSG licenses expiring in 60 days | No | VRSG Error | Robert Gaines | 2019-04-27 | Failure Category Software | Software
#JTC00000981 | Hold | CAT 2 | Robert Gaines | 20 ASOS | 5 | 2019-03-14 12:08:12 | 2019-03-14 12:08:12 | 5 | MVP VRSG shutting down | No | VRSG Error | Robert Gaines |  | Failure Category Software | Software
#JTC00000982 | Pending | CAT 2 | Skip Hamilton | 20 ASOS | 5 | 2019-03-14 12:11:20 | 2019-03-14 12:11:20 | 5 | Scenario Editor not opening. | No | VRSG Error | Skip Hamilton |  | Failure Category Software | Software
#JTC00000983 | Solved | CAT 2 | Robert Gaines | 20 ASOS | 5 | 2019-03-14 12:20:55 | 2019-03-14 12:20:55 | 5 | Physical Security | No | Other - See Comments | Robert Gaines | 2019-04-22 | Failure Category Other | Other
#JTC00000984 | Pending | CAT 2 | Robert Gaines | 20 ASOS | 5 | 2019-03-14 12:51:28 | 2019-03-14 12:51:28 | 5 | Rover Feed at Student 2 Station | No | Q-Fires ROVER Error | Robert Gaines |  | Failure Category Software | Software
#JTC00000992 | Solved | CAT 2 | Robert Gaines | 20 ASOS | 5 | 2019-03-15 16:29:08 | 2019-03-15 16:29:08 | 5 | Role Player Monitor | No | Monitor | Robert Gaines | 2019-04-26 | Failure Category Hardware | Hardware
#JTC00001022 | Pending | CAT 2 | Robert Gaines | 20 ASOS | 5 | 2019-04-01 20:47:01 | 2019-04-01 20:47:01 | 5 | Replacement RP-PC Monitor does not fit the mount | No | Monitor | Robert Gaines |  | Failure Category Hardware | Hardware
#JTC00001037 | Pending | CAT 2 | Robert Gaines | 20 ASOS | 5 | 2019-04-03 20:46:25 | 2019-04-03 20:46:25 | 5 | Ranger 47-2 is falling apart | No | Ranger 47 | Robert Gaines |  | Failure Category Hardware | Hardware
#JTC00000310 | Pending | CAT 2 | Skip Hamilton | 10 ASOS | 6 | 2018-04-17 14:42:11 | 2018-04-17 14:42:11 | 6 | MVP visual height error during DMO events | No | VRSG Error | Skip Hamilton |  | Failure Category Software | Software
#JTC00000850 | Solved | CAT 2 | Skip Hamilton | 10 ASOS | 6 | 2019-01-30 15:56:45 | 2019-01-30 15:56:45 | 6 | Student Station #1 Radio, MVP Stealth View | No | ASTi Error | Skip Hamilton | 2019-04-30 | Failure Category Software | Software
#JTC00000900 | Solved | CAT 3 | Skip Hamilton | 10 ASOS | 6 | 2019-02-08 16:01:17 | 2019-02-08 16:01:17 | 6 | 1.2.9 upgrade | No | Operator Error | Skip Hamilton | 2019-04-30 | Failure Category Other | Other
#JTC00000907 | Solved | CAT 1 | Skip Hamilton | 10 ASOS | 6 | 2019-02-12 18:25:16 | 2019-02-12 18:25:16 | 6 | Multiple issues: Projector #7 error light, ect. | No | Projector Failure (SONY) | Skip Hamilton | 2019-04-30 | Failure Category Visual | Visual
#JTC00000134 | Hold | CAT 3 | Devin Hoeckel | 19 ASOS | 7 | 2018-01-08 16:57:45 | 2018-01-08 16:57:45 | 7 | Entities not viewable in parts of the SW US | No | Visual Database Discrepancy | Devin Hoeckel |  | Failure Category Software | Software
#JTC00000224 | Pending | CAT 2 | Kyle Zamudio | 19 ASOS | 7 | 2018-03-08 21:24:00 | 2018-03-08 21:24:00 | 7 | ROLE Player radio transmits garbled at initial start up. | No | ASTi Error | Kyle Zamudio |  | Failure Category Software | Software
#JTC00000852 | Solved | CAT 1 | Skip Hamilton | 19 ASOS | 7 | 2019-01-30 20:44:27 | 2019-01-30 20:44:27 | 7 | DIScover issue | No | DIScover Error | Skip Hamilton | 2019-04-30 | Failure Category Software | Software
#JTC00000854 | Solved | CAT 1 | Robert Gaines | 19 ASOS | 7 | 2019-01-31 14:16:18 | 2019-01-31 14:16:18 | 7 | DOME images out of sequence | No | Surround Error | Robert Gaines | 2019-04-30 | Failure Category Visual | Visual
#JTC00000855 | Open | CAT 2 | Skip Hamilton | 19 ASOS | 7 | 2019-01-31 14:19:00 | 2019-01-31 14:19:00 | 7 | DOME image color and blending is very poor | No | Calibration | Skip Hamilton |  | Failure Category Visual | Visual
#JTC00000856 | Solved | CAT 2 | Devin Hoeckel | 19 ASOS | 7 | 2019-01-31 14:48:10 | 2019-01-31 14:48:10 | None | Dome came up with surround Broken...Projectors not coming on in time. | No | Closed by Merge | Devin Hoeckel | 2019-04-30 | Failure Category Other | Other
#JTC00000870 | Solved | CAT 3 | Skip Hamilton | 19 ASOS | 7 | 2019-02-01 15:08:14 | 2019-02-01 15:08:14 | 7 | MACE maintenance expired | No | MACE Error | Skip Hamilton | 2019-04-30 | Failure Category Software | Software
#JTC00000871 | Solved | CAT 2 | Devin Hoeckel | 19 ASOS | 7 | 2019-02-01 17:31:26 | 2019-02-01 17:31:26 | 7 | IG7 appears to have a bad displayport cable. | No | DisplayPort Cable Failure | Devin Hoeckel | 2019-04-30 | Failure Category Visual | Visual
#JTC00000897 | Solved | CAT 3 | Robert Gaines | 19 ASOS | 7 | 2019-02-08 14:53:23 | 2019-02-08 14:53:23 | 7 | TrackIR | No | TrackIR | Robert Gaines | 2019-04-19 | Failure Category Hardware | Hardware
#JTC00000906 | Solved | CAT 3 | Devin Hoeckel | 19 ASOS | 7 | 2019-02-11 17:12:23 | 2019-02-11 17:12:23 | 7 | JTAC Ranger no Roofclamping | No | Q-Fires Startup Error | Devin Hoeckel | 2019-04-30 | Failure Category Software | Software
#JTC00000958 | Solved | CAT 3 | Robert Gaines | 19 ASOS | 7 | 2019-03-01 14:26:53 | 2019-03-01 14:26:53 | 7 | IZLID cap no longer functional | No | IZLID | Robert Gaines | 2019-04-18 | Failure Category Hardware | Hardware
#JTC00000991 | Pending | CAT 2 | Robert Gaines | 19 ASOS | 7 | 2019-03-14 20:32:25 | 2019-03-14 20:32:25 | 7 | ROVER feed | No | Q-Fires ROVER Error | Robert Gaines |  | Failure Category Software | Software
#JTC00000996 | Solved | CAT 2 | Robert Gaines | 19 ASOS | 7 | 2019-03-19 17:58:57 | 2019-03-19 17:58:57 | 7 | Student 1 / 148 won't transmit | No | ASTi Error | Robert Gaines | 2019-04-26 | Failure Category Software | Software
#JTC00000997 | Solved | CAT 2 | Robert Gaines | 19 ASOS | 7 | 2019-03-19 20:27:41 | 2019-03-19 20:27:41 | 7 | Student radio issues | No | Operator Error | Robert Gaines | 2019-04-03 | Failure Category Other | Other
#JTC00000789 | Pending | CAT 3 | Devin Hoeckel | 3 ASOS, Det 1 | 8 | 2019-01-17 17:08:27 | 2019-01-17 17:08:27 | 8 | Dome Image Blurry | No | Calibration | Devin Hoeckel |  | Failure Category Visual | Visual
#JTC00000823 | Pending | CAT 2 | Robert Gaines | 3 ASOS, Det 1 | 8 | 2019-01-25 16:05:04 | 2019-01-25 16:05:04 | 8 | Projector 8 not booting up and has "XOXOXO" on it. Incorrect Resolution | No | Projector Failure (SONY) | Robert Gaines |  | Failure Category Visual | Visual
#JTC00000990 | Solved | CAT 3 | Robert Gaines | 3 ASOS, Det 1 | 8 | 2019-03-14 19:18:19 | 2019-03-14 19:18:19 | 8 | VRSG Terrain Inquiry and Configuration Guidance | No | VRSG Error | Robert Gaines | 2019-04-26 | Failure Category Software | Software
#JTC00001001 | Solved | CAT 2 | Robert Gaines | 3 ASOS, Det 1 | 8 | 2019-03-26 19:36:00 | 2019-03-26 19:36:00 | 8 | IG - 8 GPU critical failure | No | Other - See Comments | Robert Gaines | 2019-04-22 | Failure Category Other | Other
#JTC00001003 | Solved | CAT 2 | Robert Gaines | 3 ASOS, Det 1 | 8 | 2019-03-26 19:44:32 | 2019-03-26 19:44:32 | 8 | DIScord Settings no Longer Function with Upgrade 2 | No | MACE Error | Robert Gaines | 2019-04-19 | Failure Category Software | Software
#JTC00000765 | Pending | CAT 2 | Robert Gaines | 25 ASOS | 9 | 2019-01-10 22:25:35 | 2019-01-10 22:25:35 | 9 | Degraded video quality from MVP VRSG | No | Q-Fires ROVER Error | Robert Gaines |  | Failure Category Software | Software
#JTC00000770 | Pending | CAT 2 | Robert Gaines | 25 ASOS | 9 | 2019-01-11 23:38:23 | 2019-01-11 23:38:23 | 9 | absent transporter erector launcher (TEL) in VRSG | No | Visual Database Discrepancy | Robert Gaines |  | Failure Category Software | Software
#JTC00000846 | Solved | CAT 2 | Skip Hamilton | 25 ASOS | 9 | 2019-01-29 23:57:12 | 2019-01-29 23:57:12 | 9 | Dome view from the shoes of the standing JTAC | No | MACE Error | Skip Hamilton | 2019-04-30 | Failure Category Software | Software
#JTC00000922 | Solved | CAT 3 | Kyle Zamudio | 25 ASOS | 9 | 2019-02-21 18:25:50 | 2019-02-21 18:25:50 | 9 | Package from Quatadyn returned | No | Other - See Comments | Kyle Zamudio | 2019-04-27 | Failure Category Other | Other
#JTC00000524 | Hold | CAT 2 | Skip Hamilton | 15 ASOS | 10 | 2018-09-04 12:49:03 | 2018-09-04 12:49:03 | 10 | Tear in screen | No | Screen Damaged | Skip Hamilton |  | Failure Category Visual | Visual
#JTC00000836 | Solved | CAT 2 | Skip Hamilton | 15 ASOS | 10 | 2019-01-29 13:57:55 | 2019-01-29 13:57:55 | 10 | Multiple Issues Post Upgrade 2 | No | Software Upgrade Issues | Skip Hamilton | 2019-04-30 | Failure Category Other | Other
#JTC00000837 | Solved | CAT 3 | Skip Hamilton | 15 ASOS | 10 | 2019-01-29 15:16:36 | 2019-01-29 15:16:36 | 10 | Jan 19 Scans (UNCLASSIFIED) | No | Cybersecurity Update | Skip Hamilton | 2019-04-30 | Failure Category Other | Other
#JTC00000857 | Solved | CAT 2 | Skip Hamilton | 15 ASOS | 10 | 2019-01-31 14:50:25 | 2019-01-31 14:50:25 | 10 | Izlid Tag was set to wrong one, IZLID cap isn't functioning correctly, set to ignore IZLID functions | No | DIScover Error | Skip Hamilton | 2019-04-30 | Failure Category Software | Software
#JTC00000918 | Solved | CAT 2 | Skip Hamilton | 15 ASOS | 10 | 2019-02-20 19:47:32 | 2019-02-20 19:47:32 | 10 | IZLID TAG | No | IZLID | Skip Hamilton | 2019-04-30 | Failure Category Hardware | Hardware
#JTC00000956 | Solved | CAT 3 | Skip Hamilton | 15 ASOS | 10 | 2019-03-01 13:38:14 | 2019-03-01 13:38:14 | 10 | Feb 2019 Patch (UNCLASSIFIED) | No | Operator Error | Skip Hamilton | 2019-04-26 | Failure Category Other | Other
#JTC00000967 | Solved | CAT 2 | Robert Gaines | 15 ASOS | 10 | 2019-03-04 18:27:42 | 2019-03-04 18:27:42 | 10 | Audio Cable for Student 1 | No | ASTi Audio Cable | Robert Gaines | 2019-04-26 | Failure Category Hardware | Hardware
#JTC00000976 | Solved | CAT 3 | Robert Gaines | 15 ASOS | 10 | 2019-03-08 12:44:45 | 2019-03-08 12:44:45 | 10 | Merged into ticket #JTC00001011 | No | Closed by Merge | Robert Gaines | 2019-04-24 | Failure Category Other | Other
#JTC00000702 | Hold | CAT 2 | Skip Hamilton | WPC | 11 | 2018-12-11 11:58:14 | 2018-12-11 11:58:14 | 11 | MVP VRSG Crashing | No | VRSG Error | Skip Hamilton |  | Failure Category Software | Software
#JTC00000903 | Solved | CAT 1 | Skip Hamilton | WPC | 11 | 2019-02-11 11:53:18 | 2019-02-11 11:53:18 | 11 | IOS INOP | No | Operator Error | Skip Hamilton | 2019-04-30 | Failure Category Other | Other
#JTC00000972 | Pending | CAT 2 | Robert Gaines | WPC | 11 | 2019-03-06 13:40:32 | 2019-03-06 13:40:32 | 11 | RP Station INOP on NATO Secret Drives | No | MACE Error | Robert Gaines |  | Failure Category Software | Software
#JTC00000654 | Hold | CAT 2 | Skip Hamilton | 2 ASOS | 12 | 2018-11-20 13:54:53 | 2018-11-20 13:54:53 | 12 | Temporary canvas replacement screen requires replacement with high-contrast screen. | No | Screen Damaged | Skip Hamilton |  | Failure Category Visual | Visual
#JTC00000848 | Solved | CAT 3 | Skip Hamilton | 2 ASOS | 12 | 2019-01-30 11:35:39 | 2019-01-30 11:35:39 | 12 | Patch not installing | No | Cybersecurity Update | Skip Hamilton | 2019-04-30 | Failure Category Other | Other
#JTC00000859 | Solved | CAT 3 | Skip Hamilton | 2 ASOS | 12 | 2019-01-31 14:58:48 | 2019-01-31 14:58:48 | 11 | Vilseck location patch assistance (UNCLASSIFIED) | No | Software Upgrade Issues | Skip Hamilton | 2019-04-30 | Failure Category Other | Other
#JTC00000861 | Solved | CAT 2 | Kyle Zamudio | 2 ASOS | 12 | 2019-01-31 15:39:03 | 2019-01-31 15:39:03 | 12 | VRSG keeps crashing on the Role Player | No | VRSG Error | Kyle Zamudio | 2019-04-30 | Failure Category Software | Software
#JTC00000862 | Hold | CAT 2 | Kyle Zamudio | 2 ASOS | 12 | 2019-01-31 15:45:53 | 2019-01-31 15:45:53 | 12 | Viewpoint attachment in dome jumps from one entitiy to another | No | VRSG Error | Kyle Zamudio |  | Failure Category Software | Software
#JTC00000863 | Solved | CAT 2 | Kyle Zamudio | 2 ASOS | 12 | 2019-01-31 16:05:05 | 2019-01-31 16:05:05 | 12 | Odd issues (in MACE) related to Discover in the EME | No | DIScover Error | Kyle Zamudio | 2019-04-30 | Failure Category Software | Software
#JTC00000933 | Solved | CAT 3 | Steve Dumont | 2 ASOS | 12 | 2019-02-26 15:29:48 | 2019-02-26 15:29:48 | 12 | Merge ticket 1253 | No | Closed by Merge | Steve Dumont | 2019-04-27 | Failure Category Other | Other
#JTC00000936 | Solved | CAT 3 | Steve Dumont | 2 ASOS | 12 | 2019-02-26 18:20:27 | 2019-02-26 18:20:27 | 12 | Vilseck calling about HF application | No | Closed by Merge | Steve Dumont | 2019-04-27 | Failure Category Other | Other
#JTC00000948 | Solved | CAT 3 | Steve Dumont | 2 ASOS | 12 | 2019-02-27 16:11:02 | 2019-02-27 16:11:02 | 12 | Voicemail from: A. Michael Samborski | No | Closed by Merge | Steve Dumont | 2019-04-26 | Failure Category Other | Other
#JTC00000949 | Solved | CAT 3 | Steve Dumont | 2 ASOS | 12 | 2019-02-27 16:14:57 | 2019-02-27 16:14:57 | 12 | Issues with Sound/ASTi Post UG2/HF | No | ASTi Error | Steve Dumont | 2019-04-23 | Failure Category Software | Software
#JTC00000953 | Solved | CAT 1 | Robert Gaines | 2 ASOS | 12 | 2019-02-28 13:49:31 | 2019-02-28 13:49:31 | 12 | JTC TRS not acting as it should after 1.2.9 install | No | Operator Error | Robert Gaines | 2019-04-26 | Failure Category Other | Other
#JTC00001010 | New | CAT 2 | Devin Hoeckel | 2 ASOS | 12 | 2019-03-29 09:19:37 | 2019-03-29 09:19:37 | 11 | Temporary canvas replacement screen requires replacement with high-contrast screen. | No | Screen Damaged | Devin Hoeckel |  | Failure Category Visual | Visual
#JTC00001012 | Pending | CAT 2 | Robert Gaines | 2 ASOS | 12 | 2019-03-29 15:30:21 | 2019-03-29 15:30:21 | 11 | IOS turns on by itself | No | IOS PC | Robert Gaines |  | Failure Category Hardware | Hardware
#JTC00000985 | Pending | CAT 2 | Robert Gaines | 12 CTS | 13 | 2019-03-14 15:22:54 | 2019-03-14 15:22:54 | 13 | Projector 7 - Failure | No | Projector Failure (SONY) | Robert Gaines |  | Failure Category Visual | Visual
#JTC00000986 | Pending | CAT 2 | Robert Gaines | 12 CTS | 13 | 2019-03-14 15:26:45 | 2019-03-14 15:26:45 | 13 | Projector 8 - Failure | No | Projector Failure (SONY) | Robert Gaines |  | Failure Category Visual | Visual
#JTC00000858 | Solved | CAT 3 | Skip Hamilton | 20 ASOS, Det 1 | 14 | 2019-01-31 14:58:45 | 2019-01-31 14:58:45 | 14 | Site doesn't have ASTi drive keys, can't complete ASTi upgrade. | No | Operator Error | Skip Hamilton | 2019-04-30 | Failure Category Other | Other
#JTC00000931 | Solved | CAT 2 | Skip Hamilton | 20 ASOS, Det 1 | 14 | 2019-02-25 20:30:14 | 2019-02-25 20:30:14 | 14 | Asti Drive Enclosure screws are stripped and need a replacement sent in order to mount the upgrade SSD | No | Closed by Merge | Skip Hamilton | 2019-04-27 | Failure Category Other | Other
#JTC00000937 | Pending | CAT 2 | Skip Hamilton | 20 ASOS, Det 1 | 14 | 2019-02-26 18:42:08 | 2019-02-26 18:42:08 | 14 | Ranger 47 2 Inoperable | No | Other - See Comments | Skip Hamilton |  | Failure Category Other | Other
#JTC00000938 | Solved | CAT 2 | Robert Gaines | 20 ASOS, Det 1 | 14 | 2019-02-26 18:44:12 | 2019-02-26 18:44:12 | 14 | Ranger 47 Viewpoint Underground | No | DIScover Error | Robert Gaines | 2019-04-27 | Failure Category Software | Software
#JTC00000939 | Solved | CAT 2 | Skip Hamilton | 20 ASOS, Det 1 | 14 | 2019-02-26 18:45:35 | 2019-02-26 18:45:35 | 14 | Voisus unable to adjust mic and headset volumes | No | ASTi Error | Skip Hamilton | 2019-04-27 | Failure Category Software | Software
#JTC00000940 | Solved | CAT 2 | Skip Hamilton | 20 ASOS, Det 1 | 14 | 2019-02-26 18:48:06 | 2019-02-26 18:48:06 | 14 | ASTI Hard drive screw stripped | No | Other | Skip Hamilton | 2019-04-27 | Failure Category Hardware | Hardware
#JTC00000941 | Solved | CAT 3 | Skip Hamilton | 20 ASOS, Det 1 | 14 | 2019-02-26 18:54:21 | 2019-02-26 18:54:21 | 14 | VRSG License Expiring (60 Days) | No | Other - See Comments | Skip Hamilton | 2019-04-26 | Failure Category Other | Other
#JTC00000944 | Solved | CAT 2 | Robert Gaines | 20 ASOS, Det 1 | 14 | 2019-02-26 22:25:13 | 2019-02-26 22:25:13 | 14 | Bad Cable - Headset Student 1 | No | ASTi Audio Cable | Robert Gaines | 2019-04-26 | Failure Category Hardware | Hardware
#JTC00000945 | Solved | CAT 2 | Skip Hamilton | 20 ASOS, Det 1 | 14 | 2019-02-27 14:35:17 | 2019-02-27 14:35:17 | 14 | ASHLEY Audio not working | No | ASTi Error | Skip Hamilton | 2019-04-26 | Failure Category Software | Software
#JTC00000946 | Solved | CAT 2 | Skip Hamilton | 20 ASOS, Det 1 | 14 | 2019-02-27 14:37:01 | 2019-02-27 14:37:01 | 14 | MVP VRSG Random Shutdown | No | VRSG Error | Skip Hamilton | 2019-04-26 | Failure Category Software | Software
#JTC00000951 | Solved | CAT 2 | Skip Hamilton | 20 ASOS, Det 1 | 14 | 2019-02-27 20:22:39 | 2019-02-27 20:22:39 | 14 | ASTI License Won't Update | No | Closed by Merge | Skip Hamilton | 2019-04-26 | Failure Category Other | Other
#JTC00000957 | Solved | CAT 3 | Devin Hoeckel | 20 ASOS, Det 1 | 14 | 2019-03-01 14:18:38 | 2019-03-01 14:18:38 | 14 | Camera for Calibration - Error not powered | No | Calibration | Devin Hoeckel | 2019-04-26 | Failure Category Visual | Visual
#JTC00000168 | Hold | CAT 2 | Skip Hamilton | 6 CTS | 17 | 2018-02-08 20:30:12 | 2018-02-08 20:30:12 | 16 | Projector #4 image (bottom right of screen blacks out for a couple seconds or flickers and goes to a yellow/green tint over the image every 5-10 minutes | No | DisplayPort Cable Failure | Skip Hamilton |  | Failure Category Visual | Visual
#JTC00000171 | Hold | CAT 2 | Skip Hamilton | 6 CTS | 17 | 2018-02-08 21:32:28 | 2018-02-08 21:32:28 | 16 | Projector #10 image blacks out routinely for 1-3 seconds and then comes back | No | DisplayPort Cable Failure | Skip Hamilton |  | Failure Category Visual | Visual
#JTC00000625 | Hold | CAT 2 | Skip Hamilton | 6 CTS | 17 | 2018-11-07 17:10:51 | 2018-11-07 17:10:51 | 15 | VRSG on MVP shutting down by itself during mission | No | VRSG Error | Skip Hamilton |  | Failure Category Software | Software
#JTC00000626 | Hold | CAT 2 | Skip Hamilton | 6 CTS | 17 | 2018-11-07 17:11:36 | 2018-11-07 17:11:36 | 16 | VRSG on MVP shutting down by itself during mission | No | VRSG Error | Skip Hamilton |  | Failure Category Software | Software
#JTC00000740 | Hold | CAT 2 | Robert Gaines | 6 CTS | 17 | 2018-12-21 20:59:26 | 2018-12-21 20:59:26 | 15 | IG 1 VRSG starts up in window Mode on all 3 devices | No | VRSG Error | Robert Gaines |  | Failure Category Software | Software
#JTC00000775 | Hold | CAT 2 | Robert Gaines | 6 CTS | 17 | 2019-01-14 22:27:04 | 2019-01-14 22:27:04 | 17 | Projector #9 strobing yellow tint on entire image | No | Projector Failure (BARCO) | Robert Gaines |  | Failure Category Visual | Visual
#JTC00000793 | Pending | CAT 2 | Robert Gaines | 6 CTS | 17 | 2019-01-18 19:05:31 | 2019-01-18 19:05:31 | 16 | RPS Targeting Pod Display Issue & MVP TGP Accuracy | No | DIScover Error | Robert Gaines |  | Failure Category Software | Software
#JTC00000814 | Pending | CAT 2 | Skip Hamilton | 6 CTS | 17 | 2019-01-24 18:26:35 | 2019-01-24 18:26:35 | 16 | Projector # 7 goes to stand by mode every 10 minutes, image turns black | No | Projector Failure (BARCO) | Skip Hamilton |  | Failure Category Visual | Visual
#JTC00000815 | Open | CAT 2 | Robert Gaines | 6 CTS | 17 | 2019-01-24 18:28:07 | 2019-01-24 18:28:07 | 16 | Pilot Station MACE shuts down by itself during mission | No | MACE Error | Robert Gaines |  | Failure Category Software | Software
#JTC00000816 | Hold | CAT 2 | Robert Gaines | 6 CTS | 17 | 2019-01-24 18:29:24 | 2019-01-24 18:29:24 | 16 | Pilot Station VRSG closes by itself during missions | No | VRSG Error | Robert Gaines |  | Failure Category Software | Software
#JTC00000911 | Solved | CAT 2 | Skip Hamilton | 6 CTS | 17 | 2019-02-13 16:48:25 | 2019-02-13 16:48:25 | 16 | Student 2 PRC-117G no transmit | No | ASTi Audio Cable | Skip Hamilton | 2019-04-30 | Failure Category Hardware | Hardware
#JTC00000912 | Pending | CAT 2 | Skip Hamilton | 6 CTS | 17 | 2019-02-13 22:05:17 | 2019-02-13 22:05:17 | 15 | Student 1, M41 firing by itself rapid fire | No | M-4 | Skip Hamilton |  | Failure Category Hardware | Hardware
#JTC00000971 | Solved | CAT 3 | Robert Gaines | 6 CTS | 17 | 2019-03-05 19:36:30 | 2019-03-05 19:36:30 | 15 | Systems 15, 16, 17 have old AAJTS display cables | No | Other - See Comments | Robert Gaines | 2019-04-10 | Failure Category Other | Other
#JTC00000261 | Solved | CAT 3 | Robert Gaines | 5 ASOS | 18 | 2018-03-27 17:26:43 | 2018-03-27 17:26:43 | 18 | MACE sound scripting does not work properly with ASTi radios | No | Other - See Comments | Robert Gaines | 2019-04-22 | Failure Category Other | Other
#JTC00000605 | Pending | CAT 2 | Robert Gaines | 5 ASOS | 18 | 2018-10-26 21:37:36 | 2018-10-26 21:37:36 | 18 | M4 #1 continuously fires in MACE | No | M-4 | Robert Gaines |  | Failure Category Hardware | Hardware
#JTC00000650 | Pending | CAT 2 | Robert Gaines | 5 ASOS | 18 | 2018-11-19 16:33:42 | 2018-11-19 16:33:42 | 18 | VRSG Remote fails to consistently update the terrain search path | No | DOC Error | Robert Gaines |  | Failure Category Software | Software
#JTC00000671 | Pending | CAT 2 | Robert Gaines | 5 ASOS | 18 | 2018-11-27 23:25:58 | 2018-11-27 23:25:58 | 18 | Q-Fires Rover Crashing | No | Q-Fires ROVER Error | Robert Gaines |  | Failure Category Software | Software
#JTC00000687 | Hold | CAT 2 | Robert Gaines | 5 ASOS | 18 | 2018-12-05 15:43:54 | 2018-12-05 15:43:54 | 18 | MVP VRSG Crash | No | VRSG Error | Robert Gaines |  | Failure Category Software | Software
#JTC00000717 | Hold | CAT 2 | Robert Gaines | 5 ASOS | 18 | 2018-12-14 15:51:59 | 2018-12-14 15:51:59 | 18 | Grids unreadable on student and RPS ROVER displays | No | DIScover Error | Robert Gaines |  | Failure Category Software | Software
#JTC00000853 | Solved | CAT 3 | Robert Gaines | 5 ASOS | 18 | 2019-01-30 22:25:07 | 2019-01-30 22:25:07 | 18 | crates | No | Out of Scope | Robert Gaines | 2019-04-30 | Failure Category Other | Other
#JTC00000866 | Solved | CAT 2 | Devin Hoeckel | 5 ASOS | 18 | 2019-01-31 16:55:02 | 2019-01-31 16:55:02 | 18 | Tags and Anchors weren't showing up in DIScover | No | Indotraq Anchor | Devin Hoeckel | 2019-04-30 | Failure Category Hardware | Hardware
#JTC00000869 | Solved | CAT 3 | Robert Gaines | 5 ASOS | 18 | 2019-02-01 00:44:00 | 2019-02-01 00:44:00 | 18 | Sidetone in headset | No | ASTi Error | Robert Gaines | 2019-04-30 | Failure Category Software | Software
#JTC00000873 | Hold | CAT 3 | Devin Hoeckel | 5 ASOS | 18 | 2019-02-01 23:51:12 | 2019-02-01 23:51:12 | 18 | MACE maintenance expired | No | MACE Error | Devin Hoeckel |  | Failure Category Software | Software
#JTC00000889 | Solved | CAT 3 | Robert Gaines | 5 ASOS | 18 | 2019-02-06 21:09:57 | 2019-02-06 21:09:57 | 18 | Hotfix Installation Sequence Inquiry | No | Other - See Comments | Robert Gaines | 2019-04-30 | Failure Category Other | Other
#JTC00000890 | Solved | CAT 3 | Robert Gaines | 5 ASOS | 18 | 2019-02-06 21:49:10 | 2019-02-06 21:49:10 | 18 | Hotfix | No | Other - See Comments | Robert Gaines | 2019-04-30 | Failure Category Other | Other
#JTC00000893 | Solved | CAT 2 | Robert Gaines | 5 ASOS | 18 | 2019-02-07 18:02:29 | 2019-02-07 18:02:29 | 18 | PSC Headset not transmiting | No | Headset | Robert Gaines | 2019-04-30 | Failure Category Hardware | Hardware
#JTC00000914 | Solved | CAT 2 | Robert Gaines | 5 ASOS | 18 | 2019-02-20 15:41:27 | 2019-02-20 15:41:27 | 18 | EME Server crashed or hung during startup | No | EME-Server | Robert Gaines | 2019-04-30 | Failure Category Hardware | Hardware
#JTC00000924 | Solved | CAT 2 | Skip Hamilton | 5 ASOS | 18 | 2019-02-22 17:37:12 | 2019-02-22 17:37:12 | 18 | Nessus daemon issues | No | Nessus Scanner | Skip Hamilton | 2019-04-27 | Failure Category Software | Software
#JTC00000932 | Solved | CAT 3 | Robert Gaines | 5 ASOS | 18 | 2019-02-25 23:05:56 | 2019-02-25 23:05:56 | 18 | New operator training | No | Other - See Comments | Robert Gaines | 2019-04-27 | Failure Category Other | Other
#JTC00000965 | Hold | CAT 3 | Robert Gaines | 5 ASOS | 18 | 2019-03-01 22:02:29 | 2019-03-01 22:02:29 | 18 | Sound levels | No | ASTi Error | Robert Gaines |  | Failure Category Software | Software
#JTC00000980 | Pending | CAT 3 | Robert Gaines | 5 ASOS | 18 | 2019-03-13 14:11:23 | 2019-03-13 14:11:23 | 18 | MACE Detonation Tool Sound - Faulty Sound Mapping | No | ASTi Error | Robert Gaines |  | Failure Category Software | Software
#JTC00000998 | Solved | CAT 3 | Robert Gaines | 5 ASOS | 18 | 2019-03-19 23:42:52 | 2019-03-19 23:42:52 | 18 | DOC Dome Hud | No | DIScover Error | Robert Gaines | 2019-04-26 | Failure Category Software | Software
#JTC00000999 | Solved | CAT 3 | Robert Gaines | 5 ASOS | 18 | 2019-03-19 23:43:23 | 2019-03-19 23:43:23 | 18 | Projector shut down | No | DIScover Error | Robert Gaines | 2019-04-26 | Failure Category Software | Software
#JTC00001006 | Solved | CAT 3 | Robert Gaines | 5 ASOS | 18 | 2019-03-27 19:25:15 | 2019-03-27 19:25:15 | 18 | Multiple crashes during a DMO event | No | MACE Error | Robert Gaines | 2019-04-10 | Failure Category Software | Software
#JTC00000568 | Hold | CAT 2 | Robert Gaines | 23 STS | 19 | 2018-10-05 17:21:05 | 2018-10-05 17:21:05 | 19 | IOS Boots at Random | No | Surround Error | Robert Gaines |  | Failure Category Visual | Visual
#JTC00000840 | Solved | CAT 3 | Skip Hamilton | 23 STS | 19 | 2019-01-29 18:53:51 | 2019-01-29 18:53:51 | 14 | Calling to track down an ASTi Hard Drive Key | No | Closed by Merge | Skip Hamilton | 2019-04-30 | Failure Category Other | Other
#JTC00000841 | Solved | CAT 3 | Skip Hamilton | 23 STS | 19 | 2019-01-29 18:58:35 | 2019-01-29 18:58:35 | 14 | Site needs an ASTi Hard Drive Key, misplaced original | No | Operator Error | Skip Hamilton | 2019-04-30 | Failure Category Other | Other
#JTC00000847 | Solved | CAT 3 | Skip Hamilton | 23 STS | 19 | 2019-01-30 02:47:41 | 2019-01-30 02:47:41 | 8 | Dev 008 calling with questions about where to send Cyber scans | No | Other - See Comments | Skip Hamilton | 2019-04-30 | Failure Category Other | Other
#JTC00000888 | Solved | CAT 2 | Robert Gaines | 23 STS | 19 | 2019-02-06 20:59:58 | 2019-02-06 20:59:58 | 23 | Upgrade 2 - Installation Errors | No | Software Upgrade Issues | Robert Gaines | 2019-04-30 | Failure Category Other | Other
#JTC00000929 | Solved | CAT 3 | Skip Hamilton | 23 STS | 19 | 2019-02-25 18:21:41 | 2019-02-25 18:21:41 | 14 | Ft Polk calling about ASTi Drive Replacement | No | Closed by Merge | Skip Hamilton | 2019-04-27 | Failure Category Other | Other
#JTC00000947 | Solved | CAT 3 | Skip Hamilton | 23 STS | 19 | 2019-02-27 15:54:43 | 2019-02-27 15:54:43 | 19 | Questions on Cyber Patches and Upgrade 2 | No | Operator Error | Skip Hamilton | 2019-04-26 | Failure Category Other | Other
#JTC00000952 | Solved | CAT 2 | Skip Hamilton | 23 STS | 19 | 2019-02-27 20:25:27 | 2019-02-27 20:25:27 | 14 | Ft Polk calling about ASTi License | No | ASTi Error | Skip Hamilton | 2019-04-26 | Failure Category Software | Software
#JTC00000959 | Solved | CAT 2 | Robert Gaines | 23 STS | 19 | 2019-03-01 14:50:47 | 2019-03-01 14:50:47 | None | Merged ticket 1262 | No | Closed by Merge | Robert Gaines | 2019-04-26 | Failure Category Other | Other
#JTC00000960 | Solved | CAT 3 | Devin Hoeckel | 23 STS | 19 | 2019-03-01 15:19:36 | 2019-03-01 15:19:36 | None | Wanted to add Terrain | No | Other - See Comments | Devin Hoeckel | 2019-04-11 | Failure Category Other | Other
#JTC00000961 | Solved | CAT 3 | Skip Hamilton | 23 STS | 19 | 2019-03-01 16:10:32 | 2019-03-01 16:10:32 | 10 | IA Update Inquiry | No | Other - See Comments | Skip Hamilton | 2019-04-11 | Failure Category Other | Other
#JTC00000970 | Solved | CAT 2 | Robert Gaines | 23 STS | 19 | 2019-03-05 17:35:20 | 2019-03-05 17:35:20 | 19 | Dome Resolution Dropped | No | Surround Error | Robert Gaines | 2019-04-11 | Failure Category Visual | Visual
#JTC00000974 | Solved | CAT 2 | Robert Gaines | 23 STS | 19 | 2019-03-07 14:58:58 | 2019-03-07 14:58:58 | 19 | Discover Crashed - MVP Unresponsive | No | DIScover Error | Robert Gaines | 2019-04-11 | Failure Category Software | Software
#JTC00000977 | Solved | CAT 3 | Devin Hoeckel | 23 STS | 19 | 2019-03-08 16:53:50 | 2019-03-08 16:53:50 | 25 | Operator having trouble with system fully shutting down. | No | ASTi Error | Devin Hoeckel | 2019-04-26 | Failure Category Software | Software
#JTC00000987 | Solved | CAT 3 | Robert Gaines | 23 STS | 19 | 2019-03-14 16:52:15 | 2019-03-14 16:52:15 | 20 | RP-PC Display Issues | No | Operator Error | Robert Gaines | 2019-04-26 | Failure Category Other | Other
#JTC00000908 | Solved | CAT 3 | Steve Dumont | STTS | 20 | 2019-02-12 19:50:42 | 2019-02-12 19:50:42 | 20 | Voicemail from: Brian Hellard | No | Other - See Comments | Steve Dumont | 2019-04-30 | Failure Category Other | Other
#JTC00000973 | Solved | CAT 2 | Steve Dumont | STTS | 20 | 2019-03-06 16:16:47 | 2019-03-06 16:16:47 | 20 | Student Station 1 will not produce an image through tablet; bad mini-DP cable and extender | No | USB Cable | Steve Dumont | 2019-04-26 | Failure Category Hardware | Hardware
#JTC00000975 | Solved | CAT 2 | Steve Dumont | STTS | 20 | 2019-03-07 16:38:28 | 2019-03-07 16:38:28 | 20 | Runaway M-4 Carbine #1; device fires autonomously--need a replacement and repairs on faulty device | No | M-4 | Steve Dumont | 2019-04-23 | Failure Category Hardware | Hardware
#JTC00000995 | Solved | CAT 2 | Skip Hamilton | STTS | 20 | 2019-03-19 16:00:58 | 2019-03-19 16:00:58 | 19 | Error when switching terrain | No | DOC Error | Skip Hamilton | 2019-04-26 | Failure Category Software | Software
#JTC00001013 | Hold | CAT 2 | Steve Dumont | STTS | 20 | 2019-03-29 19:44:51 | 2019-03-29 19:44:51 | 20 | Runaway M-4 Carbine #2; device fires autonomously--repairs needed | No | M-4 | Steve Dumont |  | Failure Category Hardware | Hardware
#JTC00000838 | Solved | CAT 1 | Skip Hamilton | 13 ASOS | 21 | 2019-01-29 15:19:12 | 2019-01-29 15:19:12 | 21 | projector #3 Inop | No | Projector Failure (SONY) | Skip Hamilton | 2019-04-30 | Failure Category Visual | Visual
#JTC00000913 | Solved | CAT 1 | Robert Gaines | 13 ASOS | 21 | 2019-02-19 21:25:20 | 2019-02-19 21:25:20 | 21 | IG-2 surround and operation | No | Closed by Merge | Robert Gaines | 2019-04-30 | Failure Category Other | Other
#JTC00000921 | Solved | CAT 2 | Robert Gaines | 13 ASOS | 21 | 2019-02-21 16:41:44 | 2019-02-21 16:41:44 | 21 | VDL not transmitting to Student 2 and Terrain not loading on RPC and MVP | No | IG PC | Robert Gaines | 2019-04-29 | Failure Category Hardware | Hardware
#JTC00000926 | Pending | CAT 2 | Robert Gaines | 13 ASOS | 21 | 2019-02-22 21:02:25 | 2019-02-22 21:02:25 | 21 | Student Station won't pick up MVP ROVER feed | No | Q-Fires ROVER Error | Robert Gaines |  | Failure Category Software | Software
#JTC00000963 | Pending | CAT 3 | Devin Hoeckel | 13 ASOS | 21 | 2019-03-01 17:33:59 | 2019-03-01 17:33:59 | 21 | LED Tasklight has stopped working | No | Desk Light | Devin Hoeckel |  | Failure Category Hardware | Hardware
#JTC00000978 | Solved | CAT 2 | Robert Gaines | 13 ASOS | 21 | 2019-03-12 14:26:00 | 2019-03-12 14:26:00 | 21 | NAS Synchronization Issues | No | Network Attached Storage (NAS) | Robert Gaines | 2019-04-26 | Failure Category Hardware | Hardware
#JTC00000993 | Solved | CAT 3 | Robert Gaines | 13 ASOS | 21 | 2019-03-18 15:37:56 | 2019-03-18 15:37:56 | 21 | DAT Switch exhibits abnormal behavior - failure possible | No | Network Switch | Robert Gaines | 2019-04-09 | Failure Category Hardware | Hardware
#JTC00000397 | Hold | CAT 2 | Steve Dumont | 9 ASOS | 22 | 2018-06-13 14:11:32 | 2018-06-13 14:11:32 | 22 | Seam separation Ft Hood 9 ASOS | No | Screen Damaged | Steve Dumont |  | Failure Category Visual | Visual
#JTC00000882 | Solved | CAT 3 | Skip Hamilton | 9 ASOS | 22 | 2019-02-06 17:19:29 | 2019-02-06 17:19:29 | 24 | Anchor 6 has different firmware, causing "Version Mismatch" in IndoTraq Tab of Discover | No | Other - See Comments | Skip Hamilton | 2019-04-01 | Failure Category Other | Other
#JTC00000883 | Solved | CAT 2 | Skip Hamilton | 9 ASOS | 22 | 2019-02-06 17:21:50 | 2019-02-06 17:21:50 | 24 | Projector 8 randomly switches to NVG mode, then back to correct mode of Scenario | No | Projector Failure (SONY) | Skip Hamilton | 2019-04-08 | Failure Category Visual | Visual
#JTC00000891 | Solved | CAT 2 | Steve Dumont | 9 ASOS | 22 | 2019-02-07 17:55:34 | 2019-02-07 17:55:34 | 22 | Student 2 didn't run up properly | No | Student Station PC | Steve Dumont | 2019-04-30 | Failure Category Hardware | Hardware
#JTC00000892 | Solved | CAT 2 | Robert Gaines | 9 ASOS | 22 | 2019-02-07 17:57:31 | 2019-02-07 17:57:31 | 22 | Q-Fires crashed during training event | No | Q-Fires ROVER Error | Robert Gaines | 2019-04-30 | Failure Category Software | Software
#JTC00000894 | Solved | CAT 2 | Steve Dumont | 9 ASOS | 22 | 2019-02-07 18:02:53 | 2019-02-07 18:02:53 | 22 | IG3/projectors 5 and 6 blank | No | IG PC | Steve Dumont | 2019-04-30 | Failure Category Hardware | Hardware
#JTC00000895 | Solved | CAT 2 | Robert Gaines | 9 ASOS | 22 | 2019-02-07 21:46:09 | 2019-02-07 21:46:09 | 22 | System did not shut down after 5 attempts | No | DOC Error | Robert Gaines | 2019-04-30 | Failure Category Software | Software
#JTC00000896 | Solved | CAT 2 | Robert Gaines | 9 ASOS | 22 | 2019-02-08 14:25:37 | 2019-02-08 14:25:37 | 22 | Projector 3 and 4 projecting wrong size picture | No | Surround Error | Robert Gaines | 2019-04-30 | Failure Category Visual | Visual
#JTC00000920 | Hold | CAT 2 | Steve Dumont | 9 ASOS | 22 | 2019-02-21 01:23:20 | 2019-02-21 01:23:20 | 24 | IG8/PRJ8 Projector Cable Faulty; troubleshot cables and identified single cable non functional--restored comms using single cable 4096x2160@29hz | No | Monitor Cable | Steve Dumont |  | Failure Category Hardware | Hardware
#JTC00000923 | Solved | CAT 2 | Steve Dumont | 9 ASOS | 22 | 2019-02-22 14:15:11 | 2019-02-22 14:15:11 | 22 | Student 2 lost rover | No | Q-Fires ROVER Error | Steve Dumont | 2019-04-27 | Failure Category Software | Software
#JTC00000925 | Solved | CAT 2 | Steve Dumont | 9 ASOS | 22 | 2019-02-22 18:12:15 | 2019-02-22 18:12:15 | 22 | VRSG/MACE crashed at RP station | No | MACE Error | Steve Dumont | 2019-04-27 | Failure Category Software | Software
#JTC00000943 | Hold | CAT 3 | Steve Dumont | 9 ASOS | 22 | 2019-02-26 21:12:18 | 2019-02-26 21:12:18 | 24 | Shutter function not working from DOC to turn off light emissions from projectors | No | Projector Failure (SONY) | Steve Dumont |  | Failure Category Visual | Visual
#JTC00000864 | Solved | CAT 2 | Skip Hamilton | DMOC | 23 | 2019-01-31 16:41:30 | 2019-01-31 16:41:30 | 23 | Solid stae drive unable to be scanned | No | Other - See Comments | Skip Hamilton | 2019-04-30 | Failure Category Other | Other
#JTC00000865 | Solved | CAT 2 | Skip Hamilton | DMOC | 23 | 2019-01-31 16:49:58 | 2019-01-31 16:49:58 | 23 | System 2 Upgrade | No | Software Upgrade Issues | Skip Hamilton | 2019-04-30 | Failure Category Other | Other
#JTC00001000 | Solved | CAT 2 | Robert Gaines | DMOC | 23 | 2019-03-20 15:50:59 | 2019-03-20 15:50:59 | 23 | FW: Issues with the DOME | No | Operator Error | Robert Gaines | 2019-04-09 | Failure Category Other | Other
#JTC00001002 | Solved | CAT 2 | Devin Hoeckel | DMOC | 23 | 2019-03-26 19:39:51 | 2019-03-26 19:39:51 | 23 | Question concerning volume in the dome and boresighting the Rangers | No | Operator Error | Devin Hoeckel | 2019-04-26 | Failure Category Other | Other
#JTC00001004 | Solved | CAT 2 | Skip Hamilton | DMOC | 23 | 2019-03-26 20:18:41 | 2019-03-26 20:18:41 | 23 | Sound system creating crackling and feedback from speakers | No | ASTi Error | Skip Hamilton | 2019-04-02 | Failure Category Software | Software
#JTC00001007 | Solved | CAT 2 | Kyle Zamudio | DMOC | 23 | 2019-03-27 19:42:32 | 2019-03-27 19:42:32 | 23 | Looking for new terrain data information | No | Other - See Comments | Kyle Zamudio | 2019-04-02 | Failure Category Other | Other
#JTC00000849 | Hold | CAT 2 | Steve Dumont | 607 ASOG | 26 | 2019-01-30 11:38:38 | 2019-01-30 11:38:38 | 26 | IG 8 has a faulty dp cable | No | Monitor Cable | Steve Dumont |  | Failure Category Hardware | Hardware
#JTC00000979 | Pending | CAT 2 | Robert Gaines | 607 ASOG | 26 | 2019-03-13 05:01:07 | 2019-03-13 05:01:07 | 26 | black dot in the visual of ranger 1 | No | Ranger 47 | Robert Gaines |  | Failure Category Hardware | Hardware