## Sheet1
Ticket ID | Status | Discrepancy | Submitter | Unit | Device ID | Date/Time Reported | Date/Time Acknowledged | Notification Mode | Subject | Repeat CAT 1 | Corrective Action | Asignee | Date Rsolved | Root Cause | Remarks
#JTC00000397 | Hold | CAT 2 | Steve Dumont | QuantaDyn | 0 | 2018-06-13 14:11:32 | 2018-06-13 14:11:32 | None | Seam separation Ft Hood 9 ASOS | No | None | Steve Dumont | 2018-06-13 | Root Cause - Visual Screen Damaged | Screen Damaged
#JTC00000207 | Solved | CAT 2 | Devin Hoeckel | 14 ASOS | 3 | 2018-03-02 16:17:42 | 2018-03-02 16:17:42 | Web form | ASTi freq bleed over | No | ASTi Radios Bleeding over during DMO events. Only site to report such activity and is captured in a different ticket | Devin Hoeckel | 2018-03-02 | Root Cause - Software ASTi Error | ASTi Error
#JTC00000347 | Hold | CAT 2 | Devin Hoeckel | 14 ASOS | 3 | 2018-05-10 13:56:37 | 2018-05-10 13:56:37 | Web form | ASTI Radios bleeding over. | No | Issue sent to ASTi for review | Devin Hoeckel | 2018-05-10 | Root Cause - Software ASTi Error | ASTi Error
#JTC00000254 | Solved | CAT 2 | Chris Johnson | 7 ASOS | 4 | 2018-03-22 17:33:41 | 2018-03-22 17:33:41 | None | VRSG license expire | No | None | Chris Johnson | 2018-03-22 | Undefined | None
#JTC00000206 | Solved | CAT 2 | Chris Johnson | 20 ASOS | 5 | 2018-03-01 19:48:23 | 2018-03-01 19:48:23 | None | BAD Feb Update disk | No | None | Chris Johnson | 2018-03-01 | Undefined | None
#JTC00000216 | Solved | CAT 1 | Chris Johnson | 10 ASOS | 6 | 2018-03-06 21:14:01 | 2018-03-06 21:14:01 | None | Sony Projector login | No | None | Chris Johnson | 2018-03-06 | Undefined | None
#JTC00000217 | Solved | CAT 1 | Chris Johnson | 10 ASOS | 6 | 2018-03-07 15:24:13 | 2018-03-07 15:24:13 | None | Projector blending | No | None | Chris Johnson | 2018-03-07 | Undefined | None
#JTC00000218 | Solved | CAT 1 | Chris Johnson | 10 ASOS | 6 | 2018-03-07 15:25:17 | 2018-03-07 15:25:17 | None | Prjoector recalibration | No | None | Chris Johnson | 2018-03-07 | Undefined | None
#JTC00000310 | Pending | CAT 2 | Skip Hamilton | 10 ASOS | 6 | 2018-04-17 14:42:11 | 2018-04-17 14:42:11 | Web form | MVP visual height error during DMO events | No | Floating Entities during DMO on MVP Views | Skip Hamilton | 2019-04-01 | Root Cause - Software VRSG Error | VRSG Error
#JTC00000134 | Hold | CAT 2 | Devin Hoeckel | 19 ASOS | 7 | 2018-01-08 16:57:45 | 2018-01-08 16:57:45 | None | Entities not viewable in parts of the SW US | No | None | Devin Hoeckel | 2018-01-08 | Root Cause - Software Visual Database Discrepancy | Visual Database Discrepancy
#JTC00000224 | Pending | CAT 2 | Kyle Zamudio | 19 ASOS | 7 | 2018-03-08 21:24:00 | 2018-03-08 21:24:00 | None | ROLE Player radio transmits garbled at initial start up. | No | None | Kyle Zamudio | 2018-03-08 | Root Cause - Software ASTi Error | ASTi Error
#JTC00000232 | Solved | CAT 2 | Chris Johnson | 19 ASOS | 7 | 2018-03-14 20:33:10 | 2018-03-14 20:33:10 | None | ROLE PLAYER POD | No | None | Chris Johnson | 2018-03-14 | Undefined | None
#JTC00000245 | Solved | CAT 2 | Devin Hoeckel | 19 ASOS | 7 | 2018-03-21 20:31:23 | 2018-03-21 20:31:23 | None | EME equipment is showing up under the ground | No | None | Devin Hoeckel | 2018-03-21 | Undefined | None
#JTC00000246 | Solved | CAT 2 | Devin Hoeckel | 19 ASOS | 7 | 2018-03-21 20:38:00 | 2018-03-21 20:38:00 | None | A/C are splitting into duobles | No | None | Devin Hoeckel | 2018-03-21 | Undefined | None
#JTC00000249 | Solved | CAT 2 | Chris Johnson | 19 ASOS | 7 | 2018-03-22 14:36:37 | 2018-03-22 14:36:37 | None | Incoming call from +12704619994 | No | None | Chris Johnson | 2018-03-22 | Undefined | None
#JTC00000258 | Solved | CAT 2 | Devin Hoeckel | 19 ASOS | 7 | 2018-03-26 13:06:14 | 2018-03-26 13:06:14 | None | Scalable coming up with error message, won't run. | No | None | Devin Hoeckel | 2018-03-26 | Undefined | None
#JTC00000237 | Solved | CAT 2 | Chris Johnson | 25 ASOS | 9 | 2018-03-20 21:48:19 | 2018-03-20 21:48:19 | None | Feb 18 Scans and Update files | No | None | Chris Johnson | 2018-03-20 | Undefined | None
#JTC00000244 | Solved | CAT 1 | Devin Hoeckel | 25 ASOS | 9 | 2018-03-21 20:18:29 | 2018-03-21 20:18:29 | None | VRSG does not display correctly in dome | No | None | Devin Hoeckel | 2018-03-21 | Undefined | None
#JTC00000259 | Solved | CAT 1 | Chris Johnson | 25 ASOS | 9 | 2018-03-26 22:41:49 | 2018-03-26 22:41:49 | None | March Updates Wheeler AAF HI | No | None | Chris Johnson | 2018-03-26 | Undefined | None
#JTC00000263 | Solved | CAT 2 | Chris Johnson | 25 ASOS | 9 | 2018-03-28 22:14:08 | 2018-03-28 22:14:08 | None | Projector 1 not working | No | None | Chris Johnson | 2018-03-28 | Undefined | None
#JTC00000255 | Solved | CAT 2 | Chris Johnson | 15 ASOS | 10 | 2018-03-23 21:40:51 | 2018-03-23 21:40:51 | None | Unable to connect to Security Center through Web Interface | No | None | Chris Johnson | 2018-03-23 | Undefined | None
#JTC00000257 | Solved | CAT 2 | Devin Hoeckel | 15 ASOS | 10 | 2018-03-26 12:08:18 | 2018-03-26 12:08:18 | None | ISO is Off Line | No | None | Devin Hoeckel | 2018-03-26 | Undefined | None
#JTC00000260 | Solved | CAT 2 | Chris Johnson | 15 ASOS | 10 | 2018-03-27 12:24:03 | 2018-03-27 12:24:03 | None | ACAS Scans | No | None | Chris Johnson | 2018-03-27 | Undefined | None
#JTC00000208 | Solved | CAT 2 | Devin Hoeckel | WPC | 11 | 2018-03-02 16:29:21 | 2018-03-02 16:29:21 | None | IZLID Com Failure | No | None | Devin Hoeckel | 2018-03-02 | Undefined | None
#JTC00000209 | Solved | CAT 2 | Chris Johnson | WPC | 11 | 2018-03-02 16:36:57 | 2018-03-02 16:36:57 | None | Ground based laser spot does not show in targeting pod view. | No | None | Chris Johnson | 2018-03-02 | Undefined | None
#JTC00000228 | Solved | CAT 3 | Chris Johnson | WPC | 11 | 2018-03-13 15:40:24 | 2018-03-13 15:40:24 | None | Need number other than 877 help desk number | No | None | Chris Johnson | 2018-03-13 | Undefined | None
#JTC00000229 | Solved | CAT 2 | Chris Johnson | WPC | 11 | 2018-03-13 15:52:20 | 2018-03-13 15:52:20 | None | Help | No | None | Chris Johnson | 2018-03-13 | Undefined | None
#JTC00000233 | Solved | CAT 2 | Devin Hoeckel | WPC | 11 | 2018-03-15 13:09:39 | 2018-03-15 13:09:39 | None | IOS WakeON issue | No | None | Devin Hoeckel | 2018-03-15 | Undefined | None
#JTC00000227 | Solved | CAT 1 | Devin Hoeckel | 2 ASOS | 12 | 2018-03-09 20:05:31 | 2018-03-09 20:05:31 | None | Dome display is not synched on over 50% of dome | No | None | Devin Hoeckel | 2018-03-09 | Undefined | None
#JTC00000231 | Solved | CAT 2 | Devin Hoeckel | 2 ASOS | 12 | 2018-03-14 15:27:19 | 2018-03-14 15:27:19 | None | Incoming call from +4971170731200 | No | None | Devin Hoeckel | 2018-03-14 | Undefined | None
#JTC00000213 | Solved | CAT 3 | Chris Johnson | 20 ASOS, Det 1 | 14 | 2018-03-05 21:17:43 | 2018-03-05 21:17:43 | None | Updates | No | None | Chris Johnson | 2018-03-05 | Undefined | None
#JTC00000214 | Solved | CAT 2 | Devin Hoeckel | 20 ASOS, Det 1 | 14 | 2018-03-05 21:19:25 | 2018-03-05 21:19:25 | None | IZLID | No | None | Devin Hoeckel | 2018-03-05 | Undefined | None
#JTC00000222 | Solved | CAT 1 | Chris Johnson | 20 ASOS, Det 1 | 14 | 2018-03-08 17:27:00 | 2018-03-08 17:27:00 | None | Projector Issue | No | None | Chris Johnson | 2018-03-08 | Undefined | None
#JTC00000225 | Solved | CAT 3 | Chris Johnson | 20 ASOS, Det 1 | 14 | 2018-03-09 19:35:50 | 2018-03-09 19:35:50 | None | NESSUS results | No | None | Chris Johnson | 2018-03-09 | Undefined | None
#JTC00000168 | Hold | CAT 2 | Skip Hamilton | 6 CTS | 17 | 2018-02-08 20:30:12 | 2018-02-08 20:30:12 | None | Projector #4 image (bottom right of screen blacks out for a couple seconds or flickers and goes to a yellow/green tint over the image every 5-10 minutes | No | None | Skip Hamilton | 2018-02-08 | Root Cause - Visual DisplayPort Cable Failure | DisplayPort Cable Failure
#JTC00000171 | Hold | CAT 2 | Skip Hamilton | 6 CTS | 17 | 2018-02-08 21:32:28 | 2018-02-08 21:32:28 | None | Projector #10 image blacks out routinely for 1-3 seconds and then comes back | No | None | Skip Hamilton | 2018-02-08 | Root Cause - Visual DisplayPort Cable Failure | DisplayPort Cable Failure
#JTC00000226 | Solved | CAT 2 | Chris Johnson | 6 CTS | 17 | 2018-03-09 19:58:07 | 2018-03-09 19:58:07 | None | Black spot in Ranger | No | None | Chris Johnson | 2018-03-09 | Undefined | None
#JTC00000240 | Solved | CAT 2 | Devin Hoeckel | 6 CTS | 17 | 2018-03-21 15:37:51 | 2018-03-21 15:37:51 | None | Comm Panels /foot pedals at MVP and IOS shorting out monitors, no transmit, or constant transmit | No | None | Devin Hoeckel | 2018-03-21 | Undefined | None
#JTC00000241 | Solved | CAT 2 | Chris Johnson | 6 CTS | 17 | 2018-03-21 15:41:43 | 2018-03-21 15:41:43 | None | In-dome volume insane. | No | None | Chris Johnson | 2018-03-21 | Undefined | None
#JTC00000210 | Solved | CAT 3 | Chris Johnson | 5 ASOS | 18 | 2018-03-02 23:00:21 | 2018-03-02 23:00:21 | None | Helpdesk migration | No | None | Chris Johnson | 2018-03-02 | Undefined | None
#JTC00000211 | Solved | CAT 3 | Devin Hoeckel | 5 ASOS | 18 | 2018-03-02 23:07:13 | 2018-03-02 23:07:13 | None | Korea Terrain Database | No | None | Devin Hoeckel | 2018-03-02 | Undefined | None
#JTC00000212 | Solved | CAT 2 | Devin Hoeckel | 5 ASOS | 18 | 2018-03-03 01:07:30 | 2018-03-03 01:07:30 | None | Ranger 47 lock up | No | None | Devin Hoeckel | 2018-03-03 | Undefined | None
#JTC00000215 | Solved | CAT 2 | Chris Johnson | 5 ASOS | 18 | 2018-03-06 20:14:29 | 2018-03-06 20:14:29 | None | Projectors blinking in and out | No | None | Chris Johnson | 2018-03-06 | Undefined | None
#JTC00000219 | Solved | CAT 2 | Chris Johnson | 5 ASOS | 18 | 2018-03-07 15:59:53 | 2018-03-07 15:59:53 | None | DMO operations | No | None | Chris Johnson | 2018-03-07 | Undefined | None
#JTC00000220 | Solved | CAT 2 | Devin Hoeckel | 5 ASOS | 18 | 2018-03-07 17:16:45 | 2018-03-07 17:16:45 | None | VRSG problems after editing terrain | No | None | Devin Hoeckel | 2018-03-07 | Undefined | None
#JTC00000221 | Solved | CAT 2 | Chris Johnson | 5 ASOS | 18 | 2018-03-07 17:20:58 | 2018-03-07 17:20:58 | None | Projectors blinking in and out | No | None | Chris Johnson | 2018-03-07 | Undefined | None
#JTC00000230 | Solved | CAT 2 | Chris Johnson | 5 ASOS | 18 | 2018-03-13 19:51:12 | 2018-03-13 19:51:12 | None | Ranger 47 not tracking | No | None | Chris Johnson | 2018-03-13 | Undefined | None
#JTC00000234 | Solved | CAT 2 | Chris Johnson | 5 ASOS | 18 | 2018-03-15 21:37:44 | 2018-03-15 21:37:44 | None | Ranger locked up and more | No | None | Chris Johnson | 2018-03-15 | Undefined | None
#JTC00000235 | Solved | CAT 2 | Chris Johnson | 5 ASOS | 18 | 2018-03-15 21:41:15 | 2018-03-15 21:41:15 | None | Cloud coverage displays improperly in ROVER view | No | None | Chris Johnson | 2018-03-15 | Undefined | None
#JTC00000236 | Solved | CAT 3 | Chris Johnson | 5 ASOS | 18 | 2018-03-15 21:52:37 | 2018-03-15 21:52:37 | None | Scripting radio traffic | No | None | Chris Johnson | 2018-03-15 | Undefined | None
#JTC00000238 | Solved | CAT 2 | Chris Johnson | 5 ASOS | 18 | 2018-03-21 14:41:31 | 2018-03-21 14:41:31 | None | VRSG on MVP | No | None | Chris Johnson | 2018-03-21 | Undefined | None
#JTC00000239 | Solved | CAT 3 | Chris Johnson | 5 ASOS | 18 | 2018-03-21 15:29:16 | 2018-03-21 15:29:16 | None | UPS battery | No | None | Chris Johnson | 2018-03-21 | Undefined | None
#JTC00000248 | Solved | CAT 3 | Chris Johnson | 5 ASOS | 18 | 2018-03-22 14:33:24 | 2018-03-22 14:33:24 | None | monthly cyber security package | No | None | Chris Johnson | 2018-03-22 | Undefined | None
#JTC00000250 | Solved | CAT 2 | Chris Johnson | 5 ASOS | 18 | 2018-03-22 15:55:55 | 2018-03-22 15:55:55 | None | Voisus Comm panel display a NO ROLE SET | No | None | Chris Johnson | 2018-03-22 | Undefined | None
#JTC00000251 | Solved | CAT 2 | Chris Johnson | 5 ASOS | 18 | 2018-03-22 16:05:19 | 2018-03-22 16:05:19 | None | Incoming call from +12539670181 | No | None | Chris Johnson | 2018-03-22 | Undefined | None
#JTC00000252 | Solved | CAT 2 | Chris Johnson | 5 ASOS | 18 | 2018-03-22 16:31:20 | 2018-03-22 16:31:20 | None | Incoming call from +12539670181 | No | None | Chris Johnson | 2018-03-22 | Undefined | None
#JTC00000256 | Solved | CAT 2 | Chris Johnson | 5 ASOS | 18 | 2018-03-23 23:31:50 | 2018-03-23 23:31:50 | None | Ranger locked up | No | None | Chris Johnson | 2018-03-23 | Undefined | None
#JTC00000261 | Pending | CAT 3 | Robert Gaines | 5 ASOS | 18 | 2018-03-27 17:26:43 | 2018-03-27 17:26:43 | None | MACE sound scripting does not work properly with ASTi radios | No | None | Robert Gaines | 2018-03-27 | Root Cause - Software MACE Error | MACE Error
#JTC00000264 | Solved | CAT 3 | Devin Hoeckel | 5 ASOS | 18 | 2018-03-29 16:43:37 | 2018-03-29 16:43:37 | None | Anchor issue | No | None | Devin Hoeckel | 2018-03-29 | Undefined | None
#JTC00000223 | Solved | CAT 3 | Chris Johnson | 13 ASOS | 21 | 2018-03-08 19:09:49 | 2018-03-08 19:09:49 | None | Create Password | No | None | Chris Johnson | 2018-03-08 | Undefined | None
#JTC00000242 | Solved | CAT 2 | Chris Johnson | 13 ASOS | 21 | 2018-03-21 18:57:21 | 2018-03-21 18:57:21 | None | Sys #21 IG-2 not projecting image | No | None | Chris Johnson | 2018-03-21 | Undefined | None
#JTC00000243 | Solved | CAT 2 | Chris Johnson | 13 ASOS | 21 | 2018-03-21 19:06:55 | 2018-03-21 19:06:55 | None | IG-2 will not open and produce an image | No | None | Chris Johnson | 2018-03-21 | Undefined | None
#JTC00000247 | Solved | CAT 2 | Devin Hoeckel | 13 ASOS | 21 | 2018-03-21 21:54:25 | 2018-03-21 21:54:25 | None | Incoming call from +17195240044 | No | None | Devin Hoeckel | 2018-03-21 | Undefined | None
#JTC00000253 | Solved | CAT 2 | Devin Hoeckel | 13 ASOS | 21 | 2018-03-22 17:24:24 | 2018-03-22 17:24:24 | None | Incoming call from +17195240044 | No | None | Devin Hoeckel | 2018-03-22 | Undefined | None
#JTC00000262 | Solved | CAT 2 | Chris Johnson | 13 ASOS | 21 | 2018-03-27 19:19:15 | 2018-03-27 19:19:15 | None | Projector 1 won't turn on | No | None | Chris Johnson | 2018-03-27 | Undefined | None