## Sheet1
Ticket ID | Status | Discrepancy | Submitter | Unit | Device ID | Date/Time Reported | Date/Time Acknowledged | Notification Mode | Subject | Repeat CAT 1 | Corrective Action | Asignee | Date Resolved | Root Cause | Remarks
#JTC00000137 | Solved | CAT 1 | Chris Johnson | QunataDyn | 0 | 2018-01-10 19:58:32 | 2018-01-10 19:58:32 | None | No Voice on DIScord Play back | No | None | Chris Johnson | 2019-03-26 17:07:47 | Undefined | None
#JTC00000143 | Solved | CAT 1 | Chris Johnson | None | 0 | 2018-01-24 20:12:18 | 2018-01-24 20:12:18 | None | Log in credential. | No | None | Chris Johnson | 2019-03-26 17:08:01 | Undefined | None
#JTC00000149 | Solved | CAT 1 | Chris Johnson | None | 0 | 2018-01-26 20:51:42 | 2018-01-26 20:51:42 | None | Camera issues misssions, tear in screen, cameras lost claibration, VDL will not transmit, IR/M4 marking devices not working. | No | None | Chris Johnson | 2019-03-26 17:08:14 | Undefined | None
#JTC00000177 | Solved | CAT 2 | Chris Johnson | None | 0 | 2018-02-12 19:21:16 | 2018-02-12 19:21:16 | None | DOC doesn't open automatically on sign on | No | None | Chris Johnson | 2019-03-26 17:09:14 | Undefined | None
#JTC00000178 | Solved | CAT 2 | Devin Hoeckel | None | 0 | 2018-02-12 19:23:57 | 2018-02-12 19:23:57 | None | MACE failed to open up on startup | No | None | Devin Hoeckel | 2019-03-26 17:09:16 | Undefined | None
#JTC00000179 | Solved | CAT 2 | Chris Johnson | None | 0 | 2018-02-12 19:28:10 | 2018-02-12 19:28:10 | None | Stealth Observer isn't automatically latching upon mission opening | No | None | Chris Johnson | 2019-03-26 17:09:19 | Undefined | None
#JTC00000180 | Solved | CAT 2 | Chris Johnson | None | 0 | 2018-02-12 19:30:22 | 2018-02-12 19:30:22 | None | #1 Ranger47 is upside down on initial sim startup | No | None | Chris Johnson | 2019-03-26 17:09:21 | Undefined | None
#JTC00000181 | Solved | CAT 2 | Chris Johnson | None | 0 | 2018-02-12 19:32:54 | 2018-02-12 19:32:54 | None | ROVER Camera Attached to Acft would not go below horizon | No | None | Chris Johnson | 2019-03-26 17:09:24 | Undefined | None
#JTC00000200 | Solved | CAT 3 | Chris Johnson | QunataDyn | 0 | 2018-02-26 20:04:50 | 2018-02-26 20:04:50 | None | RE: [Non-DoD Source] Create a password for JTC-TRS TSSC | No | None | Chris Johnson | 2019-03-26 17:10:04 | Undefined | None
#JTC00000397 | Hold | CAT 2 | Steve Dumont | QuantaDyn | 0 | 2018-06-13 14:11:32 | 2018-06-13 14:11:32 | None | Seam separation Ft Hood 9 ASOS | No | None | Steve Dumont |  | Root Cause - Visual Screen Damaged | Screen Damaged
#JTC00000783 | Solved | CAT 2 | Steve Dumont | QunataDyn | 0 | 2019-01-15 20:55:16 | 2019-01-15 20:55:16 | Phone call inbound | IOS Peripherals Inop on start-up; can't login to IOS to start the rest of the system because keyboard/mouse doesn't work | No | Bad USB Hub | Steve Dumont | 2019-03-27 15:42:10 | Root Cause - Hardware USB Hub | USB Hub
#JTC00000787 | Solved | CAT 3 | Chris Johnson | 724 STG | 0 | 2019-01-16 20:24:46 | 2019-01-16 20:24:46 | None | Help Desk Accounts | No | None | Chris Johnson | 2019-03-26 17:31:38 | Undefined | None
#JTC00000788 | Solved | CAT 2 | Robert Gaines | 724 STG | 0 | 2019-01-16 20:28:12 | 2019-01-16 20:28:12 | None | Roleplayer and IOS aircraft sensors lock up and quit responding to controllers | No | None | Robert Gaines | 2019-03-26 17:31:40 | Undefined | None
#JTC00000835 | Solved | CAT 2 | Steve Dumont | QunataDyn | 0 | 2019-01-29 02:02:18 | 2019-01-29 02:02:18 | None | ASTi/Voisus Transmit Issues w/ Student Station 2 & 3 on AFSOC_Conversion after UG2 & Hotfix 1.2.7/9 | No | None | Steve Dumont | 2019-03-26 17:33:18 | Undefined | None
#JTC00000842 | Solved | CAT 2 | Steve Dumont | QunataDyn | 0 | 2019-01-29 19:57:58 | 2019-01-29 19:57:58 | None | IG3 continues to Intermittently Fall out of the Network; won't shutdown/startup from DOC; shows "Offline"--Image from PRJ 5 & 6 comes and goes | No | None | Steve Dumont | 2019-03-26 17:33:33 | Undefined | None
#JTC00000843 | Solved | CAT 2 | Steve Dumont | QunataDyn | 0 | 2019-01-29 20:07:45 | 2019-01-29 20:07:45 | None | Terrain will not Path/Write-to-File to VRSG from VRSG Remote--Have to manually modify in VRSGTerrainSearchPath, Restart System to upload Terrain | No | None | Steve Dumont | 2019-03-26 17:33:35 | Undefined | None
#JTC00000844 | Solved | CAT 2 | Skip Hamilton | QunataDyn | 0 | 2019-01-29 20:14:11 | 2019-01-29 20:14:11 | None | ASTi will not Startup on Initial Startup of SIM; have to start remotely from server | No | None | Skip Hamilton | 2019-03-26 17:33:38 | Undefined | None
#JTC00000845 | Solved | CAT 2 | Steve Dumont | QunataDyn | 0 | 2019-01-29 20:20:37 | 2019-01-29 20:20:37 | None | IG4 & 8 will not Produce an Image in Dome unless set to "Desktop Cover" under Preferances in VRSG Dashboard from both IGs | No | None | Steve Dumont | 2019-03-26 17:33:39 | Undefined | None
#JTC00000898 | Solved | CAT 3 | Robert Gaines | 724 STG | 0 | 2019-02-08 14:59:32 | 2019-02-08 14:59:32 | None | Upgrade 2 - Inquiry | No | None | Robert Gaines | 2019-03-26 17:35:31 | Undefined | None
#JTC00000985 | Open | CAT 2 | Robert Gaines | None | 0 | 2019-03-14 15:22:54 | 2019-03-14 15:22:54 | None | Projector 7 - Failure | No | None | Robert Gaines |  | Root Cause - Visual Projector Failure (SONY) | Projector Failure (SONY)
#JTC00000986 | Open | CAT 2 | Robert Gaines | None | 0 | 2019-03-14 15:26:45 | 2019-03-14 15:26:45 | None | Projector 8 - Failure | No | None | Robert Gaines |  | Root Cause - Visual Projector Failure (SONY) | Projector Failure (SONY)
#JTC00000003 | Solved | CAT 1 | Chris Johnson | 17 STS | 1 | 2017-01-10 16:31:52 | 2017-01-10 16:31:52 | None | Persistent/random projector issues on start up | No | None | Chris Johnson | 2019-03-26 17:02:42 | Undefined | None
#JTC00000004 | Solved | CAT 1 | Chris Johnson | 17 STS | 1 | 2017-01-17 18:04:41 | 2017-01-17 18:04:41 | None | Projectors 1 and 6 show disconnected and can not be controlled by DIScover | No | None | Chris Johnson | 2019-03-26 17:02:44 | Undefined | None
#JTC00000005 | Solved | CAT 1 | Chris Johnson | 17 STS | 1 | 2017-02-27 21:23:28 | 2017-02-27 21:23:28 | None | IOS PC hangs at boot | No | None | Chris Johnson | 2019-03-26 17:02:47 | Undefined | None
#JTC00000006 | Solved | CAT 1 | Chris Johnson | 17 STS | 1 | 2017-02-27 21:36:02 | 2017-02-27 21:36:02 | None | IG-6 in wrong resolution | No | None | Chris Johnson | 2019-03-26 17:02:49 | Undefined | None
#JTC00000800 | Solved | CAT 2 | Steve Dumont | 17 STS | 1 | 2019-01-23 13:35:33 | 2019-01-23 13:35:33 | Phone call inbound | Periphials, itermittent connectivy. | No | Old Orignal USB hubs no longer worked | Steve Dumont | 2019-03-27 15:41:10 | Root Cause - Hardware USB Hub | USB Hub
#JTC00000950 | Solved | CAT 3 | Robert Gaines | 17 STS | 1 | 2019-02-27 20:13:28 | 2019-02-27 20:13:28 | None | VRSG License Expiration | No | None | Robert Gaines | 2019-03-27 14:45:03 | Root Cause - Software VRSG Error | VRSG Error
#JTC00000199 | Solved | CAT 2 | Chris Johnson | 14 ASOS | 3 | 2018-02-26 19:25:14 | 2018-02-26 19:25:14 | Web form | Broken Ranger 47 | No | Ranger 47 damaged | Chris Johnson | 2019-03-27 16:48:50 | Root Cause - Other Other - See Comments | Other - See Comments
#JTC00000347 | Hold | CAT 2 | Devin Hoeckel | 14 ASOS | 3 | 2018-05-10 13:56:37 | 2018-05-10 13:56:37 | Web form | ASTI Radios bleeding over. | No | Issue sent to ASTi for review | Devin Hoeckel |  | Root Cause - Software ASTi Error | ASTi Error
#JTC00000581 | Hold | CAT 3 | Devin Hoeckel | 14 ASOS | 3 | 2018-10-10 19:37:11 | 2018-10-10 19:37:11 | None | IG Projctors color-blending/Focus needs to be adjusted. | No | None | Devin Hoeckel |  | Root Cause - Visual Calibration | Calibration
#JTC00000776 | Solved | CAT 1 | Robert Gaines | 14 ASOS | 3 | 2019-01-15 15:43:37 | 2019-01-15 15:43:37 | Web form | Ranger 47's do not function correcly | No | Ranger 47 Viewpoint incorrect | Robert Gaines | 2019-03-27 15:57:21 | Root Cause - Software DIScover Error | DIScover Error
#JTC00000777 | Solved | CAT 1 | Chris Johnson | 14 ASOS | 3 | 2019-01-15 15:44:36 | 2019-01-15 15:44:36 | Web form | ASTI comms are not working. | No | ASTi Upgrade was improperly done | Chris Johnson | 2019-03-27 15:54:10 | Root Cause - Software ASTi Error | ASTi Error
#JTC00000778 | Solved | CAT 1 | Chris Johnson | 14 ASOS | 3 | 2019-01-15 15:45:53 | 2019-01-15 15:45:53 | None | Environmental sounds not working. | No | None | Chris Johnson | 2019-03-26 17:31:19 | Undefined | None
#JTC00000779 | Solved | CAT 2 | Devin Hoeckel | 14 ASOS | 3 | 2019-01-15 15:50:33 | 2019-01-15 15:50:33 | Web form | Visuals on the projectors are starting out off surround. | No | DIScover would crash on start-up causing Projectors not to turn on prior to IGS and surround would break | Devin Hoeckel | 2019-03-27 15:53:17 | Root Cause - Software DIScover Error | DIScover Error
#JTC00000780 | Solved | CAT 2 | Robert Gaines | 14 ASOS | 3 | 2019-01-15 15:52:53 | 2019-01-15 15:52:53 | Web form | DOC not working correctly. | No | Didn't Have permissions required | Robert Gaines | 2019-03-27 15:52:00 | Root Cause - Software DOC Error | DOC Error
#JTC00000868 | Solved | CAT 3 | Chris Johnson | 14 ASOS | 3 | 2019-01-31 19:39:55 | 2019-01-31 19:39:55 | Phone call inbound | DMON VOIP phones. | No | DMON Phone to plug into what swtich | Chris Johnson | 2019-03-27 15:50:52 | Root Cause - Other Other - See Comments | Other - See Comments
#JTC00000904 | Solved | CAT 2 | Devin Hoeckel | 14 ASOS | 3 | 2019-02-11 14:14:42 | 2019-02-11 14:14:42 | Phone call inbound | Cannot receive on Radios during DMO events. | No | New ASTi update blocked DMO COMMS | Devin Hoeckel | 2019-03-27 15:49:48 | Root Cause - Other Other - See Comments | Other - See Comments
#JTC00000905 | Solved | CAT 2 | Devin Hoeckel | 14 ASOS | 3 | 2019-02-11 14:31:16 | 2019-02-11 14:31:16 | Phone call inbound | Ranger 47 issues using different Model Maps. | No | DMO Model Map issues | Devin Hoeckel | 2019-03-27 15:48:33 | Root Cause - Software VRSG Error | VRSG Error
#JTC00000954 | Solved | CAT 1 | Skip Hamilton | 14 ASOS | 3 | 2019-02-28 15:45:07 | 2019-02-28 15:45:07 | None | EME Server Fails to boot. | No | Unk, M4 showing signs of busted Tag | Skip Hamilton | 2019-03-27 14:28:04 | Root Cause - Hardware M-4 | M-4
#JTC00000955 | Pending | CAT 2 | Skip Hamilton | 14 ASOS | 3 | 2019-02-28 20:57:08 | 2019-02-28 20:57:08 | Web form | M4 needs to be repaired/replaced, was causing EME-Server boot issues | No | Faulty M4 | Skip Hamilton |  | Root Cause - Hardware M-4 | M-4
#JTC00000130 | Solved | CAT 1 | Chris Johnson | 7 ASOS | 4 | 2018-01-04 18:17:20 | 2018-01-04 18:17:20 | None | NAS timing has drifted from IOS bootup | No | None | Chris Johnson | 2019-03-26 17:07:32 | Undefined | None
#JTC00000165 | Solved | CAT 1 | Chris Johnson | 7 ASOS | 4 | 2018-02-08 17:32:00 | 2018-02-08 17:32:00 | None | HUD display not showing on MVP. | No | None | Chris Johnson | 2019-03-26 17:08:48 | Undefined | None
#JTC00000767 | Solved | CAT 2 | Robert Gaines | 7 ASOS | 4 | 2019-01-11 19:29:30 | 2019-01-11 19:29:30 | None | Voicemail from: Caller +1 (706) 545-2976 | No | None | Robert Gaines | 2019-03-26 17:30:57 | Undefined | None
#JTC00000768 | Solved | CAT 2 | Steve Dumont | 7 ASOS | 4 | 2019-01-11 19:50:47 | 2019-01-11 19:50:47 | None | Multiple Projectors have dropped Surround, IG3 still having issues from GPU replacement | No | None | Steve Dumont | 2019-03-26 17:30:59 | Undefined | None
#JTC00000784 | Solved | CAT 2 | Steve Dumont | 7 ASOS | 4 | 2019-01-16 17:41:48 | 2019-01-16 17:41:48 | None | IG1/PRJ Imaging Issues; replacement cables needed--ordered and enroute | No | None | Steve Dumont | 2019-03-26 17:31:32 | Undefined | None
#JTC00000790 | Solved | CAT 2 | Robert Gaines | 7 ASOS | 4 | 2019-01-17 18:25:34 | 2019-01-17 18:25:34 | Phone call inbound | HUD has disappeared and gamepad is unresponsive | No | DOME Hud Dropped off pre Upgrade 2 | Robert Gaines | 2019-03-27 15:45:34 | Root Cause - Software MACE Error | MACE Error
#JTC00000791 | Solved | CAT 3 | Robert Gaines | 7 ASOS | 4 | 2019-01-17 18:47:43 | 2019-01-17 18:47:43 | Phone call inbound | EME Boresighting Inquiry | No | None | Robert Gaines | 2019-03-28 16:44:46 | Root Cause - Software DIScover Error | DIScover Error
#JTC00000824 | Solved | CAT 3 | Robert Gaines | 7 ASOS | 4 | 2019-01-25 20:02:26 | 2019-01-25 20:02:26 | None | Upgrade and Hotfix Inquiry | No | None | Robert Gaines | 2019-03-26 17:32:56 | Undefined | None
#JTC00000830 | Solved | CAT 2 | Devin Hoeckel | 7 ASOS | 4 | 2019-01-28 19:27:34 | 2019-01-28 19:27:34 | None | Upgrade 2 Install Question/Issues | No | None | Devin Hoeckel | 2019-03-26 17:33:08 | Undefined | None
#JTC00000834 | Solved | CAT 2 | Skip Hamilton | 7 ASOS | 4 | 2019-01-28 22:46:38 | 2019-01-28 22:46:38 | None | Upgrade 2 Install Questions/Issues | No | None | Skip Hamilton | 2019-03-26 17:33:16 | Undefined | None
#JTC00000839 | Solved | CAT 3 | Skip Hamilton | 7 ASOS | 4 | 2019-01-29 17:38:55 | 2019-01-29 17:38:55 | None | Issues/Questions with MVP and RPS post Upgarde 2 | No | None | Skip Hamilton | 2019-03-26 17:33:27 | Undefined | None
#JTC00000851 | Solved | CAT 3 | Steve Dumont | 7 ASOS | 4 | 2019-01-30 19:33:33 | 2019-01-30 19:33:33 | None | Assisted Client w/EME Configuration post UG2 | No | None | Steve Dumont | 2019-03-26 17:33:53 | Undefined | None
#JTC00000867 | Solved | CAT 2 | Devin Hoeckel | 7 ASOS | 4 | 2019-01-31 18:20:21 | 2019-01-31 18:20:21 | None | Ranger 1 not tracking and functions (lrf, laser, ) not working. | No | None | Devin Hoeckel | 2019-03-26 17:34:27 | Undefined | None
#JTC00000899 | Solved | CAT 1 | Robert Gaines | 7 ASOS | 4 | 2019-02-08 16:00:47 | 2019-02-08 16:00:47 | None | DIScover not populating with correct settings post 1.2.9 installation | No | None | Robert Gaines | 2019-03-26 17:35:34 | Undefined | None
#JTC00000901 | Solved | CAT 2 | Devin Hoeckel | 7 ASOS | 4 | 2019-02-08 18:48:58 | 2019-02-08 18:48:58 | None | Ranger 1 scroll wheel does not incrementally scroll. | No | None | Devin Hoeckel | 2019-03-26 17:35:38 | Undefined | None
#JTC00000902 | Solved | CAT 2 | Devin Hoeckel | 7 ASOS | 4 | 2019-02-08 18:53:25 | 2019-02-08 18:53:25 | None | Anchor 1 is intermittently connecting. | No | None | Devin Hoeckel | 2019-03-26 17:35:40 | Undefined | None
#JTC00000909 | Solved | CAT 2 | Steve Dumont | 7 ASOS | 4 | 2019-02-12 22:25:10 | 2019-02-12 22:25:10 | None | Voicemail from: Andre Aragon | No | None | Steve Dumont | 2019-03-26 17:35:55 | Undefined | None
#JTC00000910 | Hold | CAT 2 | Steve Dumont | 7 ASOS | 4 | 2019-02-13 13:24:45 | 2019-02-13 13:24:45 | Web form | Can't Calibrate Projectors through scalable; IG3 Error stating "Wrong Resolution Detected" | No | Attempted multiple fixes from two help desk agents and IDSI to resolve calibration issues. We were unable and need additional support to fix the problem | Steve Dumont |  | Root Cause - Software Scalable Error | Scalable Error
#JTC00000915 | Solved | CAT 2 | Robert Gaines | 7 ASOS | 4 | 2019-02-20 17:35:35 | 2019-02-20 17:35:35 | None | Phone Call from: Andre Aragon | No | None | Robert Gaines | 2019-03-26 17:36:07 | Undefined | None
#JTC00000916 | Solved | CAT 2 | Robert Gaines | 7 ASOS | 4 | 2019-02-20 18:39:58 | 2019-02-20 18:39:58 | None | Phone Call from: Andre Aragon | No | None | Robert Gaines | 2019-03-26 17:36:09 | Undefined | None
#JTC00000917 | Solved | CAT 2 | Robert Gaines | 7 ASOS | 4 | 2019-02-20 18:52:01 | 2019-02-20 18:52:01 | None | Connectivity failure during networked event | No | None | Robert Gaines | 2019-03-26 17:36:11 | Undefined | None
#JTC00000928 | Solved | CAT 2 | Robert Gaines | 7 ASOS | 4 | 2019-02-25 17:51:39 | 2019-02-25 17:51:39 | Phone call inbound | DMO connection troubleshooting | No | Missing DIS network cable | Robert Gaines | 2019-03-28 16:56:53 | Root Cause - Other Other - See Comments | Other - See Comments
#JTC00000930 | Solved | CAT 2 | Skip Hamilton | 7 ASOS | 4 | 2019-02-25 19:06:02 | 2019-02-25 19:06:02 | None | DMO Testing Issues | No | None | Skip Hamilton | 2019-03-26 17:36:41 | Undefined | None
#JTC00000934 | Solved | CAT 2 | Robert Gaines | 7 ASOS | 4 | 2019-02-26 16:09:28 | 2019-02-26 16:09:28 | None | Voicemail from: Andre Aragon | No | None | Robert Gaines | 2019-03-26 17:36:51 | Undefined | None
#JTC00000935 | Solved | CAT 2 | Robert Gaines | 7 ASOS | 4 | 2019-02-26 16:41:40 | 2019-02-26 16:41:40 | None | Voicemail from: Andre Aragon | No | None | Robert Gaines | 2019-03-26 17:36:53 | Undefined | None
#JTC00000942 | Solved | CAT 3 | Steve Dumont | 7 ASOS | 4 | 2019-02-26 18:55:27 | 2019-02-26 18:55:27 | None | Phone Call from: Andre Aragon | No | None | Steve Dumont | 2019-03-26 17:37:09 | Undefined | None
#JTC00000135 | Solved | CAT 2 | Chris Johnson | 20 ASOS | 5 | 2018-01-10 16:25:14 | 2018-01-10 16:25:14 | None | Rover / Ranger 47 not working with DTOC/ No Audio connection with DTOC | No | None | Chris Johnson | 2019-03-26 17:07:43 | Undefined | None
#JTC00000136 | Solved | CAT 1 | Chris Johnson | 20 ASOS | 5 | 2018-01-10 16:30:24 | 2018-01-10 16:30:24 | None | JTC TRS SCWG Change Request | No | None | Chris Johnson | 2019-03-26 17:07:45 | Undefined | None
#JTC00000140 | Solved | CAT 2 | Devin Hoeckel | 20 ASOS | 5 | 2018-01-17 12:47:37 | 2018-01-17 12:47:37 | None | ASTI / VOISUS | No | None | Devin Hoeckel | 2019-03-26 17:07:53 | Undefined | None
#JTC00000170 | Solved | CAT 1 | Chris Johnson | 20 ASOS | 5 | 2018-02-08 20:42:41 | 2018-02-08 20:42:41 | None | Locked out of user account | No | None | Chris Johnson | 2019-03-26 17:08:59 | Undefined | None
#JTC00000201 | Solved | CAT 2 | Chris Johnson | 20 ASOS | 5 | 2018-02-28 13:10:13 | 2018-02-28 13:10:13 | None | M4 Shoot constantly without pulling trigger | No | None | Chris Johnson | 2019-03-26 17:10:06 | Undefined | None
#JTC00000202 | Solved | CAT 2 | Chris Johnson | 20 ASOS | 5 | 2018-02-28 13:13:47 | 2018-02-28 13:13:47 | None | COMMs Fail | No | None | Chris Johnson | 2019-03-26 17:10:08 | Undefined | None
#JTC00000203 | Solved | CAT 2 | Chris Johnson | 20 ASOS | 5 | 2018-02-28 13:16:44 | 2018-02-28 13:16:44 | None | Can not communicat with DTOC Voice | No | None | Chris Johnson | 2019-03-26 17:10:10 | Undefined | None
#JTC00000204 | Solved | CAT 2 | Chris Johnson | 20 ASOS | 5 | 2018-02-28 13:19:09 | 2018-02-28 13:19:09 | None | MVP VRSG shutting down | No | None | Chris Johnson | 2019-03-26 17:10:12 | Undefined | None
#JTC00000564 | Pending | CAT 2 | Robert Gaines | 20 ASOS | 5 | 2018-10-04 12:19:12 | 2018-10-04 12:19:12 | None | PEQ-15 from M4 #2 broken tab & PEQ-15 from M4 #1 broken mount | No | None | Robert Gaines |  | Root Cause - Hardware M-4 | M-4
#JTC00000796 | Solved | CAT 2 | Devin Hoeckel | 20 ASOS | 5 | 2019-01-22 17:44:50 | 2019-01-22 17:44:50 | None | Phone Call from: Caller +1 (315) 767-7840 | No | None | Devin Hoeckel | 2019-03-26 17:31:58 | Undefined | None
#JTC00000805 | Solved | CAT 3 | Robert Gaines | 20 ASOS | 5 | 2019-01-23 21:15:16 | 2019-01-23 21:15:16 | None | Voicemail from: Caller +1 (315) 767-7840 | No | None | Robert Gaines | 2019-03-26 17:32:16 | Undefined | None
#JTC00000827 | Solved | CAT 1 | Devin Hoeckel | 20 ASOS | 5 | 2019-01-28 14:14:52 | 2019-01-28 14:14:52 | None | JTC TRS not working properly/Discover not seeing Anckers nor Tags/ Discover not starting/Sound not Working | No | None | Devin Hoeckel | 2019-03-26 17:33:02 | Undefined | None
#JTC00000872 | Hold | CAT 2 | Skip Hamilton | 20 ASOS | 5 | 2019-02-01 20:05:35 | 2019-02-01 20:05:35 | Web form | Ranger47 1 and 2 Mounts need to be replaced/repaired | No | Ranger 47 Screws were stripped from usage | Skip Hamilton |  | Root Cause - Other Other - See Comments | Other - See Comments
#JTC00000874 | Solved | CAT 2 | Skip Hamilton | 20 ASOS | 5 | 2019-02-02 01:45:19 | 2019-02-02 01:45:19 | Web form | Anchor 1 has the incorrect Firmware installed and is causing the rest of the Tags/Anchors to show "Device Mismatch" in DIScover IndoTraq Tab | No | Anchor 1 has the wrong firmware flashed, but isn't causing any issues with tracking | Skip Hamilton | 2019-03-28 01:02:13 | Root Cause - Other Other - See Comments | Other - See Comments
#JTC00000877 | Solved | CAT 2 | Robert Gaines | 20 ASOS | 5 | 2019-02-04 21:34:41 | 2019-02-04 21:34:41 | Web form | Asti | No | ASTi sounds are dependent on MACE Lock to JTAC entity | Robert Gaines | 2019-03-28 00:34:31 | Root Cause - Software ASTi Error | ASTi Error
#JTC00000878 | Solved | CAT 2 | Skip Hamilton | 20 ASOS | 5 | 2019-02-04 21:37:38 | 2019-02-04 21:37:38 | Web form | Rover Feed Student 2 Station | No | Operator couldn't move Info box out of image boundary | Skip Hamilton | 2019-03-28 00:32:19 | Root Cause - Software Q-Fires ROVER Error | Q-Fires ROVER Error
#JTC00000927 | Solved | CAT 3 | Robert Gaines | 20 ASOS | 5 | 2019-02-25 14:18:57 | 2019-02-25 14:18:57 | None | VRSG licenses expiring in 60 days | No | None | Robert Gaines | 2019-03-26 17:36:34 | Undefined | None
#JTC00000981 | Hold | CAT 2 | Robert Gaines | 20 ASOS | 5 | 2019-03-14 12:08:12 | 2019-03-14 12:08:12 | None | MVP VRSG shutting down | No | None | Robert Gaines |  | Root Cause - Software VRSG Error | VRSG Error
#JTC00000982 | Pending | CAT 2 | Skip Hamilton | 20 ASOS | 5 | 2019-03-14 12:11:20 | 2019-03-14 12:11:20 | Web form | Scenario Editor not opening. | No | VRSG Scenario Editor issues | Skip Hamilton |  | Root Cause - Software VRSG Error | VRSG Error
#JTC00000983 | Pending | CAT 2 | Robert Gaines | 20 ASOS | 5 | 2019-03-14 12:20:55 | 2019-03-14 12:20:55 | None | Physical Security | No | None | Robert Gaines |  | Root Cause - Other Other - See Comments | Other - See Comments
#JTC00000984 | Pending | CAT 2 | Robert Gaines | 20 ASOS | 5 | 2019-03-14 12:51:28 | 2019-03-14 12:51:28 | None | Rover Feed at Student 2 Station | No | None | Robert Gaines |  | Root Cause - Software Q-Fires ROVER Error | Q-Fires ROVER Error
#JTC00000148 | Solved | CAT 1 | Chris Johnson | 10 ASOS | 6 | 2018-01-26 18:33:08 | 2018-01-26 18:33:08 | None | 10 ASOS 26January ACAS Results | No | None | Chris Johnson | 2019-03-26 17:08:11 | Undefined | None
#JTC00000191 | Solved | CAT 3 | Chris Johnson | 10 ASOS | 6 | 2018-02-20 21:38:50 | 2018-02-20 21:38:50 | None | 10 ASOS February ACAS Results | No | None | Chris Johnson | 2019-03-26 17:09:45 | Undefined | None
#JTC00000194 | Solved | CAT 2 | Devin Hoeckel | 10 ASOS | 6 | 2018-02-21 17:36:24 | 2018-02-21 17:36:24 | None | Line in dome image | No | None | Devin Hoeckel | 2019-03-26 17:09:51 | Undefined | None
#JTC00000205 | Solved | CAT 1 | Chris Johnson | 10 ASOS | 6 | 2018-02-28 15:15:55 | 2018-02-28 15:15:55 | None | Projector 6 disconnected | No | None | Chris Johnson | 2019-03-26 17:10:15 | Undefined | None
#JTC00000310 | Pending | CAT 2 | Skip Hamilton | 10 ASOS | 6 | 2018-04-17 14:42:11 | 2018-04-17 14:42:11 | Web form | MVP visual height error during DMO events | No | Floating Entities during DMO on MVP Views | Skip Hamilton |  | Root Cause - Software VRSG Error | VRSG Error
#JTC00000782 | Solved | CAT 2 | Steve Dumont | 10 ASOS | 6 | 2019-01-15 19:00:37 | 2019-01-15 19:00:37 | None | VDL feed student station #2 | No | None | Steve Dumont | 2019-03-26 17:31:27 | Undefined | None
#JTC00000850 | Solved | CAT 2 | Skip Hamilton | 10 ASOS | 6 | 2019-01-30 15:56:45 | 2019-01-30 15:56:45 | None | Student Station #1 Radio, MVP Stealth View | No | None | Skip Hamilton | 2019-03-26 17:33:51 | Undefined | None
#JTC00000900 | Solved | CAT 3 | Skip Hamilton | 10 ASOS | 6 | 2019-02-08 16:01:17 | 2019-02-08 16:01:17 | None | 1.2.9 upgrade | No | None | Skip Hamilton | 2019-03-26 17:35:36 | Undefined | None
#JTC00000907 | Solved | CAT 1 | Skip Hamilton | 10 ASOS | 6 | 2019-02-12 18:25:16 | 2019-02-12 18:25:16 | None | Multiple issues: Projector #7 error light, ect. | No | None | Skip Hamilton | 2019-03-26 17:35:51 | Undefined | None
#JTC00000133 | Solved | CAT 1 | Chris Johnson | 19 ASOS | 7 | 2018-01-08 16:39:55 | 2018-01-08 16:39:55 | None | Serval AC have no sound | No | None | Chris Johnson | 2019-03-26 17:07:38 | Undefined | None
#JTC00000134 | Hold | CAT 2 | Devin Hoeckel | 19 ASOS | 7 | 2018-01-08 16:57:45 | 2018-01-08 16:57:45 | None | Entities not viewable in parts of the SW US | No | None | Devin Hoeckel |  | Root Cause - Software Visual Database Discrepancy | Visual Database Discrepancy
#JTC00000138 | Solved | CAT 1 | Chris Johnson | 19 ASOS | 7 | 2018-01-10 21:08:30 | 2018-01-10 21:08:30 | None | IZLID INOP | No | None | Chris Johnson | 2019-03-26 17:07:49 | Undefined | None
#JTC00000145 | Solved | CAT 1 | Chris Johnson | 19 ASOS | 7 | 2018-01-25 20:01:49 | 2018-01-25 20:01:49 | None | When a cultural flying entity (aircraft or helicopter) is placed in MACE with the Mission Builder>Cultural dropdown. The entity is below the surface. | No | None | Chris Johnson | 2019-03-26 17:08:05 | Undefined | None
#JTC00000146 | Solved | CAT 1 | Chris Johnson | 19 ASOS | 7 | 2018-01-26 18:01:47 | 2018-01-26 18:01:47 | None | New IZLID received, Port Failure upon installation | No | None | Chris Johnson | 2019-03-26 17:08:07 | Undefined | None
#JTC00000224 | Pending | CAT 2 | Kyle Zamudio | 19 ASOS | 7 | 2018-03-08 21:24:00 | 2018-03-08 21:24:00 | None | ROLE Player radio transmits garbled at initial start up. | No | None | Kyle Zamudio |  | Root Cause - Software ASTi Error | ASTi Error
#JTC00000766 | Solved | CAT 2 | Robert Gaines | 19 ASOS | 7 | 2019-01-11 15:30:11 | 2019-01-11 15:30:11 | None | Phone Call from: Craig Hillsman | No | None | Robert Gaines | 2019-03-26 17:30:55 | Undefined | None
#JTC00000807 | Solved | CAT 2 | Skip Hamilton | 19 ASOS | 7 | 2019-01-24 15:25:04 | 2019-01-24 15:25:04 | Web form | DOC shutting down | No | DOC was shutting down to known bug with Gamepad not being recognized by Win10 | Skip Hamilton | 2019-03-28 01:04:15 | Root Cause - Software DOC Error | DOC Error
#JTC00000808 | Solved | CAT 2 | Devin Hoeckel | 19 ASOS | 7 | 2019-01-24 15:27:37 | 2019-01-24 15:27:37 | None | None of the sound boxes are working | No | None | Devin Hoeckel | 2019-03-26 17:32:22 | Undefined | None
#JTC00000810 | Solved | CAT 2 | Robert Gaines | 19 ASOS | 7 | 2019-01-24 16:02:35 | 2019-01-24 16:02:35 | None | Voicemail from: Craig Hillsman | No | None | Robert Gaines | 2019-03-26 17:32:26 | Undefined | None
#JTC00000825 | Solved | CAT 2 | Devin Hoeckel | 19 ASOS | 7 | 2019-01-28 13:50:51 | 2019-01-28 13:50:51 | None | Issue with attaching characters | No | None | Devin Hoeckel | 2019-03-26 17:32:58 | Undefined | None
#JTC00000826 | Solved | CAT 3 | Chris Johnson | 19 ASOS | 7 | 2019-01-28 13:52:44 | 2019-01-28 13:52:44 | None | New Terrain | No | None | Chris Johnson | 2019-03-26 17:33:00 | Undefined | None
#JTC00000828 | Solved | CAT 2 | Devin Hoeckel | 19 ASOS | 7 | 2019-01-28 14:33:13 | 2019-01-28 14:33:13 | None | View in Dome is not correct when entity is attached to a vehicle. | No | None | Devin Hoeckel | 2019-03-26 17:33:05 | Undefined | None
#JTC00000852 | Solved | CAT 1 | Skip Hamilton | 19 ASOS | 7 | 2019-01-30 20:44:27 | 2019-01-30 20:44:27 | None | DIScover issue | No | None | Skip Hamilton | 2019-03-26 17:33:55 | Undefined | None
#JTC00000854 | Solved | CAT 1 | Robert Gaines | 19 ASOS | 7 | 2019-01-31 14:16:18 | 2019-01-31 14:16:18 | None | DOME images out of sequence | No | None | Robert Gaines | 2019-03-26 17:34:00 | Undefined | None
#JTC00000855 | Open | CAT 2 | Skip Hamilton | 19 ASOS | 7 | 2019-01-31 14:19:00 | 2019-01-31 14:19:00 | None | DOME image color and blending is very poor | No | None | Skip Hamilton |  | Root Cause - Visual Calibration | Calibration
#JTC00000856 | Solved | CAT 2 | Devin Hoeckel | 19 ASOS | 7 | 2019-01-31 14:48:10 | 2019-01-31 14:48:10 | None | Dome came up with surround Broken...Projectors not coming on in time. | No | None | Devin Hoeckel | 2019-03-26 17:34:04 | Undefined | None
#JTC00000870 | Solved | CAT 3 | Skip Hamilton | 19 ASOS | 7 | 2019-02-01 15:08:14 | 2019-02-01 15:08:14 | None | MACE maintenance expired | No | None | Skip Hamilton | 2019-03-26 17:34:34 | Undefined | None
#JTC00000871 | Solved | CAT 2 | Devin Hoeckel | 19 ASOS | 7 | 2019-02-01 17:31:26 | 2019-02-01 17:31:26 | None | IG7 appears to have a bad displayport cable. | No | None | Devin Hoeckel | 2019-03-26 17:34:36 | Undefined | None
#JTC00000879 | Solved | CAT 3 | Kyle Zamudio | 19 ASOS | 7 | 2019-02-05 13:34:39 | 2019-02-05 13:34:39 | Web form | HotFix 1.2.9 | No | Operator was requesting for updated install instructions for HF 1.2.9 | Kyle Zamudio | 2019-03-28 00:38:26 | Root Cause - Software Q-Fires Startup Error | Q-Fires Startup Error
#JTC00000897 | Pending | CAT 3 | Robert Gaines | 19 ASOS | 7 | 2019-02-08 14:53:23 | 2019-02-08 14:53:23 | None | TrackIR | No | None | Robert Gaines |  | Root Cause - Hardware TrackIR | TrackIR
#JTC00000906 | Solved | CAT 3 | Devin Hoeckel | 19 ASOS | 7 | 2019-02-11 17:12:23 | 2019-02-11 17:12:23 | Web form | JTAC Ranger no Roofclamping | No | Operator didn't properly install 1.2.9 HF for QFires | Devin Hoeckel | 2019-03-28 00:36:45 | Root Cause - Software Q-Fires Startup Error | Q-Fires Startup Error
#JTC00000958 | Pending | CAT 3 | Robert Gaines | 19 ASOS | 7 | 2019-03-01 14:26:53 | 2019-03-01 14:26:53 | None | IZLID cap no longer functional | No | None | Robert Gaines |  | Root Cause - Hardware IZLID | IZLID
#JTC00000991 | Pending | CAT 2 | Robert Gaines | 19 ASOS | 7 | 2019-03-14 20:32:25 | 2019-03-14 20:32:25 | None | ROVER feed | No | None | Robert Gaines |  | Undefined | None
#JTC00000153 | Solved | CAT 1 | Chris Johnson | 3 ASOS, Det 1 | 8 | 2018-01-29 22:50:00 | 2018-01-29 22:50:00 | None | Surround not working | No | None | Chris Johnson | 2019-03-26 17:08:22 | Undefined | None
#JTC00000749 | Solved | CAT 2 | Robert Gaines | 3 ASOS, Det 1 | 8 | 2019-01-02 18:57:49 | 2019-01-02 18:57:49 | None | HOTAS Throttle has shorted out | No | None | Robert Gaines | 2019-03-26 17:30:16 | Undefined | None
#JTC00000760 | Solved | CAT 3 | Kyle Zamudio | 3 ASOS, Det 1 | 8 | 2019-01-10 07:25:27 | 2019-01-10 07:25:27 | None | DORT will not populate scenario | No | MACE had wrong DIS settings | Kyle Zamudio | 2019-03-26 19:50:12 | Root Cause - Software MACE Error | MACE Error
#JTC00000761 | Solved | CAT 2 | Robert Gaines | 3 ASOS, Det 1 | 8 | 2019-01-10 07:35:26 | 2019-01-10 07:35:26 | Web form | FMV feed choppy or frozen | No | Operator attempted to change VDL code on DOC | Robert Gaines | 2019-03-28 00:43:09 | Root Cause - Software DOC Error | DOC Error
#JTC00000789 | Pending | CAT 3 | Devin Hoeckel | 3 ASOS, Det 1 | 8 | 2019-01-17 17:08:27 | 2019-01-17 17:08:27 | None | Dome Image Blurry | No | None | Devin Hoeckel |  | Root Cause - Visual Calibration | Calibration
#JTC00000822 | Solved | CAT 3 | Kyle Zamudio | 3 ASOS, Det 1 | 8 | 2019-01-25 15:42:08 | 2019-01-25 15:42:08 | None | Track IR not seeing headset | No | TrackIR was crashing, reinstalled software | Kyle Zamudio | 2019-03-26 19:47:23 | Root Cause - Software VRSG Error | VRSG Error
#JTC00000823 | Pending | CAT 2 | Robert Gaines | 3 ASOS, Det 1 | 8 | 2019-01-25 16:05:04 | 2019-01-25 16:05:04 | None | Projector 8 not booting up and has "XOXOXO" on it. Incorrect Resolution | No | None | Robert Gaines |  | Root Cause - Visual Projector Failure (SONY) | Projector Failure (SONY)
#JTC00000182 | Solved | CAT 3 | Chris Johnson | 25 ASOS | 9 | 2018-02-12 22:16:52 | 2018-02-12 22:16:52 | None | Update and Scans Jan 2018 | No | None | Chris Johnson | 2019-03-26 17:09:26 | Undefined | None
#JTC00000186 | Solved | CAT 3 | Chris Johnson | 25 ASOS | 9 | 2018-02-14 21:47:39 | 2018-02-14 21:47:39 | None | Jan Scans 2nd time :-) | No | None | Chris Johnson | 2019-03-26 17:09:35 | Undefined | None
#JTC00000764 | Solved | CAT 2 | Robert Gaines | 25 ASOS | 9 | 2019-01-10 22:23:54 | 2019-01-10 22:23:54 | None | DIS traffic broadcasting on 192.168.120.11 port 5069 and DMO setting are suppose to be on the new port 6993 | No | None | Robert Gaines | 2019-03-26 17:30:50 | Undefined | None
#JTC00000765 | Pending | CAT 2 | Robert Gaines | 25 ASOS | 9 | 2019-01-10 22:25:35 | 2019-01-10 22:25:35 | None | Degraded video quality from MVP VRSG | No | None | Robert Gaines |  | Root Cause - Software Q-Fires ROVER Error | Q-Fires ROVER Error
#JTC00000769 | Solved | CAT 2 | Robert Gaines | 25 ASOS | 9 | 2019-01-11 23:31:14 | 2019-01-11 23:31:14 | None | 3D mouse doesn't work | No | None | Robert Gaines | 2019-03-26 17:31:01 | Undefined | None
#JTC00000770 | Pending | CAT 2 | Robert Gaines | 25 ASOS | 9 | 2019-01-11 23:38:23 | 2019-01-11 23:38:23 | None | absent transporter erector launcher (TEL) in VRSG | No | None | Robert Gaines |  | Root Cause - Software Visual Database Discrepancy | Visual Database Discrepancy
#JTC00000832 | Solved | CAT 2 | Kyle Zamudio | 25 ASOS | 9 | 2019-01-28 20:00:16 | 2019-01-28 20:00:16 | None | Cable - Custom Intfc to military Headset | No | None | Kyle Zamudio | 2019-03-26 17:33:12 | Undefined | None
#JTC00000846 | Solved | CAT 2 | Skip Hamilton | 25 ASOS | 9 | 2019-01-29 23:57:12 | 2019-01-29 23:57:12 | Web form | Dome view from the shoes of the standing JTAC | No | MACE Visual Settings were incorrect | Skip Hamilton | 2019-03-28 00:47:49 | Root Cause - Software MACE Error | MACE Error
#JTC00000885 | Solved | CAT 2 | Skip Hamilton | 25 ASOS | 9 | 2019-02-06 19:12:16 | 2019-02-06 19:12:16 | Web form | IZLID is LED Malfunction | No | DIScover dropped IZLID COM port after Upgrade 2 . | Skip Hamilton | 2019-03-28 00:46:36 | Root Cause - Software DIScover Error | DIScover Error
#JTC00000922 | Solved | CAT 3 | Kyle Zamudio | 25 ASOS | 9 | 2019-02-21 18:25:50 | 2019-02-21 18:25:50 | Web form | Package from Quatadyn returned | No | Operator was updating mailing information to avoid return to sender packages | Kyle Zamudio | 2019-03-28 00:45:09 | Root Cause - Other Other - See Comments | Other - See Comments
#JTC00000142 | Solved | CAT 1 | Chris Johnson | 15 ASOS | 10 | 2018-01-19 15:17:06 | 2018-01-19 15:17:06 | None | Patch file corrupt | No | None | Chris Johnson | 2019-03-26 17:07:59 | Undefined | None
#JTC00000524 | Hold | CAT 2 | Skip Hamilton | 15 ASOS | 10 | 2018-09-04 12:49:03 | 2018-09-04 12:49:03 | None | Tear in screen | No | None | Skip Hamilton |  | Root Cause - Visual Screen Damaged | Screen Damaged
#JTC00000821 | Solved | CAT 3 | Robert Gaines | 15 ASOS | 10 | 2019-01-25 14:38:25 | 2019-01-25 14:38:25 | None | Upgrade 2 Process Inquiry | No | None | Robert Gaines | 2019-03-26 17:32:50 | Undefined | None
#JTC00000829 | Solved | CAT 2 | Robert Gaines | 15 ASOS | 10 | 2019-01-28 19:10:57 | 2019-01-28 19:10:57 | None | Post Upgrade 2 issues, IZLID, Ranger 47, DOME HUD, VLC Student 2 | No | None | Robert Gaines | 2019-03-27 15:05:03 | Undefined | None
#JTC00000833 | Solved | CAT 2 | Robert Gaines | 15 ASOS | 10 | 2019-01-28 21:14:08 | 2019-01-28 21:14:08 | None | Post Upgrade 2 issues, IZLID, Ranger 47, DOME HUD, VLC Student 2 | No | None | Robert Gaines | 2019-03-26 17:33:14 | Undefined | None
#JTC00000836 | Solved | CAT 2 | Skip Hamilton | 15 ASOS | 10 | 2019-01-29 13:57:55 | 2019-01-29 13:57:55 | None | Multiple Issues Post Upgrade 2 | No | None | Skip Hamilton | 2019-03-26 17:33:21 | Undefined | None
#JTC00000837 | Solved | CAT 3 | Skip Hamilton | 15 ASOS | 10 | 2019-01-29 15:16:36 | 2019-01-29 15:16:36 | None | Jan 19 Scans (UNCLASSIFIED) | No | None | Skip Hamilton | 2019-03-26 17:33:23 | Undefined | None
#JTC00000857 | Solved | CAT 2 | Skip Hamilton | 15 ASOS | 10 | 2019-01-31 14:50:25 | 2019-01-31 14:50:25 | Phone call inbound | Izlid Tag was set to wrong one, IZLID cap isn't functioning correctly, set to ignore IZLID functions | No | IZLID tag was set to wrong Tag and IZLID Cap switch was malfunctioning | Skip Hamilton | 2019-03-28 00:51:01 | Root Cause - Software DIScover Error | DIScover Error
#JTC00000918 | Solved | CAT 2 | Skip Hamilton | 15 ASOS | 10 | 2019-02-20 19:47:32 | 2019-02-20 19:47:32 | Phone call inbound | IZLID TAG | No | IZLID Tag was broken/damaged | Skip Hamilton | 2019-03-28 00:51:41 | Root Cause - Hardware IZLID | IZLID
#JTC00000183 | Solved | CAT 3 | Chris Johnson | WPC | 11 | 2018-02-13 08:17:14 | 2018-02-13 08:17:14 | None | January 2018 JTC TRS_WPC Scan | No | None | Chris Johnson | 2019-03-26 17:09:28 | Undefined | None
#JTC00000198 | Solved | CAT 2 | Chris Johnson | WPC | 11 | 2018-02-26 14:52:11 | 2018-02-26 14:52:11 | None | WPC Projector 2 INOP | No | None | Chris Johnson | 2019-03-26 17:09:59 | Undefined | None
#JTC00000702 | Open | CAT 2 | Skip Hamilton | WPC | 11 | 2018-12-11 11:58:14 | 2018-12-11 11:58:14 | None | MVP Crashing | No | None | Skip Hamilton |  | Root Cause - Software VRSG Error | VRSG Error
#JTC00000903 | Solved | CAT 1 | Skip Hamilton | WPC | 11 | 2019-02-11 11:53:18 | 2019-02-11 11:53:18 | Voicemail | IOS INOP | No | Operator accidentally started the cold start process of the IOS | Skip Hamilton | 2019-03-28 00:52:56 | Root Cause - Other Operator Error | Operator Error
#JTC00000972 | Pending | CAT 2 | Robert Gaines | WPC | 11 | 2019-03-06 13:40:32 | 2019-03-06 13:40:32 | None | RP Station INOP on NATO Secret Drives | No | None | Robert Gaines |  | Root Cause - Software MACE Error | MACE Error
#JTC00000131 | Solved | CAT 1 | Chris Johnson | 2 ASOS | 12 | 2018-01-05 04:29:35 | 2018-01-05 04:29:35 | None | System not connecting to startup script | No | None | Chris Johnson | 2019-03-26 17:07:34 | Undefined | None
#JTC00000141 | Solved | CAT 1 | Chris Johnson | 2 ASOS | 12 | 2018-01-17 19:46:21 | 2018-01-17 19:46:21 | None | Nessus Server stopped during patch update process | No | None | Chris Johnson | 2019-03-26 17:07:55 | Undefined | None
#JTC00000156 | Solved | CAT 1 | Chris Johnson | 2 ASOS | 12 | 2018-02-01 15:57:20 | 2018-02-01 15:57:20 | None | NAS timing has drifted from IOS bootup | No | None | Chris Johnson | 2019-03-26 17:08:28 | Undefined | None
#JTC00000654 | Hold | CAT 2 | Skip Hamilton | 2 ASOS | 12 | 2018-11-20 13:54:53 | 2018-11-20 13:54:53 | None | Temporary canvas replacement screen requires replacement with high-contrast screen. | No | None | Skip Hamilton |  | Root Cause - Visual Screen Damaged | Screen Damaged
#JTC00000753 | Solved | CAT 2 | Robert Gaines | 2 ASOS | 12 | 2019-01-08 09:48:53 | 2019-01-08 09:48:53 | None | Issue with VDL pod unresponsive/locking up from IOS PC | No | None | Robert Gaines | 2019-03-26 17:30:24 | Undefined | None
#JTC00000848 | Solved | CAT 3 | Skip Hamilton | 2 ASOS | 12 | 2019-01-30 11:35:39 | 2019-01-30 11:35:39 | None | Patch not installing | No | None | Skip Hamilton | 2019-03-26 17:33:47 | Undefined | None
#JTC00000859 | Solved | CAT 3 | Skip Hamilton | 2 ASOS | 12 | 2019-01-31 14:58:48 | 2019-01-31 14:58:48 | None | Vilseck location patch assistance (UNCLASSIFIED) | No | None | Skip Hamilton | 2019-03-26 17:34:10 | Undefined | None
#JTC00000860 | Solved | CAT 3 | Skip Hamilton | 2 ASOS | 12 | 2019-01-31 14:58:51 | 2019-01-31 14:58:51 | Web form | Vilseck Jan 2019 Patch Scan | No | Operator needed to re-run patch on EME-Server and rescan | Skip Hamilton | 2019-03-28 00:54:38 | Root Cause - Other Other - See Comments | Other - See Comments
#JTC00000861 | Solved | CAT 2 | Kyle Zamudio | 2 ASOS | 12 | 2019-01-31 15:39:03 | 2019-01-31 15:39:03 | None | VRSG keeps crashing on the Role Player | No | None | Kyle Zamudio | 2019-03-26 17:34:14 | Undefined | None
#JTC00000862 | Hold | CAT 2 | Kyle Zamudio | 2 ASOS | 12 | 2019-01-31 15:45:53 | 2019-01-31 15:45:53 | None | Viewpoint attachment in dome jumps from one entitiy to another | No | None | Kyle Zamudio |  | Root Cause - Software VRSG Error | VRSG Error
#JTC00000863 | Solved | CAT 2 | Kyle Zamudio | 2 ASOS | 12 | 2019-01-31 16:05:05 | 2019-01-31 16:05:05 | None | Odd issues (in MACE) related to Discover in the EME | No | None | Kyle Zamudio | 2019-03-26 17:34:19 | Undefined | None
#JTC00000933 | Solved | CAT 3 | Steve Dumont | 2 ASOS | 12 | 2019-02-26 15:29:48 | 2019-02-26 15:29:48 | None | Inquiry Regarding HF Updates | No | None | Steve Dumont | 2019-03-26 17:36:49 | Undefined | None
#JTC00000936 | Solved | CAT 3 | Steve Dumont | 2 ASOS | 12 | 2019-02-26 18:20:27 | 2019-02-26 18:20:27 | None | Vilseck calling about HF application | No | None | Steve Dumont | 2019-03-26 17:36:56 | Undefined | None
#JTC00000948 | Solved | CAT 3 | Steve Dumont | 2 ASOS | 12 | 2019-02-27 16:11:02 | 2019-02-27 16:11:02 | None | Voicemail from: A. Michael Samborski | No | None | Steve Dumont | 2019-03-27 14:48:33 | Root Cause - Other Other - See Comments | Other - See Comments
#JTC00000949 | Pending | CAT 3 | Steve Dumont | 2 ASOS | 12 | 2019-02-27 16:14:57 | 2019-02-27 16:14:57 | None | Issues with Sound/ASTi Post UG2/HF | No | None | Steve Dumont |  | Root Cause - Software ASTi Error | ASTi Error
#JTC00000953 | Solved | CAT 1 | Robert Gaines | 2 ASOS | 12 | 2019-02-28 13:49:31 | 2019-02-28 13:49:31 | None | JTC TRS not acting as it should after 1.2.9 install | No | The client concurs with the decision to close the ticket and has agreed to submit additional tickets if the solutions implemented today do not stick. | Robert Gaines | 2019-03-27 14:30:11 | Root Cause - Other Operator Error | Operator Error
#JTC00000540 | Open | CAT 2 | Skip Hamilton | 12 CTS | 13 | 2018-09-12 21:57:01 | 2018-09-12 21:57:01 | None | Re: IG 8 surround broken / bad display port | No | None | Skip Hamilton |  | Root Cause - Visual DisplayPort Cable Failure | DisplayPort Cable Failure
#JTC00000755 | Solved | CAT 2 | Skip Hamilton | 12 CTS | 13 | 2019-01-08 18:06:01 | 2019-01-08 18:06:01 | None | Project 8 not displaying an image | No | None | Skip Hamilton | 2019-03-26 17:30:31 | Undefined | None
#JTC00000756 | Solved | CAT 2 | Skip Hamilton | 12 CTS | 13 | 2019-01-08 18:32:17 | 2019-01-08 18:32:17 | None | Projector 8 not displaying image | No | None | Skip Hamilton | 2019-03-26 17:30:33 | Undefined | None
#JTC00000786 | Solved | CAT 2 | Robert Gaines | 12 CTS | 13 | 2019-01-16 19:25:11 | 2019-01-16 19:25:11 | None | Voicemail from: Caller +1 (916) 769-0757 | No | None | Robert Gaines | 2019-03-26 17:31:36 | Undefined | None
#JTC00000147 | Solved | CAT 2 | Chris Johnson | 20 ASOS, Det 1 | 14 | 2018-01-26 18:07:04 | 2018-01-26 18:07:04 | None | Small Hole in Screen | No | None | Chris Johnson | 2019-03-26 17:08:09 | Undefined | None
#JTC00000190 | Solved | CAT 3 | Chris Johnson | 20 ASOS, Det 1 | 14 | 2018-02-20 20:35:51 | 2018-02-20 20:35:51 | None | Nessus Scan Results - Unclass | No | None | Chris Johnson | 2019-03-26 17:09:42 | Undefined | None
#JTC00000757 | Solved | CAT 3 | Skip Hamilton | 20 ASOS, Det 1 | 14 | 2019-01-08 18:34:40 | 2019-01-08 18:34:40 | None | Nessus Scans | No | None | Skip Hamilton | 2019-03-26 17:30:35 | Undefined | None
#JTC00000858 | Solved | CAT 3 | Skip Hamilton | 20 ASOS, Det 1 | 14 | 2019-01-31 14:58:45 | 2019-01-31 14:58:45 | None | Site doesn't have ASTi drive keys, can't complete ASTi upgrade. | No | None | Skip Hamilton | 2019-03-26 19:48:58 | Undefined | None
#JTC00000931 | Solved | CAT 2 | Skip Hamilton | 20 ASOS, Det 1 | 14 | 2019-02-25 20:30:14 | 2019-02-25 20:30:14 | None | Asti Drive Enclosure screws are stripped and need a replacement sent in order to mount the upgrade SSD | No | None | Skip Hamilton | 2019-03-26 17:36:45 | Undefined | None
#JTC00000937 | Pending | CAT 2 | Skip Hamilton | 20 ASOS, Det 1 | 14 | 2019-02-26 18:42:08 | 2019-02-26 18:42:08 | Mail | Ranger 47 2 Inoperable | No | Ranger 47 Display Issues | Skip Hamilton |  | Root Cause - Other Other - See Comments | Other - See Comments
#JTC00000938 | Solved | CAT 2 | Robert Gaines | 20 ASOS, Det 1 | 14 | 2019-02-26 18:44:12 | 2019-02-26 18:44:12 | None | Ranger 47 Viewpoint Underground | No | None | Robert Gaines | 2019-03-26 17:37:00 | Undefined | None
#JTC00000939 | Solved | CAT 2 | Skip Hamilton | 20 ASOS, Det 1 | 14 | 2019-02-26 18:45:35 | 2019-02-26 18:45:35 | None | Voisus unable to adjust mic and headset volumes | No | None | Skip Hamilton | 2019-03-26 17:37:02 | Undefined | None
#JTC00000940 | Solved | CAT 2 | Skip Hamilton | 20 ASOS, Det 1 | 14 | 2019-02-26 18:48:06 | 2019-02-26 18:48:06 | None | ASTI Hard drive screw stripped | No | None | Skip Hamilton | 2019-03-26 17:37:05 | Undefined | None
#JTC00000941 | Solved | CAT 3 | Skip Hamilton | 20 ASOS, Det 1 | 14 | 2019-02-26 18:54:21 | 2019-02-26 18:54:21 | None | VRSG License Expiring (60 Days) | No | None | Skip Hamilton | 2019-03-26 17:37:07 | Undefined | None
#JTC00000944 | Solved | CAT 2 | Robert Gaines | 20 ASOS, Det 1 | 14 | 2019-02-26 22:25:13 | 2019-02-26 22:25:13 | None | Bad Cable - Headset Student 1 | No | None | Robert Gaines | 2019-03-26 17:37:13 | Undefined | None
#JTC00000945 | Solved | CAT 2 | Skip Hamilton | 20 ASOS, Det 1 | 14 | 2019-02-27 14:35:17 | 2019-02-27 14:35:17 | Phone call inbound | ASHLEY Audio not working | No | Site didn't have ASTi 7 installed | Skip Hamilton | 2019-03-27 15:01:08 | Root Cause - Software ASTi Error | ASTi Error
#JTC00000946 | Solved | CAT 2 | Skip Hamilton | 20 ASOS, Det 1 | 14 | 2019-02-27 14:37:01 | 2019-02-27 14:37:01 | None | MVP VRSG Random Shutdown | No | VRSG Crash 1.2.7 MVP | Skip Hamilton | 2019-03-27 14:51:15 | Root Cause - Software VRSG Error | VRSG Error
#JTC00000951 | Solved | CAT 2 | Skip Hamilton | 20 ASOS, Det 1 | 14 | 2019-02-27 20:22:39 | 2019-02-27 20:22:39 | None | ASTI License Won't Update | No | None | Skip Hamilton | 2019-03-27 14:43:28 | Root Cause - Other Other - See Comments | Other - See Comments
#JTC00000128 | Solved | CAT 1 | Chris Johnson | 6 CTS | 17 | 2018-01-02 20:43:06 | 2018-01-02 20:43:06 | None | 3 holes in screen of Dome #2 (Sys #16) | No | None | Chris Johnson | 2019-03-26 17:07:28 | Undefined | None
#JTC00000129 | Solved | CAT 1 | Chris Johnson | 6 CTS | 17 | 2018-01-03 20:30:34 | 2018-01-03 20:30:34 | None | PEQ/IR pointer on both M4s inop (do not fire or track), IZLID inop (does not fire or track) | No | None | Chris Johnson | 2019-03-26 17:07:30 | Undefined | None
#JTC00000132 | Solved | CAT 1 | Chris Johnson | 6 CTS | 17 | 2018-01-06 03:06:45 | 2018-01-06 03:06:45 | None | Logitech Joystick not working on IOS computer | No | None | Chris Johnson | 2019-03-26 17:07:36 | Undefined | None
#JTC00000139 | Solved | CAT 1 | Chris Johnson | 6 CTS | 17 | 2018-01-16 20:13:32 | 2018-01-16 20:13:32 | None | Projected images in the entire middle row of the screen with the exception of the far left middle image, | No | None | Chris Johnson | 2019-03-26 17:07:51 | Undefined | None
#JTC00000144 | Solved | CAT 1 | Chris Johnson | 6 CTS | 17 | 2018-01-25 18:50:54 | 2018-01-25 18:50:54 | None | Weapon Sensor view does not stay locked on assigned target | No | None | Chris Johnson | 2019-03-26 17:08:03 | Undefined | None
#JTC00000151 | Solved | CAT 1 | Chris Johnson | 6 CTS | 17 | 2018-01-29 19:02:27 | 2018-01-29 19:02:27 | None | Project #6 shutting off. | No | None | Chris Johnson | 2019-03-26 17:08:17 | Undefined | None
#JTC00000160 | Solved | CAT 2 | Chris Johnson | 6 CTS | 17 | 2018-02-05 22:52:56 | 2018-02-05 22:52:56 | None | MVP Ranger views / Stelth Observer view / JTAC view does not expand to full screen when tapped once on touchscreen | No | None | Chris Johnson | 2019-03-26 17:08:38 | Undefined | None
#JTC00000167 | Solved | CAT 2 | Devin Hoeckel | 6 CTS | 17 | 2018-02-08 18:26:19 | 2018-02-08 18:26:19 | None | Asti radios / Comm Panels at MPV and IOS station no transmit, constant transmit or causing monitors to black out | No | None | Devin Hoeckel | 2019-03-26 17:08:53 | Undefined | None
#JTC00000168 | Hold | CAT 2 | Skip Hamilton | 6 CTS | 17 | 2018-02-08 20:30:12 | 2018-02-08 20:30:12 | None | Projector #4 image (bottom right of screen blacks out for a couple seconds or flickers and goes to a yellow/green tint over the image every 5-10 minutes | No | None | Skip Hamilton |  | Root Cause - Visual DisplayPort Cable Failure | DisplayPort Cable Failure
#JTC00000169 | Solved | CAT 2 | Chris Johnson | 6 CTS | 17 | 2018-02-08 20:40:21 | 2018-02-08 20:40:21 | None | In-dome devices (PEQS/IZLID/Rangers) do not fire and/or track with movement in Systems 15,16 17 | No | None | Chris Johnson | 2019-03-26 17:08:57 | Undefined | None
#JTC00000171 | Hold | CAT 2 | Skip Hamilton | 6 CTS | 17 | 2018-02-08 21:32:28 | 2018-02-08 21:32:28 | None | Projector #10 image blacks out routinely for 1-3 seconds and then comes back | No | None | Skip Hamilton |  | Root Cause - Visual DisplayPort Cable Failure | DisplayPort Cable Failure
#JTC00000187 | Solved | CAT 1 | Devin Hoeckel | 6 CTS | 17 | 2018-02-15 16:02:57 | 2018-02-15 16:02:57 | None | Student 1 comms shut down by themselves | No | None | Devin Hoeckel | 2019-03-26 17:09:36 | Undefined | None
#JTC00000192 | Solved | CAT 2 | Devin Hoeckel | 6 CTS | 17 | 2018-02-21 15:31:03 | 2018-02-21 15:31:03 | None | Projector #9 displaying white vertical lines through image | No | None | Devin Hoeckel | 2019-03-26 17:09:47 | Undefined | None
#JTC00000193 | Solved | CAT 2 | Chris Johnson | 6 CTS | 17 | 2018-02-21 16:47:46 | 2018-02-21 16:47:46 | None | Discover shutting down by itself during mission | No | None | Chris Johnson | 2019-03-26 17:09:49 | Undefined | None
#JTC00000195 | Solved | CAT 1 | Devin Hoeckel | 6 CTS | 17 | 2018-02-22 16:22:51 | 2018-02-22 16:22:51 | None | Projector 10 image does not realign position from the jigsaw pattern when you go into VRSG Remote / RESET. | No | None | Devin Hoeckel | 2019-03-26 17:09:53 | Undefined | None
#JTC00000625 | Pending | CAT 2 | Skip Hamilton | 6 CTS | 17 | 2018-11-07 17:10:51 | 2018-11-07 17:10:51 | None | VRSG on MVP shutting down by itself during mission | No | None | Skip Hamilton |  | Root Cause - Software VRSG Error | VRSG Error
#JTC00000626 | Pending | CAT 2 | Skip Hamilton | 6 CTS | 17 | 2018-11-07 17:11:36 | 2018-11-07 17:11:36 | None | VRSG on MVP shutting down by itself during mission | No | None | Skip Hamilton |  | Root Cause - Software VRSG Error | VRSG Error
#JTC00000740 | Hold | CAT 2 | Robert Gaines | 6 CTS | 17 | 2018-12-21 20:59:26 | 2018-12-21 20:59:26 | None | IG 1 VRSG starts up in window Mode on all 3 devices | No | None | Robert Gaines |  | Root Cause - Software VRSG Error | VRSG Error
#JTC00000751 | Solved | CAT 2 | Robert Gaines | 6 CTS | 17 | 2019-01-04 00:28:46 | 2019-01-04 00:28:46 | None | Cultural File contents are not displayed within VRSG | No | None | Robert Gaines | 2019-03-26 17:30:20 | Undefined | None
#JTC00000762 | Solved | CAT 2 | Robert Gaines | 6 CTS | 17 | 2019-01-10 18:30:05 | 2019-01-10 18:30:05 | None | IG Resolution issues | No | None | Robert Gaines | 2019-03-26 17:30:46 | Undefined | None
#JTC00000763 | Solved | CAT 2 | Robert Gaines | 6 CTS | 17 | 2019-01-10 19:11:39 | 2019-01-10 19:11:39 | None | Voicemail from: Tim Toole | No | None | Robert Gaines | 2019-03-26 17:30:48 | Undefined | None
#JTC00000772 | Solved | CAT 3 | Robert Gaines | 6 CTS | 17 | 2019-01-14 17:14:13 | 2019-01-14 17:14:13 | None | Phone Call from: Tim Toole | No | None | Robert Gaines | 2019-03-26 17:31:07 | Undefined | None
#JTC00000775 | Hold | CAT 2 | Robert Gaines | 6 CTS | 17 | 2019-01-14 22:27:04 | 2019-01-14 22:27:04 | None | Projector #9 strobing yellow tint on entire image | No | None | Robert Gaines |  | Root Cause - Visual Projector Failure (BARCO) | Projector Failure (BARCO)
#JTC00000785 | Solved | CAT 2 | Devin Hoeckel | 6 CTS | 17 | 2019-01-16 19:09:47 | 2019-01-16 19:09:47 | None | Student Tablets transmitting but nothing heard | No | None | Devin Hoeckel | 2019-03-26 17:31:34 | Undefined | None
#JTC00000793 | Pending | CAT 2 | Robert Gaines | 6 CTS | 17 | 2019-01-18 19:05:31 | 2019-01-18 19:05:31 | None | RPS Targeting Pod Display Issue & MVP TGP Accuracy | No | Targeting Pod error | Robert Gaines |  | Root Cause - Software DIScover Error | DIScover Error
#JTC00000794 | Solved | CAT 2 | Robert Gaines | 6 CTS | 17 | 2019-01-22 15:15:52 | 2019-01-22 15:15:52 | None | Resolution Settings Purged | No | None | Robert Gaines | 2019-03-26 17:31:54 | Undefined | None
#JTC00000795 | Solved | CAT 2 | Robert Gaines | 6 CTS | 17 | 2019-01-22 16:35:31 | 2019-01-22 16:35:31 | None | Voicemail from: Tim Toole | No | None | Robert Gaines | 2019-03-26 17:31:56 | Undefined | None
#JTC00000798 | Solved | CAT 2 | Robert Gaines | 6 CTS | 17 | 2019-01-22 23:35:33 | 2019-01-22 23:35:33 | None | Voicemail from: Tim Toole | No | None | Robert Gaines | 2019-03-26 17:32:02 | Undefined | None
#JTC00000801 | Solved | CAT 2 | Robert Gaines | 6 CTS | 17 | 2019-01-23 15:35:10 | 2019-01-23 15:35:10 | None | Voicemail from: Tim Toole | No | None | Robert Gaines | 2019-03-26 17:32:08 | Undefined | None
#JTC00000802 | Solved | CAT 2 | Robert Gaines | 6 CTS | 17 | 2019-01-23 15:50:56 | 2019-01-23 15:50:56 | None | Projector #3 light source failure | No | None | Robert Gaines | 2019-03-26 17:32:10 | Undefined | None
#JTC00000812 | Solved | CAT 2 | Skip Hamilton | 6 CTS | 17 | 2019-01-24 18:15:19 | 2019-01-24 18:15:19 | None | DOC closing by itself every 10-15 minutes | No | None | Skip Hamilton | 2019-03-26 17:32:30 | Undefined | None
#JTC00000814 | Pending | CAT 2 | Skip Hamilton | 6 CTS | 17 | 2019-01-24 18:26:35 | 2019-01-24 18:26:35 | None | Projector # 7 goes to stand by mode every 10 minutes, image turns black | No | None | Skip Hamilton |  | Root Cause - Visual Projector Failure (BARCO) | Projector Failure (BARCO)
#JTC00000815 | Open | CAT 2 | Robert Gaines | 6 CTS | 17 | 2019-01-24 18:28:07 | 2019-01-24 18:28:07 | None | Pilot Station MACE shuts down by itself during mission | No | None | Robert Gaines |  | Root Cause - Software MACE Error | MACE Error
#JTC00000816 | Hold | CAT 2 | Robert Gaines | 6 CTS | 17 | 2019-01-24 18:29:24 | 2019-01-24 18:29:24 | None | Pilot Station VRSG closes by itself during missions | No | None | Robert Gaines |  | Root Cause - Software VRSG Error | VRSG Error
#JTC00000817 | Solved | CAT 1 | Skip Hamilton | 6 CTS | 17 | 2019-01-24 18:31:28 | 2019-01-24 18:31:28 | None | Projector #3 does not project image. | No | None | Skip Hamilton | 2019-03-26 17:32:42 | Undefined | None
#JTC00000818 | Solved | CAT 2 | Robert Gaines | 6 CTS | 17 | 2019-01-24 21:46:27 | 2019-01-24 21:46:27 | None | Voicemail from: Tim Toole | No | None | Robert Gaines | 2019-03-26 17:32:44 | Undefined | None
#JTC00000912 | Pending | CAT 2 | Skip Hamilton | 6 CTS | 17 | 2019-02-13 22:05:17 | 2019-02-13 22:05:17 | Web form | Student 1, M41 firing by itself rapid fire | No | None | Skip Hamilton |  | Root Cause - Hardware M-4 | M-4
#JTC00000971 | Pending | CAT 3 | Robert Gaines | 6 CTS | 17 | 2019-03-05 19:36:30 | 2019-03-05 19:36:30 | None | Systems 15, 16, 17 have old AAJTS display cables | No | None | Robert Gaines |  | Root Cause - Visual DisplayPort Cable Failure | DisplayPort Cable Failure
#JTC00000150 | Solved | CAT 1 | Chris Johnson | 5 ASOS | 18 | 2018-01-29 15:57:42 | 2018-01-29 15:57:42 | None | Dome VRSG not starting | No | None | Chris Johnson | 2019-03-26 17:08:16 | Undefined | None
#JTC00000152 | Solved | CAT 1 | Chris Johnson | 5 ASOS | 18 | 2018-01-29 21:58:04 | 2018-01-29 21:58:04 | None | Ranger 47 view and ranging | No | None | Chris Johnson | 2019-03-26 17:08:20 | Undefined | None
#JTC00000154 | Solved | CAT 1 | Chris Johnson | 5 ASOS | 18 | 2018-01-31 16:20:52 | 2018-01-31 16:20:52 | None | Asti web interface access denied. | No | None | Chris Johnson | 2019-03-26 17:08:24 | Undefined | None
#JTC00000155 | Solved | CAT 1 | Chris Johnson | 5 ASOS | 18 | 2018-01-31 21:03:54 | 2018-01-31 21:03:54 | None | Tracking system is not working properly | No | None | Chris Johnson | 2019-03-26 17:08:26 | Undefined | None
#JTC00000157 | Solved | CAT 2 | Chris Johnson | 5 ASOS | 18 | 2018-02-01 16:57:26 | 2018-02-01 16:57:26 | None | DORT not working | No | None | Chris Johnson | 2019-03-26 17:08:30 | Undefined | None
#JTC00000158 | Solved | CAT 1 | Chris Johnson | 5 ASOS | 18 | 2018-02-05 15:37:28 | 2018-02-05 15:37:28 | None | Nessus plugins don't appear to be updating | No | None | Chris Johnson | 2019-03-26 17:08:33 | Undefined | None
#JTC00000159 | Solved | CAT 2 | Chris Johnson | 5 ASOS | 18 | 2018-02-05 19:15:13 | 2018-02-05 19:15:13 | None | DOC panel keep disappear after open | No | None | Chris Johnson | 2019-03-26 17:08:35 | Undefined | None
#JTC00000161 | Solved | CAT 1 | Chris Johnson | 5 ASOS | 18 | 2018-02-07 18:53:25 | 2018-02-07 18:53:25 | None | Targeting pod wouldn't look at ground | No | None | Chris Johnson | 2019-03-26 17:08:40 | Undefined | None
#JTC00000162 | Solved | CAT 1 | Chris Johnson | 5 ASOS | 18 | 2018-02-07 19:04:24 | 2018-02-07 19:04:24 | None | Ranger 47 locked up and IZLID wouldn't work | No | None | Chris Johnson | 2019-03-26 17:08:42 | Undefined | None
#JTC00000163 | Solved | CAT 1 | Chris Johnson | 5 ASOS | 18 | 2018-02-07 19:09:01 | 2018-02-07 19:09:01 | None | DOME VRSGs not displaying properly | No | None | Chris Johnson | 2019-03-26 17:08:44 | Undefined | None
#JTC00000164 | Solved | CAT 1 | Chris Johnson | 5 ASOS | 18 | 2018-02-08 00:45:04 | 2018-02-08 00:45:04 | None | Targeting Pod Won't look at the Ground | No | None | Chris Johnson | 2019-03-26 17:08:46 | Undefined | None
#JTC00000166 | Solved | CAT 2 | Devin Hoeckel | 5 ASOS | 18 | 2018-02-08 17:58:19 | 2018-02-08 17:58:19 | None | IOS Comm pannel | No | None | Devin Hoeckel | 2019-03-26 17:08:51 | Undefined | None
#JTC00000172 | Solved | CAT 2 | Chris Johnson | 5 ASOS | 18 | 2018-02-09 00:51:45 | 2018-02-09 00:51:45 | None | Multiple target option not working properly | No | None | Chris Johnson | 2019-03-26 17:09:03 | Undefined | None
#JTC00000173 | Solved | CAT 1 | Chris Johnson | 5 ASOS | 18 | 2018-02-09 16:17:45 | 2018-02-09 16:17:45 | None | Discover panel disappear | No | None | Chris Johnson | 2019-03-26 17:09:05 | Undefined | None
#JTC00000174 | Solved | CAT 2 | Chris Johnson | 5 ASOS | 18 | 2018-02-09 21:31:51 | 2018-02-09 21:31:51 | None | Targeting pod locked above horizon won't look at ground | No | None | Chris Johnson | 2019-03-26 17:09:08 | Undefined | None
#JTC00000175 | Solved | CAT 3 | Chris Johnson | 5 ASOS | 18 | 2018-02-09 21:35:23 | 2018-02-09 21:35:23 | None | Need Add on account | No | None | Chris Johnson | 2019-03-26 17:09:10 | Undefined | None
#JTC00000176 | Solved | CAT 2 | Chris Johnson | 5 ASOS | 18 | 2018-02-09 21:56:15 | 2018-02-09 21:56:15 | None | Helos on 9-line not firing on correct target OR firing short | No | None | Chris Johnson | 2019-03-26 17:09:12 | Undefined | None
#JTC00000184 | Solved | CAT 2 | Chris Johnson | 5 ASOS | 18 | 2018-02-14 00:29:36 | 2018-02-14 00:29:36 | None | MVP and Comm crash | No | None | Chris Johnson | 2019-03-26 17:09:30 | Undefined | None
#JTC00000185 | Solved | CAT 2 | Chris Johnson | 5 ASOS | 18 | 2018-02-14 16:55:48 | 2018-02-14 16:55:48 | None | MVP display an error message "NO ROLE SET" | No | None | Chris Johnson | 2019-03-26 17:09:32 | Undefined | None
#JTC00000188 | Solved | CAT 2 | Chris Johnson | 5 ASOS | 18 | 2018-02-15 17:33:31 | 2018-02-15 17:33:31 | None | Ranger 47 locked up - not tracking | No | None | Chris Johnson | 2019-03-26 17:09:38 | Undefined | None
#JTC00000189 | Solved | CAT 2 | Chris Johnson | 5 ASOS | 18 | 2018-02-15 17:43:24 | 2018-02-15 17:43:24 | None | Ranger 47 and IZLID buttons not working. | No | None | Chris Johnson | 2019-03-26 17:09:40 | Undefined | None
#JTC00000196 | Solved | CAT 2 | Chris Johnson | 5 ASOS | 18 | 2018-02-23 07:09:33 | 2018-02-23 07:09:33 | None | Projectors blink in and out | No | None | Chris Johnson | 2019-03-26 17:09:55 | Undefined | None
#JTC00000261 | Pending | CAT 3 | Robert Gaines | 5 ASOS | 18 | 2018-03-27 17:26:43 | 2018-03-27 17:26:43 | None | MACE sound scripting does not work properly with ASTi radios | No | None | Robert Gaines |  | Root Cause - Software MACE Error | MACE Error
#JTC00000605 | Hold | CAT 2 | Robert Gaines | 5 ASOS | 18 | 2018-10-26 21:37:36 | 2018-10-26 21:37:36 | None | M4 #1 continuously fires in MACE | No | None | Robert Gaines |  | Root Cause - Hardware M-4 | M-4
#JTC00000650 | Pending | CAT 2 | Robert Gaines | 5 ASOS | 18 | 2018-11-19 16:33:42 | 2018-11-19 16:33:42 | None | VRSG Remote fails to consistently update the terrain search path | No | None | Robert Gaines |  | Root Cause - Software DOC Error | DOC Error
#JTC00000671 | Pending | CAT 2 | Robert Gaines | 5 ASOS | 18 | 2018-11-27 23:25:58 | 2018-11-27 23:25:58 | None | Q-Fires Rover Crashing | No | None | Robert Gaines |  | Root Cause - Software Q-Fires ROVER Error | Q-Fires ROVER Error
#JTC00000687 | Hold | CAT 2 | Robert Gaines | 5 ASOS | 18 | 2018-12-05 15:43:54 | 2018-12-05 15:43:54 | None | MVP VRSG Crash | No | None | Robert Gaines |  | Root Cause - Software VRSG Error | VRSG Error
#JTC00000717 | Hold | CAT 2 | Robert Gaines | 5 ASOS | 18 | 2018-12-14 15:51:59 | 2018-12-14 15:51:59 | None | Grids unreadable on student and RPS ROVER displays | No | Targeting Pod Plugin | Robert Gaines |  | Root Cause - Software DIScover Error | DIScover Error
#JTC00000759 | Solved | CAT 2 | Robert Gaines | 5 ASOS | 18 | 2019-01-09 23:11:11 | 2019-01-09 23:11:11 | None | Supplementary server system is non-functional | No | None | Robert Gaines | 2019-03-26 17:30:40 | Undefined | None
#JTC00000771 | Solved | CAT 2 | Robert Gaines | 5 ASOS | 18 | 2019-01-14 16:37:25 | 2019-01-14 16:37:25 | None | DOC failed on start-up, EME-Display didn't recognize Ranger 47, Anchors and Tabs had USB Port Failure | No | None | Robert Gaines | 2019-03-26 17:31:05 | Undefined | None
#JTC00000773 | Solved | CAT 2 | Robert Gaines | 5 ASOS | 18 | 2019-01-14 17:38:36 | 2019-01-14 17:38:36 | None | Phone Call from: Dave Devine | No | None | Robert Gaines | 2019-03-26 17:31:09 | Undefined | None
#JTC00000774 | Solved | CAT 2 | Skip Hamilton | 5 ASOS | 18 | 2019-01-14 20:19:09 | 2019-01-14 20:19:09 | None | Voicemail from: Dave Devine | No | None | Skip Hamilton | 2019-03-26 17:31:11 | Undefined | None
#JTC00000781 | Solved | CAT 2 | Robert Gaines | 5 ASOS | 18 | 2019-01-15 16:01:04 | 2019-01-15 16:01:04 | None | Ranger 47 does not roof clamp | No | None | Robert Gaines | 2019-03-26 17:31:25 | Undefined | None
#JTC00000792 | Solved | CAT 2 | Robert Gaines | 5 ASOS | 18 | 2019-01-17 19:47:28 | 2019-01-17 19:47:28 | None | IG-04 will not yield a working VNC Session | No | None | Robert Gaines | 2019-03-26 17:31:50 | Undefined | None
#JTC00000797 | Solved | CAT 2 | Robert Gaines | 5 ASOS | 18 | 2019-01-22 18:10:49 | 2019-01-22 18:10:49 | None | IZLID fails to project a beam | No | None | Robert Gaines | 2019-03-26 17:32:00 | Undefined | None
#JTC00000799 | Solved | CAT 3 | Robert Gaines | 5 ASOS | 18 | 2019-01-23 00:33:44 | 2019-01-23 00:33:44 | None | UPS #1 showing "Replace Battery" | No | None | Robert Gaines | 2019-03-26 17:32:04 | Undefined | None
#JTC00000803 | Solved | CAT 2 | Robert Gaines | 5 ASOS | 18 | 2019-01-23 17:33:34 | 2019-01-23 17:33:34 | None | IG-04 Drops resolution settings, prevents access via VNC, and fails to start VRSG | No | None | Robert Gaines | 2019-03-26 17:32:12 | Undefined | None
#JTC00000806 | Solved | CAT 2 | Robert Gaines | 5 ASOS | 18 | 2019-01-24 05:00:42 | 2019-01-24 05:00:42 | None | Headset not transmitting | No | None | Robert Gaines | 2019-03-26 17:32:18 | Undefined | None
#JTC00000819 | Solved | CAT 2 | Robert Gaines | 5 ASOS | 18 | 2019-01-25 00:12:26 | 2019-01-25 00:12:26 | None | Speaker system does not generate sound after the most recent ASTi update | No | None | Robert Gaines | 2019-03-26 17:32:46 | Undefined | None
#JTC00000820 | Solved | CAT 3 | Robert Gaines | 5 ASOS | 18 | 2019-01-25 00:16:10 | 2019-01-25 00:16:10 | None | DOC Fails to shut down EME and IOS | No | None | Robert Gaines | 2019-03-26 17:32:48 | Undefined | None
#JTC00000853 | Solved | CAT 3 | Robert Gaines | 5 ASOS | 18 | 2019-01-30 22:25:07 | 2019-01-30 22:25:07 | None | crates | No | None | Robert Gaines | 2019-03-26 17:33:57 | Undefined | None
#JTC00000866 | Solved | CAT 2 | Devin Hoeckel | 5 ASOS | 18 | 2019-01-31 16:55:02 | 2019-01-31 16:55:02 | None | Tags and Anchors weren't showing up in DIScover | No | None | Devin Hoeckel | 2019-03-26 17:34:25 | Undefined | None
#JTC00000869 | Solved | CAT 3 | Robert Gaines | 5 ASOS | 18 | 2019-02-01 00:44:00 | 2019-02-01 00:44:00 | None | Sidetone in headset | No | None | Robert Gaines | 2019-03-26 17:34:32 | Undefined | None
#JTC00000873 | Hold | CAT 3 | Devin Hoeckel | 5 ASOS | 18 | 2019-02-01 23:51:12 | 2019-02-01 23:51:12 | None | MACE maintenance expired | No | None | Devin Hoeckel |  | Root Cause - Software MACE Error | MACE Error
#JTC00000889 | Solved | CAT 3 | Robert Gaines | 5 ASOS | 18 | 2019-02-06 21:09:57 | 2019-02-06 21:09:57 | None | Hotfix Installation Sequence Inquiry | No | None | Robert Gaines | 2019-03-26 17:35:13 | Undefined | None
#JTC00000890 | Solved | CAT 3 | Robert Gaines | 5 ASOS | 18 | 2019-02-06 21:49:10 | 2019-02-06 21:49:10 | None | Hotfix | No | None | Robert Gaines | 2019-03-26 17:35:15 | Undefined | None
#JTC00000893 | Solved | CAT 2 | Robert Gaines | 5 ASOS | 18 | 2019-02-07 18:02:29 | 2019-02-07 18:02:29 | None | PSC Headset not transmiting | No | None | Robert Gaines | 2019-03-26 17:35:21 | Undefined | None
#JTC00000914 | Solved | CAT 2 | Robert Gaines | 5 ASOS | 18 | 2019-02-20 15:41:27 | 2019-02-20 15:41:27 | None | EME Server crashed or hung during startup | No | None | Robert Gaines | 2019-03-26 17:36:05 | Undefined | None
#JTC00000924 | Solved | CAT 2 | Skip Hamilton | 5 ASOS | 18 | 2019-02-22 17:37:12 | 2019-02-22 17:37:12 | None | Nessus daemon issues | No | None | Skip Hamilton | 2019-03-26 17:36:28 | Undefined | None
#JTC00000932 | Solved | CAT 3 | Robert Gaines | 5 ASOS | 18 | 2019-02-25 23:05:56 | 2019-02-25 23:05:56 | None | New operator training | No | None | Robert Gaines | 2019-03-26 17:36:47 | Undefined | None
#JTC00000965 | Pending | CAT 2 | Robert Gaines | 5 ASOS | 18 | 2019-03-01 22:02:29 | 2019-03-01 22:02:29 | None | Sound levels | No | None | Robert Gaines |  | Root Cause - Software ASTi Error | ASTi Error
#JTC00000980 | Pending | CAT 3 | Robert Gaines | 5 ASOS | 18 | 2019-03-13 14:11:23 | 2019-03-13 14:11:23 | None | MACE Detonation Tool Sound - Faulty Sound Mapping | No | None | Robert Gaines |  | Root Cause - Software ASTi Error | ASTi Error
#JTC00000197 | Solved | CAT 1 | Chris Johnson | 23 STS | 19 | 2018-02-23 17:33:31 | 2018-02-23 17:33:31 | None | Trainer Broked | No | None | Chris Johnson | 2019-03-26 17:09:57 | Undefined | None
#JTC00000568 | Hold | CAT 2 | Robert Gaines | 23 STS | 19 | 2018-10-05 17:21:05 | 2018-10-05 17:21:05 | None | IG & Proj 4 having resolution issues and IOS is randoly booting up overnight after system shutdown | No | None | Robert Gaines |  | Root Cause - Visual Surround Error | Surround Error
#JTC00000831 | Solved | CAT 3 | Skip Hamilton | 23 STS | 19 | 2019-01-28 19:33:52 | 2019-01-28 19:33:52 | None | Needed clarification on where to install ASTi SSD for Upgrade 2 | No | None | Skip Hamilton | 2019-03-26 17:33:10 | Undefined | None
#JTC00000840 | Solved | CAT 3 | Skip Hamilton | 23 STS | 19 | 2019-01-29 18:53:51 | 2019-01-29 18:53:51 | None | Calling to track down an ASTi Hard Drive Key | No | None | Skip Hamilton | 2019-03-26 17:33:29 | Undefined | None
#JTC00000841 | Solved | CAT 3 | Skip Hamilton | 23 STS | 19 | 2019-01-29 18:58:35 | 2019-01-29 18:58:35 | None | Site needs an ASTi Hard Drive Key, misplaced original | No | None | Skip Hamilton | 2019-03-26 17:33:31 | Undefined | None
#JTC00000847 | Solved | CAT 3 | Skip Hamilton | 23 STS | 19 | 2019-01-30 02:47:41 | 2019-01-30 02:47:41 | Voicemail | Dev 008 calling with questions about where to send Cyber scans | No | Site needed to know where to submit ACAS Scan results | Skip Hamilton | 2019-03-28 00:41:14 | Root Cause - Other Other - See Comments | Other - See Comments
#JTC00000875 | Solved | CAT 3 | Robert Gaines | 23 STS | 19 | 2019-02-04 15:05:34 | 2019-02-04 15:05:34 | Phone call inbound | IA update script yields "Illegal Path" error | No | Operator wasn't running GPO script with Admin credentails and had the incorrect file path | Robert Gaines | 2019-03-27 15:39:55 | Root Cause - Other Operator Error | Operator Error
#JTC00000888 | Solved | CAT 2 | Robert Gaines | 23 STS | 19 | 2019-02-06 20:59:58 | 2019-02-06 20:59:58 | None | Upgrade 2 - Installation Errors | No | None | Robert Gaines | 2019-03-26 17:35:10 | Undefined | None
#JTC00000929 | Solved | CAT 3 | Skip Hamilton | 23 STS | 19 | 2019-02-25 18:21:41 | 2019-02-25 18:21:41 | None | Ft Polk calling about ASTi Drive Replacement | No | None | Skip Hamilton | 2019-03-26 17:36:39 | Undefined | None
#JTC00000947 | Solved | CAT 3 | Skip Hamilton | 23 STS | 19 | 2019-02-27 15:54:43 | 2019-02-27 15:54:43 | None | Questions on Cyber Patches and Upgrade 2 | No | not the SIM operator or ISSO | Skip Hamilton | 2019-03-27 14:49:57 | Root Cause - Other Operator Error | Operator Error
#JTC00000952 | Solved | CAT 2 | Skip Hamilton | 23 STS | 19 | 2019-02-27 20:25:27 | 2019-02-27 20:25:27 | None | Ft Polk calling about ASTi License | No | Did not insert dongle for license | Skip Hamilton | 2019-03-27 14:42:13 | Root Cause - Software ASTi Error | ASTi Error
#JTC00000908 | Solved | CAT 3 | Steve Dumont | STTS | 20 | 2019-02-12 19:50:42 | 2019-02-12 19:50:42 | None | Voicemail from: Brian Hellard | No | None | Steve Dumont | 2019-03-26 17:35:53 | Undefined | None
#JTC00000975 | Hold | CAT 2 | Steve Dumont | STTS | 20 | 2019-03-07 16:38:28 | 2019-03-07 16:38:28 | Web form | Runaway M-4 Carbine #1; device fires autonomously--need a replacement and repairs on faulty device | No | Trigger pressure sensor is presumed to be faulty | Steve Dumont |  | Root Cause - Hardware M-4 | M-4
#JTC00000809 | Solved | CAT 1 | Robert Gaines | 13 ASOS | 21 | 2019-01-24 15:56:19 | 2019-01-24 15:56:19 | None | System will not start up and IG-2 is dead | No | None | Robert Gaines | 2019-03-26 17:32:24 | Undefined | None
#JTC00000811 | Solved | CAT 1 | Robert Gaines | 13 ASOS | 21 | 2019-01-24 17:00:32 | 2019-01-24 17:00:32 | None | Trying to work with Robert Gaines but email is rejecting. Keep getting undeliverable messages when sending to the help desk. | No | None | Robert Gaines | 2019-03-26 17:32:28 | Undefined | None
#JTC00000813 | Solved | CAT 3 | Robert Gaines | 13 ASOS | 21 | 2019-01-24 18:17:40 | 2019-01-24 18:17:40 | None | Windows boot manager comes up on EME-server at boot. | No | None | Robert Gaines | 2019-03-26 17:32:33 | Undefined | None
#JTC00000838 | Solved | CAT 1 | Skip Hamilton | 13 ASOS | 21 | 2019-01-29 15:19:12 | 2019-01-29 15:19:12 | None | projector #3 Inop | No | None | Skip Hamilton | 2019-03-26 17:33:25 | Undefined | None
#JTC00000876 | Solved | CAT 2 | Robert Gaines | 13 ASOS | 21 | 2019-02-04 15:19:31 | 2019-02-04 15:19:31 | None | IG-2 Faulty projector cable | No | None | Robert Gaines | 2019-03-26 17:34:46 | Undefined | None
#JTC00000913 | Solved | CAT 1 | Robert Gaines | 13 ASOS | 21 | 2019-02-19 21:25:20 | 2019-02-19 21:25:20 | None | IG-2 surround and operation | No | None | Robert Gaines | 2019-03-26 17:36:03 | Undefined | None
#JTC00000921 | Solved | CAT 2 | Robert Gaines | 13 ASOS | 21 | 2019-02-21 16:41:44 | 2019-02-21 16:41:44 | None | VDL not transmitting to Student 2 and Terrain not loading on RPC and MVP | No | None | Robert Gaines | 2019-03-26 17:36:21 | Undefined | None
#JTC00000926 | Pending | CAT 2 | Robert Gaines | 13 ASOS | 21 | 2019-02-22 21:02:25 | 2019-02-22 21:02:25 | None | Student Station won't pick up MVP ROVER feed | No | None | Robert Gaines |  | Root Cause - Software Q-Fires ROVER Error | Q-Fires ROVER Error
#JTC00000963 | Pending | CAT 3 | Devin Hoeckel | 13 ASOS | 21 | 2019-03-01 17:33:59 | 2019-03-01 17:33:59 | None | LED Tasklight has stopped working | No | None | Devin Hoeckel |  | Root Cause - Hardware Desk Light | Desk Light
#JTC00000993 | Pending | CAT 3 | Robert Gaines | 13 ASOS | 21 | 2019-03-18 15:37:56 | 2019-03-18 15:37:56 | None | DAT Switch exhibits abnormal behavior - failure possible | No | None | Robert Gaines |  | Undefined | None
#JTC00000804 | Solved | CAT 3 | Steve Dumont | 9 ASOS | 22 | 2019-01-23 18:21:57 | 2019-01-23 18:21:57 | None | Defective Audio Cable on Instructor Station & Gamepad Support Bracket that Connects to Tripod is broken--T-Nut is stripped; replacements needed | No | None | Steve Dumont | 2019-03-26 17:32:14 | Undefined | None
#JTC00000880 | Solved | CAT 2 | Kyle Zamudio | 9 ASOS | 22 | 2019-02-05 17:46:56 | 2019-02-05 17:46:56 | None | Mace and VRSG crashed on RP | No | None | Kyle Zamudio | 2019-03-26 17:34:54 | Undefined | None
#JTC00000884 | Solved | CAT 2 | Skip Hamilton | 9 ASOS | 22 | 2019-02-06 17:28:51 | 2019-02-06 17:28:51 | None | QFires Rover Crashed on Student 2 | No | None | Skip Hamilton | 2019-03-26 17:35:02 | Undefined | None
#JTC00000886 | Solved | CAT 2 | Steve Dumont | 9 ASOS | 22 | 2019-02-06 20:31:54 | 2019-02-06 20:31:54 | None | Lost sound in dome | No | None | Steve Dumont | 2019-03-26 17:35:06 | Undefined | None
#JTC00000887 | Solved | CAT 3 | Robert Gaines | 9 ASOS | 22 | 2019-02-06 20:35:27 | 2019-02-06 20:35:27 | None | A-10 gun run takes anywhere from 5 - 10 minutes. | No | None | Robert Gaines | 2019-03-26 17:35:08 | Undefined | None
#JTC00000891 | Solved | CAT 2 | Steve Dumont | 9 ASOS | 22 | 2019-02-07 17:55:34 | 2019-02-07 17:55:34 | None | Student 2 didn't run up properly | No | None | Steve Dumont | 2019-03-26 17:35:17 | Undefined | None
#JTC00000892 | Solved | CAT 2 | Robert Gaines | 9 ASOS | 22 | 2019-02-07 17:57:31 | 2019-02-07 17:57:31 | None | Q-Fires crashed during training event | No | None | Robert Gaines | 2019-03-26 17:35:19 | Undefined | None
#JTC00000894 | Solved | CAT 2 | Steve Dumont | 9 ASOS | 22 | 2019-02-07 18:02:53 | 2019-02-07 18:02:53 | None | IG3/projectors 5 and 6 blank | No | None | Steve Dumont | 2019-03-26 17:35:23 | Undefined | None
#JTC00000895 | Solved | CAT 2 | Robert Gaines | 9 ASOS | 22 | 2019-02-07 21:46:09 | 2019-02-07 21:46:09 | None | System did not shut down after 5 attempts | No | None | Robert Gaines | 2019-03-26 17:35:25 | Undefined | None
#JTC00000896 | Solved | CAT 2 | Robert Gaines | 9 ASOS | 22 | 2019-02-08 14:25:37 | 2019-02-08 14:25:37 | None | Projector 3 and 4 projecting wrong size picture | No | None | Robert Gaines | 2019-03-26 17:35:27 | Undefined | None
#JTC00000919 | Solved | CAT 2 | Steve Dumont | 9 ASOS | 22 | 2019-02-21 01:18:40 | 2019-02-21 01:18:40 | None | Student Station 1 transmit function failed; audio cables are worn and shorting out--new cables needed | No | None | Steve Dumont | 2019-03-26 17:36:16 | Undefined | None
#JTC00000920 | Hold | CAT 2 | Steve Dumont | 9 ASOS | 22 | 2019-02-21 01:23:20 | 2019-02-21 01:23:20 | Web form | IG8/PRJ8 Projector Cable Faulty; troubleshot cables and identified single cable non functional--restored comms using single cable 4096x2160@29hz | No | Cables are out of stock | Steve Dumont |  | Root Cause - Hardware Monitor Cable | Monitor Cable
#JTC00000923 | Solved | CAT 2 | Steve Dumont | 9 ASOS | 22 | 2019-02-22 14:15:11 | 2019-02-22 14:15:11 | None | Student 2 lost rover | No | None | Steve Dumont | 2019-03-26 17:36:26 | Undefined | None
#JTC00000925 | Solved | CAT 2 | Steve Dumont | 9 ASOS | 22 | 2019-02-22 18:12:15 | 2019-02-22 18:12:15 | None | VRSG/MACE crashed at RP station | No | None | Steve Dumont | 2019-03-26 17:36:30 | Undefined | None
#JTC00000943 | Hold | CAT 3 | Steve Dumont | 9 ASOS | 22 | 2019-02-26 21:12:18 | 2019-02-26 21:12:18 | None | Shutter function not working from DOC to turn off light emissions from projectors | No | None | Steve Dumont |  | Root Cause - Visual Projector Failure (SONY) | Projector Failure (SONY)
#JTC00000750 | Solved | CAT 2 | Robert Gaines | DMOC | 23 | 2019-01-03 19:24:28 | 2019-01-03 19:24:28 | None | IG-8 Will not connect | No | None | Robert Gaines | 2019-03-26 17:30:18 | Undefined | None
#JTC00000864 | Solved | CAT 2 | Skip Hamilton | DMOC | 23 | 2019-01-31 16:41:30 | 2019-01-31 16:41:30 | None | Solid stae drive unable to be scanned | No | None | Skip Hamilton | 2019-03-26 17:34:21 | Undefined | None
#JTC00000865 | Solved | CAT 2 | Skip Hamilton | DMOC | 23 | 2019-01-31 16:49:58 | 2019-01-31 16:49:58 | None | System 2 Upgrade | No | None | Skip Hamilton | 2019-03-26 17:34:23 | Undefined | None
#JTC00001000 | Open | CAT 2 | Robert Gaines | DMOC | 23 | 2019-03-20 15:50:59 | 2019-03-20 15:50:59 | None | FW: Issues with the DOME | No | None | Robert Gaines |  | Undefined | None
#JTC00000849 | Hold | CAT 2 | Steve Dumont | 607 ASOG | 26 | 2019-01-30 11:38:38 | 2019-01-30 11:38:38 | Web form | IG 8 has a faulty dp cable | No | Waiting for SIM OPR to confirm new cable was recieved | Steve Dumont |  | Root Cause - Hardware Monitor Cable | Monitor Cable
#JTC00000881 | Solved | CAT 3 | Robert Gaines | 607 ASOG | 26 | 2019-02-06 11:39:58 | 2019-02-06 11:39:58 | None | MACE not showing high res imagery paths for S. Korea | No | None | Robert Gaines | 2019-03-26 17:34:56 | Undefined | None
#JTC00000979 | Pending | CAT 2 | Robert Gaines | 607 ASOG | 26 | 2019-03-13 05:01:07 | 2019-03-13 05:01:07 | None | black dot in the visual of ranger 1 | No | None | Robert Gaines |  | Root Cause - Hardware Ranger 47 | Ranger 47
#JTC00000754 | Solved | CAT 2 | Robert Gaines | 26 STS | 28 | 2019-01-08 15:33:59 | 2019-01-08 15:33:59 | None | Projector values are doubled in DOC Panel | No | None | Robert Gaines | 2019-03-26 17:30:28 | Undefined | None
#JTC00000758 | Solved | CAT 2 | Steve Dumont | 26 STS | 28 | 2019-01-09 16:46:56 | 2019-01-09 16:46:56 | None | DIScover- Failure to start on daily start-up procedure | No | None | Steve Dumont | 2019-03-26 17:30:37 | Undefined | None